# IT Transformation Guide: Complete Implementation Framework

A Comprehensive Guide to Transforming from Development-Focused IT to Modern Orchestration Model

## Executive Summary

### The Challenge

Your IT organization has historically focused on internal software development. However, the modern IT landscape requires orchestrating a complex ecosystem of:

- SaaS platforms (Salesforce, ServiceNow, etc.)

- Internal custom development (where it adds unique value)

- System integrations (APIs, data flows, events)

- Data platforms (analytics, AI/ML)

- Cloud infrastructure (scalable, modern)

Your current structure—organized around programming languages and software products with developers, testers, and functional analysts—isn't equipped for this reality.

### The Solution

Transform to a modern IT organization with:

- Stream-Aligned Teams: Cross-functional teams owning business domains (not technology stacks)

- Platform Teams: Providing self-service infrastructure (integration, data, DevOps)

- Architecture Practice: Ensuring coherence and standards across the ecosystem

- Data & AI Capability: Turning data into competitive advantage

- Vendor Management: Optimizing SaaS and partner relationships

- Product Ownership: Business-aligned leaders driving outcomes, not outputs

### The Return

- Faster delivery: 30-50% reduction in lead time

- Better business alignment: 70% capacity on new features vs. 20% today

- Data-driven decisions: Analytics and AI capabilities

- Reduced integration costs: 40-60% savings through platforms

- SaaS optimization: €300K+/year savings

### Critical Success Factors

- Invest in architecture first and hire an Enterprise Architect (Month 1-2) - they design everything else and this prevents costly integration mistakes

- Start with pilots, not big bang - prove the model with 1-2 teams

- Invest in platforms early - integration and data platforms are foundational

- Data before AI - get to 90%+ data quality before heavy AI investment

- Heavy change management - 40% of effort is people, not technology

- Business engagement from day 1 - Product Owners from business side

- Don't try to change everything at once - Your developers, testers, and functional analysts are valuable; evolve their roles rather than replace them

- Create clear swim lanes - Be explicit about when to build vs. buy vs. integrate

- Build vendor management muscle - SaaS relationships need active management

- Don't abandon Agile - But recognize it needs adaptation for SaaS implementation and larger programs

- Start small with AI - Don't build a large AI team until you have data foundations in place

The key insight is that your organization needs to evolve from a "development factory" to a "technology orchestrator" - still building some things, but increasingly integrating, configuring, and governing a complex ecosystem of internal and external systems.

## Current State Assessment

### Current IT Structure

Leadership:

- Head of IT Applications

- Operations Manager

Teams:

- Several teams led by Team Success Managers

- Teams consist of: Developers, Testers, Functional Analysts

- Teams organized by technology or product (e.g., "Java team," "SAP team")

- Working via Scrum methodology

Missing Capabilities:

- ❌ No architects (enterprise, solution, data, security)

- ❌ No business analysts (have functional analysts, not same role)

- ❌ No product owners with authority

- ❌ No project managers for complex initiatives

- ❌ No integration specialists or platform

- ❌ No data engineers or data scientists

- ❌ No vendor management capability

### Current Challenges

Technical Challenges:

- Point-to-point integrations (brittle, hard to maintain)

- No standardized integration approach

- Data scattered across systems

- Technical debt accumulating

- Difficult to integrate SaaS solutions

Organizational Challenges:

- Teams organized by technology, not business outcomes

- Unclear ownership of business domains

- Handoffs between teams slow things down

- Business frustrated with IT responsiveness

- Cannot leverage data for insights or AI

Capability Gaps:

- No architecture practice (decisions made ad-hoc)

- No platform thinking (every team builds everything)

- Limited SaaS evaluation expertise

- No data platform or governance

- Vendor relationships managed reactively

### Current Capacity Allocation

Estimated time allocation:

- 50% - Maintenance, technical debt, "keeping lights on"

- 30% - Small enhancements and bug fixes

- 20% - New features and projects

Business value delivered: ~€10M/year (estimated based on new capabilities enabled)

### Current IT Spend

- IT Personnel: €5M/year (~50 people × €100K average)

- Infrastructure & Operations: €1.5M/year

- SaaS Subscriptions: €800K/year (likely underreported due to shadow IT)

- Projects/Contractors: €1M/year

- Total: €8.3M/year

### Critical Gaps to Address

Your current setup is missing several key capabilities:

Strategic & Architecture Layer

- Enterprise/Solution Architects - Essential for SaaS integration, system landscapes, data architecture, and AI strategy. They ensure systems work together coherently and make build-vs-buy decisions

- Data Architects/Data Engineers - Critical for your AI ambitions and managing data across multiple systems

- Security Architect - Increasingly important with SaaS vendors and data initiatives

Business-IT Bridge

- Business Analysts - To translate business needs and evaluate SaaS solutions against requirements

- Product Owners/Managers - True product ownership beyond what Scrum Masters typically provide

- Vendor/Contract Managers - To manage SaaS relationships, contracts, and vendor performance

Delivery & Integration

- Integration Specialists - For API management, iPaaS platforms, and system connectivity

- Project/Program Managers - For larger initiatives that span multiple teams/vendors

- DevOps/Platform Engineers - To manage hybrid environments (on-prem + cloud + SaaS)

## Future State Vision

### Vision Statement

"An IT organization that orchestrates internal development, SaaS platforms, and AI/ML capabilities to deliver business outcomes at speed, with data-driven decisions and seamless integration across our technology ecosystem."

### Future IT Structure

Tier 1: Leadership

CTO

├── Head of IT Applications (existing, evolved)

├── Head of Enterprise Architecture (NEW)

├── Head of Data & AI (NEW)

├── Operations Manager (existing, evolved to Head of Platform Engineering)

└── Head of Vendor & Partner Management (NEW)

Tier 2: Enabling Functions (support all teams)

- Architecture Guild (enterprise, solution, data, security architects)

- Platform/DevOps Team (infrastructure, CI/CD, integration)

- Data Engineering Team (pipelines, governance, ML platforms)

- Center of Excellence for AI/ML

- Vendor Management Office

Tier 3: Delivery Teams

Reorganize from purely functional Scrum teams to:

Stream-Aligned Teams (product-focused):

- Cross-functional teams owning specific business domains/products

- Can build custom software OR configure/integrate SaaS solutions

For example:

- Customer Experience Team (owns CRM, customer portal, e-commerce)

- Order-to-Cash Team (owns order processing, invoicing)

- Supply Chain Team (owns procurement, inventory, logistics)

- Product Data Team (owns product information, catalogs, pricing)

- Finance & Reporting Team (owns financial systems, reporting)

- HR & Operations Team (owns HR systems, internal operations)

Each team has:

- Product Owner (from business side)

- Business Analyst

- Developers (4-6, mixed skills)

- Testers (1-2)

- Virtual: Solution Architect (20-40% allocation)

Platform Teams:

- Integration Platform Team (APIs, iPaaS, event streaming)

- Data Platform Team (data warehouse/lake, quality, catalog)

- AI/ML Platform Team (ML ops, model deployment)

- DevOps/Platform Engineering Team (CI/CD, infrastructure, monitoring)

Complicated subsystem teams (if needed):

- For highly specialized technical areas

### Future Capacity Allocation

Target time allocation:

- 25% - Maintenance (reduced from 50%)

- 10% - Technical debt (explicit, managed)

- 65% - New features and projects (increased from 20%)

Business value delivered: €20M/year

### Future IT Spend (Steady State, Year 3)

- IT Personnel: €7.5M/year (75 people)

- Infrastructure & Platforms: €2.5M/year

- SaaS Subscriptions: €500K/year (consolidated)

- Training & Development: €300K/year

- Total: €10.8M/year

Incremental cost: €2.5M/year Incremental value: €10M+/year Net benefit: €7.5M+/year

### Organizational Principles

Move from Scrum-only to hybrid delivery:

- Product mode for ongoing platform/product development (Scrum/Kanban)

- Project mode for large implementations (especially SaaS rollouts, AI projects)

- BAU mode for vendor management and minor enhancements

Create clear decision rights:

- Architecture Review Board (for tech decisions, vendor selection)

- Data Governance Board (for data strategy, AI ethics)

- Portfolio Management (for prioritization across build/buy/integrate)

Build new competencies:

- SaaS evaluation and vendor management

- API/integration architecture

- Data governance and quality

- Cloud-native development

- AI/ML engineering and MLOps

## Organizational Structure

### Organization Chart - Target State

CTO

│

├─── Head of IT Applications

│    │

│    ├─── Stream-Aligned Teams (6-7 teams)

│    │    ├─── Customer Experience Team

│    │    │    ├─── Product Owner (reports to VP Sales)

│    │    │    ├─── Business Analyst

│    │    │    ├─── 4-5 Developers

│    │    │    ├─── 1-2 Testers

│    │    │    └─── Solution Architect (shared, 20-40%)

│    │    │

│    │    ├─── Order-to-Cash Team

│    │    │    └─── [similar structure]

│    │    │

│    │    ├─── Supply Chain Team

│    │    ├─── Product Data Team

│    │    ├─── Finance & Reporting Team

│    │    └─── HR & Operations Team

│    │

│    └─── Business Analysts (pool/shared if needed)

│

├─── Head of Enterprise Architecture

│    │

│    ├─── Enterprise Architect

│    ├─── Solution Architects (3-4)

│    ├─── Data Architect

│    └─── Security Architect

│

├─── Head of Data & AI

│    │

│    ├─── Data Platform Team

│    │    ├─── Data Engineering Lead

│    │    ├─── Data Engineers (3-4)

│    │    ├─── Analytics Engineer (1)

│    │    └─── Data Governance Specialist

│    │

│    └─── AI/ML Center of Excellence

│         ├─── Data Scientists (2-3)

│         ├─── ML Engineers (2-3)

│         └─── AI Product Manager

│

├─── Head of Platform Engineering (evolved from Operations Manager)

│    │

│    ├─── Integration Platform Team

│    │    ├─── Integration Architect

│    │    ├─── Integration Engineers (3-4)

│    │    └─── Technical Writer

│    │

│    ├─── DevOps/Platform Engineering Team

│    │    ├─── Platform Engineering Lead

│    │    ├─── Platform Engineers (3-4)

│    │    └─── Site Reliability Engineer

│    │

│    └─── Operations & Support

│

└─── Head of Vendor & Partner Management

│

├─── Vendor Managers (1-2)

├─── Contract Administrator

└─── Vendor Security Analyst

### Reporting Relationships

Key Principle: Product Owners report to business, not IT

Stream-Aligned Teams:

- Developers, Testers, BA → Report to Head of IT Applications

- Product Owner → Reports to Business VP (e.g., VP Sales, VP Operations)

- Solution Architect → Reports to Head of Enterprise Architecture (matrixed to teams)

Platform Teams:

- All members → Report to Head of Platform Engineering or relevant head

- Serve stream-aligned teams as internal customers

Architects:

- All → Report to Head of Enterprise Architecture

- Enterprise Architect → Peer to other heads, reports to CTO

Data & AI:

- All → Report to Head of Data & AI

- Data Architect → Dual reporting: Head of Data & AI + Head of EA (dotted line)

### Stream-Aligned Teams

What Are Stream-Aligned Teams?

The Core Principle

Platform teams provide internal products that stream-aligned teams consume. They turn complexity into simplicity.

Stream-aligned teams own a value stream - a flow of work that delivers business value to customers or internal users. Instead of organizing by technology (the Java team, the .NET team, the ERP team), you organize by business capability. Team has end-to-end responsibility for a specific business capability.

Example Structure for Your Organization

Let's say you're a manufacturing company. Instead of organizing by technology (Java, .NET), by component (frontend, backend, database) or product (SAP, Salesforce):

- ❌ Team A: SAP developers

- ❌ Team B: .NET developers

- ❌ Team C: Integration team

You organize by business domain:

- ✅ Order-to-Cash Team: Owns everything from order entry through invoicing (might use SAP, custom apps, Salesforce)

- ✅ Supply Chain Team: Owns procurement, inventory, logistics (might use SAP, custom WMS, external logistics APIs)

- ✅ Customer Experience Team: Owns customer portal, self-service, notifications (might use custom apps, Zendesk, Twilio)

- ✅ Product Data Team: Owns product information, pricing, catalogs (might use PIM system, custom apps, e-commerce platform)

Why Stream-Aligned Teams?

Problems with current model (organized by technology):

- Handoffs between teams slow delivery

- No clear ownership of business outcomes

- "Not my team" mentality when issues arise

- Business stakeholders don't know who owns what

- Conway's Law: architecture mirrors org structure (siloed architecture)

Benefits of stream-aligned teams:

- ✅ Fast flow of value (minimal handoffs)

- ✅ Clear ownership and accountability

- ✅ Teams understand business context

- ✅ Business stakeholders have clear partner

- ✅ Teams can make decisions independently

- ✅ Architecture evolves toward business domains

### Platform Teams

What Are Platform Teams?

Definition: Teams that provide internal products (platforms) that reduce cognitive load for stream-aligned teams and accelerate their delivery.

Platform = Internal Product:

- Stream-aligned teams are the customers

- Platform team treats platform as a product

- Self-service capabilities

- Documentation, support, and continuous improvement

Why Platform Teams?

Without Platform Teams:

- Every stream team builds their own integrations → duplicate work, inconsistent patterns

- Every stream team manages their own CI/CD → different approaches, reinventing wheel

- Every stream team handles their own data pipelines → no reusability, quality issues

- Result: Cognitive overload, slow delivery, technical debt

With Platform Teams:

- Integration Platform team provides reusable connectors → stream teams plug and play

- DevOps Platform team provides CI/CD pipelines → stream teams just deploy

- Data Platform team provides data access → stream teams query data easily

- Result: Stream teams focus on business value, accelerated delivery

### Architecture Function

Why Architecture Matters

Without Architecture Practice:

- Technology decisions made ad-hoc by individual teams

- Inconsistent approaches across teams (10 different ways to do same thing)

- Integration spaghetti (every team integrates differently, point-to-point connections everywhere)

- Vendor sprawl (3 teams buy 3 different tools for same purpose)

- Technical debt accumulates unmanaged

- Security gaps and compliance risks (each team implementing auth differently)

- Redundant SaaS purchases (3 teams buying different project management tools)

- Data silos (customer data in 7 places, all slightly different)

- Impossible AI initiatives (can't find/trust/access data)

- No one sees the big picture

With Architecture Practice:

- Strategic technology direction

- Consistent patterns and standards

- Coherent system landscape

- Informed technology decisions

- Managed technical debt

- Security and compliance by design

- Enablement, not gatekeeping

Enterprise Architect - Practical, Not Ivory Tower

The wrong EA can be counterproductive.

What you DON'T want:

- ❌ EA who creates 100-page architecture documents nobody reads

- ❌ EA who says "no" to everything without alternatives

- ❌ EA who doesn't understand business urgency ("that'll take 6 months to evaluate")

- ❌ EA who speaks only in abstract concepts (TOGAF phases, Zachman framework)

- ❌ EA who never talks to developers or business

- ❌ EA who creates governance bottlenecks

- ❌ EA who is disconnected from reality of operations

Result: EA ignored, teams work around them, no value delivered. Waste of €130-160K/year.

The Solution: "Pragmatic Servant Leader" Enterprise Architect:

- ✅ EA who has built real systems (not just drew diagrams)

- ✅ EA who understands business urgency (sometimes "good enough now" beats "perfect later")

- ✅ EA who is hands-on when needed (can review code, debug integration issues)

- ✅ EA who enables teams ("here are 3 options, my recommendation, your call")

- ✅ EA who speaks business language (revenue, cost, risk - not just technical)

- ✅ EA who builds relationships (developers trust them, business respects them)

- ✅ EA who creates just enough documentation (what's useful, not comprehensive)

- ✅ EA who facilitates good decisions rather than makes all decisions

Result: EA is trusted advisor, teams seek their input, decisions are better, value is clear.

### Data & AI Capability Function

This is your future competitive advantage, but it requires solid foundations.

Head of Data & AI role

Reports to CTO, peers with other IT heads.

Responsibilities:

- Data strategy and roadmap

- AI/ML strategy

- Data governance program

- Analytics strategy

- Partnerships with business for data initiatives

- Building data culture

Data Maturity Journey

Most organizations need to progress through stages. Don't skip stages.

Phase 0: Data Chaos (Your likely starting point)

- Data scattered across systems

- No centralized repository

- Unknown data quality

- Manual reporting (Excel hell)

- No data governance

- Focus: Survive, get basic reports

Phase 1: Data Foundation (Months 1-12)

Focus 100% on getting data foundations right before heavy AI investment.

- Data warehouse/lake established

- Data quality measured and improving

- Core data domains identified and owned

- Basic governance in place

- Self-service analytics starting

- Focus: Build solid foundation

Phase 2: Analytics Capability (Months 6-18)

Once data foundations are solid, build analytics capability.

- High data quality (90%+ for tier 1 data)

- Comprehensive data catalog

- Self-service analytics mature

- Descriptive and diagnostic analytics

- Culture shift toward data-driven decisions

- Focus: Enable business with data insights

Phase 3: Predictive AI/ML Capability (Months 18-36+)

Only after data and analytics foundations are solid.

- Predictive models in production

- ML platform operational

- Data science team productive

- AI use cases delivering value

- MLOps practices established

Phase 4: Prescriptive (Months 36+)

- Prescriptive analytics (recommend actions)

- Automated decision-making

- AI embedded in business processes

- Competitive advantage from data/AI

- Focus: Transform business with AI

CRITICAL: Most organizations fail because they try to jump to Phase 3-4 without Phase 1-2 foundation.

### Vendor & Partner Management

This is entirely new capability for your organization.

Vendor Management Framework

Why Vendor Management Matters:

Without vendor management:

- Duplicate SaaS purchases (3 teams buy 3 project management tools)

- Poor contracts (no exit clauses, locked into unfavorable terms)

- Vendor sprawl (100+ vendors, nobody managing them)

- Security risks (vendors not vetted)

- Cost overruns (auto-renewals, unused licenses)

- Vendor performance issues not addressed

With vendor management:

- Consolidated vendor portfolio

- Optimized contracts and costs

- Vendor security and compliance

- Performance management and accountability

- Strategic vendor partnerships

Critical Vendor Management Practices:

Vendor Tiering:

- Tier 1 (Strategic): Mission-critical, high spend, quarterly exec reviews (e.g., your ERP, CRM)

- Tier 2 (Important): Significant but not critical, bi-annual reviews (e.g., HR system, project management)

- Tier 3 (Tactical): Low risk/spend, annual review (e.g., survey tools, collaboration tools)

SLA Management: Don't just accept vendor's standard SLAs. Define what matters:

- Uptime requirements

- Response/resolution times

- Data backup/recovery

- Performance metrics

- Support availability

Vendor Consolidation: You'll discover your teams have bought overlapping tools. Vendor management actively consolidates:

- "We have 4 different project management tools across teams → standardize on 1-2"

- "3 teams bought different API testing tools → platform team provides standard tool"

### Product Owners and Project Managers

Product Owner (PO) in Stream-Aligned Teams

This is different from a Scrum Master facilitating Scrum ceremonies.

Responsibilities:

- Product vision: What should this domain/product become?

- Backlog prioritization: What gets built next and why?

- Stakeholder management: Balancing competing business needs

- ROI focus: Ensuring work delivers business value

- Roadmap planning: 3-6 month forward view

- Go/no-go decisions: When to release, when to pivot

- Metrics ownership: Defining and tracking success metrics

Profile:

- Deep business domain knowledge

- Strategic thinking ability

- Decisive - comfortable making trade-offs

- Technical enough to understand feasibility

- Empowered by leadership to make decisions

- Often comes from business side, not IT

Key difference from BA:

- BA: "What should we build?" (the requirements)

- PO: "What should we build first, and why?" (the strategy)

In SaaS context: PO decides: "We'll use Salesforce for sales but custom-build our quoting engine because it's unique to our business." BA then defines requirements for the custom quoting engine.

PO + Business Analyst: How They Work Together

This relationship is critical and often confusing.

Clear Separation of Responsibilities

Product Owner:

- WHAT to build (prioritization)

- WHY we're building it (business value, outcomes)

- WHEN to build it (roadmap, sprint prioritization)

- WHO it's for (user segments, stakeholders)

- Success criteria (metrics, OKRs)

Business Analyst:

- HOW it should work (detailed requirements, user flows)

- WHAT the detailed requirements are (fields, validations, rules)

- Testing (UAT coordination, acceptance testing)

- Change management (training, documentation, rollout)

- Process design (current state, future state, process maps)

Product Owners vs. Project Managers

The Critical Distinction

This is one of the most confusing aspects of the transformation. Let me make it crystal clear.

Product Owner

= Owns the product/solution for its lifetime

= WHAT we build and WHY (the product/solution itself)

Project Manager

= Owns a specific initiative from start to end

= WHEN, WHO, and HOW MUCH (the delivery of complex initiatives)

Think of it this way:

- Product Owner: Owns a house (maintains it, improves it, lives in it forever)

- Project Manager: Manages the construction or renovation project (temporary engagement)

When You Need Each

Product Owner (Always for stream-aligned teams):

- ✅ Every stream-aligned team needs a Product Owner

- ✅ Permanent role (years)

- ✅ Owns business domain and its technology

- ✅ Continuous delivery and improvement

Project Manager (Only for complex initiatives):

- ✅ Large SaaS implementations (ERP, CRM, HCM)

- ✅ Multi-team projects (3+ teams)

- ✅ Long duration (6+ months)

- ✅ Large budget (>€250K)

- ✅ Complex dependencies

- ✅ High executive visibility

Many projects DON'T need a PM:

- ❌ Single team work

- ❌ Short duration (<4 months)

- ❌ Small scope

- ❌ Product Owner + Tech Lead sufficient

### The Business Analyst Role

Why Business Analysts are Critical to Your Success

The Reality: Product Owners Can't Do Everything

Product Owner's Dilemma:

- PO needs to be strategic (roadmap, vision, stakeholder management)

- PO needs to be tactical (backlog, sprint planning, acceptance)

- PO needs to be detailed (requirements, acceptance criteria, edge cases)

- Problem: Can't be all three simultaneously, especially part-time PO

Business Analyst Fills the Gap:

- BA is the "execution partner" for the PO

- PO provides direction ("What" and "Why")

- BA figures out details ("How specifically" and "What about edge cases")

- BA is the multiplier that makes part-time PO sustainable

Without BA:

- ❌ PO drowns in detail work

- ❌ Requirements are thin (developers constantly asking questions)

- ❌ Edge cases missed (bugs, rework)

- ❌ PO can't focus on strategic work

- ❌ Part-time PO impossible

With BA:

- ✅ PO focuses on strategy and prioritization

- ✅ Requirements are detailed and clear

- ✅ Edge cases identified upfront

- ✅ Developers can work efficiently

- ✅ Part-time PO sustainable

## Team Evolution Stories: What Happens to Current People

Let's talk about specific scenarios for your current team members.

### Scenario: Senior Developer (10 years experience)

Current role: Senior .NET developer on one of your teams, technically strong, some business domain knowledge (e.g., finance systems).

Evolution options:

Option A: Stay as Senior/Staff Developer

- Remains in Product Data Team (new stream-aligned structure)

- Continues development work but with clearer business focus

- Learns some new technologies (cloud, APIs, integration patterns)

- Mentors junior developers

- Participates in architecture reviews

- Career path: Staff Developer → Principal Developer

Option B: Become Solution Architect

- Leverages technical depth and business knowledge

- Gets training in architecture practices and patterns

- Starts embedded 40% with old team, 20% with 2 other teams

- Develops architecture skills over 12-18 months

- Career path: Solution Architect → Senior SA → Enterprise Architect

Option C: Become Product Owner

- If interested in business side and has domain expertise

- Needs training in product management

- Shifts from technical to business-technical hybrid

- Works closely with business stakeholders

- Career path: Product Owner → Senior PO → Head of Product

How you support them:

- Career conversation: "Here are your options. What excites you?"

- Training budget: Conferences, courses, certifications

- Transition plan: 6-12 months to make the shift

- Mentorship: Pair them with external architect consultant initially

- Safety net: "Try it for 6 months, we can adjust if it's not the right fit"

### Scenario: Functional Analyst (5 years experience)

Current role: Functional analyst who understands both business processes and systems, bridges business and IT, writes functional specifications.

Evolution options:

Option A: Become Business Analyst

- Natural evolution of current role

- Training in modern BA techniques (user stories, journey mapping, SaaS evaluation)

- Embeds in stream-aligned team

- More business-facing, less technical documentation

- Career path: BA → Senior BA → Lead BA

Option B: Become Product Owner

- If they have strong business relationships and strategic thinking

- Shift from "what to build" to "what to build first"

- Training in product management, metrics, roadmapping

- Career path: PO → Senior PO → Group PM

Option C: Specialize in SaaS Configuration

- If they're technical enough and interested

- Become Salesforce admin, ServiceNow configurator, etc.

- Still analysis work, but hands-on with tools

- Career path: SaaS Specialist → Senior SaaS Specialist → SaaS Architect

How you support them:

- Recognize they're already doing much of this work

- Formalize the role and provide training

- Give them authority and tools

- Connect them with business stakeholders directly

- Certifications: CBAP, Salesforce Admin, Agile BA, etc.

### Scenario: Team Success Manager / Scrum Master (3 years)

Current role: Facilitates Scrum ceremonies, coaches team, removes blockers, but doesn't own product decisions.

Evolution options:

Option A: Stay as Scrum Master

- Role still valuable in stream-aligned teams

- Evolves to also coach on architecture practices, platform usage

- More focus on team health and continuous improvement

- Less demand for this role (fewer pure SMs needed)

- Career path: Scrum Master → Agile Coach → Head of Agile Practice

Option B: Become Product Owner

- If they have business domain knowledge

- Big shift from facilitator to decision-maker

- Need to develop product management skills

- Business stakeholder relationships critical

- Career path: PO → Senior PO → Group PM

Option C: Move to Operations/Platform Team

- If they're more operationally inclined

- Could become Platform team coordinator

- Focus on platform team operations and user support

- Career path: Platform Operations → Platform Manager

Option D: Transition to Organizational Change

- If they love the people/coaching side

- Help with transformation change management

- Support teams through evolution

- Career path: Change Manager → Head of Transformation

How you support them:

- Honest conversation: Some SM roles will go away

- Early identification of which path interests them

- Training and transition support

- Possibly 12-18 months to make the shift

- Some may need to leave (not all will find fit)

### Scenario: Junior Developer (2 years experience)

Current role: Junior developer, still learning, mostly implements what senior developers design.

Evolution options:

Option A: Continue as Developer

- Stays in stream-aligned team

- Grows technical skills in context of business domain

- Learns cloud, APIs, integration, SaaS configuration

- Eventually becomes mid-level, then senior

- Career path: Junior → Mid → Senior → Staff Developer

Option B: Specialize in Testing/QA

- If they show interest in quality

- Learn test automation, quality practices

- Valuable role in stream-aligned teams

- Career path: QA Engineer → Senior QA → Quality Engineering Lead

Option C: Specialize in Data Engineering

- If they show interest in data/analytics

- Learn SQL, ETL, data modeling

- Join Data Platform team

- Career path: Data Engineer → Senior DE → Data Engineering Lead

How you support them:

- Don't overwhelm with change

- Provide clear learning paths

- Pair with senior people

- Let them experiment and find their passion

- Patience - they'll grow into roles over 3-5 years

### Scenario: Operations Team Member

Current role: Maintains infrastructure, monitors systems, handles incidents, manages deployments.

Evolution options:

Option A: Join DevOps/Platform Engineering Team

- Natural evolution

- Learn cloud platforms, infrastructure as code, CI/CD

- Shift from reactive to proactive

- Build platforms that teams use

- Career path: Platform Engineer → Senior PE → Platform Engineering Lead

Option B: Specialize in SRE (Site Reliability Engineering)

- If they're interested in reliability and automation

- Learn monitoring, observability, incident management

- More strategic than traditional ops

- Career path: SRE → Senior SRE → SRE Manager

Option C: Join Integration Platform Team

- If they're interested in integration/middleware

- Learn iPaaS platform, API management

- Operational focus but for integration platform

- Career path: Integration Operations → Platform Team Lead

How you support them:

- Heavy training investment (this is big shift)

- Pair with experienced DevOps engineers (hire or contract)

- Start with pilot - let them learn by doing

- Recognize some may not want to change (that's okay)

- Clear that "keep the lights on" role is evolving

### General Principles for Team Evolution:

- Career conversations with everyone within first 3 months

- Multiple options - not one-size-fits-all

- Training budgets - significant investment per person

- Time to transition - 6-18 months depending on role

- Safety nets - try new role, can adjust

- Honest about fit - not everyone will make it (10-15% attrition expected)

- Celebrate transitions - recognize people growing

Internal-first hiring - fill 60%+ of new roles internally

### Career Paths in New Organization

Critical to show people how they can grow:

Developer Career Path:

- Junior Developer → Developer → Senior Developer → Staff Developer → Principal Developer

- Alternative: Senior Developer → Solution Architect → Enterprise Architect

- Alternative: Senior Developer → Platform Engineer → Platform Engineering Lead

Business Analyst Career Path:

- Junior BA → Business Analyst → Senior BA → Lead BA → Head of Business Analysis

- Alternative: Senior BA → Product Owner → Head of Product

Data Career Path:

- Junior Data Engineer → Data Engineer → Senior Data Engineer → Data Engineering Lead

- Alternative: Data Analyst → Data Scientist → Senior Data Scientist → Head of Data Science

Product Owner Career Path:

- Associate Product Owner → Product Owner → Senior Product Owner → Group Product Manager → Head of Product

Architecture Career Path:

- Solution Architect → Senior Solution Architect → Domain Architect → Enterprise Architect → Head of EA

Make these paths clear and provide development plans.

## Portfolio Management & Resource Coordination

Current Reality:

- 50+ projects in flight or pipeline

- 200+ change requests backlog

- All competing for same IT resources

- No clear prioritization mechanism

- "Squeaky wheel gets the grease"

- IT overwhelmed and reactive

New Challenge:

- Stream-aligned teams have dedicated resources

- But what if 3 Product Owners all want same developer?

- Who decides which project gets priority?

- How do we balance across business domains?

- Who says "no" at enterprise level?

This requires a Portfolio Management function.

### Solution: Multi-Level Governance

You need governance at three levels:

Level 1: Domain (Product Owner decides)

↓

Level 2: IT Portfolio (IT Leadership decides)

↓

Level 3: Enterprise Portfolio (Executive Team decides)

Let me detail each:

### Level 1: Domain-Level (Product Owner)

What PO Manages:

- Within their domain: Full prioritization authority

- Customer Experience PO decides priority of all customer portal work

- Order-to-Cash PO decides priority of all invoicing/order work

PO's Team Resources (Dedicated):

- 4-5 developers

- 1-2 testers

- 1 BA

- 20-40% of Solution Architect

What PO Can't Manage:

- ❌ Resources from other teams

- ❌ Shared platform resources (integration, data, infrastructure)

- ❌ Cross-domain initiatives requiring multiple teams

- ❌ Enterprise-wide changes

Example:

- Sales VP wants 10 features for customer portal

- Customer Experience PO prioritizes these 10 features

- PO has dedicated team, makes decisions independently

- No conflict with other domains (they have their own teams)

### Level 2: IT Portfolio Management

WHO: IT Portfolio Management function

Role: Head of Portfolio Management (or IT PMO)

Reports To: CTO
Peers: Head of IT Applications, Head of EA, Head of Data & AI

Team:

- Head of Portfolio Management (1)

- Portfolio Analysts (1-2)

- Project Managers (2-3, assigned to major initiatives)

What Portfolio Management Does

1. Intake & Demand Management

Single Front Door for all IT requests:

- New projects

- Major change requests

- New systems/vendors

- Cross-domain initiatives

Intake Process:

Request Submitted

↓

Portfolio Analyst Reviews

↓

Small/Domain-Specific → Send to appropriate Product Owner

↓

Large/Cross-Domain → IT Portfolio Review Board

Categorization:

- Tier 1: Single domain, <€50K, <3 months → Product Owner decides

- Tier 2: Cross-domain OR €50-250K OR 3-6 months → Portfolio review

- Tier 3: Enterprise-wide OR >€250K OR >6 months → Executive portfolio

2. Portfolio Prioritization

IT Portfolio Review Board (meets bi-weekly):

Members:

- Head of Portfolio Management (chairs)

- Head of IT Applications

- Head of Enterprise Architecture

- Head of Data & AI

- CFO representative (budget perspective)

- 2 rotating Product Owners (bring business voice)

Reviews:

- All Tier 2 requests

- Cross-domain initiatives

- Resource conflicts

- Portfolio health

Prioritization Framework (Score 1-5 on each):

| Criteria | Weight | Score |
| --- | --- | --- |
| Business Value | 35% | Revenue impact, cost savings, strategic alignment |
| Urgency | 20% | Regulatory, competitive, market window |
| Feasibility | 15% | Technical complexity, risk, dependencies |
| Resource Availability | 15% | Do we have capacity? |
| Strategic Fit | 15% | Aligns with company strategy? |

Total Score = Weighted average
Decisions: Fund, Defer, Reject

Example:

- Request: CRM integration with new marketing automation tool

- Affects: Customer Experience team (CRM) + Marketing team + Integration Platform team

- Score: High business value (4/5), Medium urgency (3/5), High feasibility (4/5), Medium resource availability (3/5), High strategic fit (5/5)

- Decision: Approved, start Q3, assign Project Manager

3. Capacity Management

Track Capacity (Updated Monthly):

| Team | Total Capacity | Committed | Available |
| --- | --- | --- | --- |
| Customer Experience | 5 people | 90% | 10% |
| Order-to-Cash | 6 people | 75% | 25% |
| Supply Chain | 6 people | 80% | 20% |
| Product Data | 5 people | 85% | 15% |
| Finance & Reporting | 4 people | 70% | 30% |
| Integration Platform | 6 people | 95% | 5% ⚠️ |
| Data Platform | 7 people | 85% | 15% |

Red Flags:

- Team >90% committed → Overloaded, can't take new work

- Platform teams >85% → Bottleneck risk

Actions:

- Adjust priorities (defer lower-priority work)

- Add resources (hire, contractors)

- Redirect work to less-loaded teams (if possible)

4. Cross-Domain Coordination

When multiple teams needed:

Example Scenario: New e-commerce platform launch

Teams Involved:

- Customer Experience team (customer portal integration)

- Product Data team (product catalog)

- Order-to-Cash team (order processing)

- Integration Platform team (integrations)

- Data Platform team (analytics)

Portfolio Management Role:

- Assign Project Manager to coordinate

- Capacity reservation across all teams

- Dependency management (team A needs B to finish first)

- Timeline coordination (aligned sprints)

- Steering committee (monthly, all POs + executives)

- Conflict resolution (if teams have competing priorities)

Project Manager coordinates, but Product Owners still make domain decisions.

5. Portfolio Reporting

Monthly Portfolio Dashboard (to CTO and Executive Team):

Projects:

- Active projects: [Count] (by status: green/yellow/red)

- Pipeline: [Count]

- Completed this quarter: [Count]

Resource Utilization:

- Overall capacity: [%]

- Teams at capacity risk: [List]

- Hiring pipeline: [Status]

Business Value:

- Value delivered this quarter: €[X]M

- Forecast for next quarter: €[Y]M

Top Risks:

- [Risk description, impact, mitigation]

- [Risk description, impact, mitigation]

Key Decisions Needed:

- [Decision 1]

- [Decision 2]

### Level 3: Enterprise Portfolio Management

WHO: Executive Team (CEO, CFO, CTO, Business VPs)

WHEN: Quarterly + Ad-hoc for major decisions

WHAT: Enterprise-wide prioritization

Decisions:

- Major investments (>€500K)

- Strategic initiatives (company-wide)

- Resource allocation across departments

- Multi-year roadmap

- Budget allocation

IT Portfolio Management provides:

- Recommendations

- Data and analysis

- Options and trade-offs

- Impact assessment

Executive Team decides:

- Which major initiatives to fund

- Business strategy alignment

- Risk acceptance

- Final prioritization

Example:

- Three major initiatives proposed:

  - New ERP system (€5M, 18 months)

  - Digital customer experience transformation (€3M, 12 months)

  - Data platform and AI (€2M, 12 months)

- Total IT capacity: Can only do 2

- Executive team decides: #2 and #3 (customer focus + data foundation)

- #1 deferred to next year

### Organizational Structure with Portfolio Management

CTO

│

├── Head of IT Applications

│   └── Product Owners + Stream-Aligned Teams

│

├── Head of Enterprise Architecture

│   └── Architects

│

├── Head of Data & AI

│   └── Data Platform + AI Teams

│

├── Head of Platform Engineering

│   └── Integration, DevOps, Operations

│

├── Head of Vendor & Partner Management

│   └── Vendor managers

│

└── Head of Portfolio Management (NEW)

├── Portfolio Analysts (1-2)

├── Project Managers (2-3)

└── Resource Coordinators (if needed)

Size: 3-6 people for 50-75 person IT org

### Key Principles for Portfolio Management

1. Transparency:

- All requests visible

- Prioritization criteria clear

- Decisions documented with rationale

- Status updates regular

2. Data-Driven:

- Prioritize based on business value, not politics

- Track capacity and utilization

- Measure outcomes, not just outputs

3. Consistency:

- Same process for everyone

- No backdoor requests

- Decisions stick (don't re-litigate constantly)

4. Empowerment:

- Product Owners decide within domain (don't micro-manage)

- Portfolio decides cross-domain (don't bottleneck)

- Executive Team decides strategic (don't abdicate)

5. Communication:

- Regular updates

- Clear decision rationale

- Manage expectations proactively

## Application Support & Service Desk

### Current State Assessment (Likely Issues)

Common Problems in Application Support

What's probably happening now:

Issue 1: No Clear Front Door

Users don't know who to call

Some call developers directly (interrupting development)

Some call their "IT friend" (inconsistent)

Some email random IT person

Requests get lost or delayed

Issue 2: Developers Doing Support

Developers interrupted constantly (context switching kills productivity)

Development capacity drained: 30-50% on support (your estimate)

Developers frustrated: "I'm fixing the same issue again instead of building new features"

Junior developers handling complex production issues (learning on the job, risky)

Issue 3: No Triage or Prioritization

Everything is "urgent" (no real urgency assessment)

P1 production issues mixed with "how do I?" questions

Critical issues not escalated fast enough

Low-priority requests take resources from high-priority

Issue 4: Knowledge Not Captured

Same questions asked repeatedly

No knowledge base or documentation

Every support person solves problems from scratch

Knowledge leaves when people leave

Issue 5: No Metrics or Accountability

Don't know: Response times, resolution times, customer satisfaction

No SLAs (Service Level Agreements)

Can't measure if support is improving or degrading

Business frustrated: "IT never responds" (but no data to prove otherwise)

Issue 6: 24/7 Operations Challenge

Shipping and Ports operate 24/7 (vessels don't wait for business hours)

Support only available 8-5 (critical systems fail at night, users stranded)

On-call rotation ad-hoc (developers burned out)

Result:

Business users frustrated (can't get help)

IT team frustrated (constant interruptions)

Systems availability suffers (issues not resolved quickly)

Trust eroded between business and IT

### Future State Vision: Professional Application Support

What Great Application Support Looks Like

For Business Users:

✅ Single point of contact: One phone number, one email, one portal

✅ Fast response: Acknowledged within 1 hour (urgent) or 4 hours (normal)

✅ Status visibility: Users can see status of their request ("assigned to tech, in progress")

✅ Competent help: Support team knows systems, solves most issues without escalation

✅ 24/7 coverage: Critical support available when operations run (especially Shipping/Ports)

✅ Proactive: Support identifies recurring issues, proposes fixes (not just firefighting)

For Development Teams:

✅ Protected time: Developers focus on building (interruptions minimal)

✅ Escalations only: Developers handle Tier 3 only (code bugs, architecture issues)

✅ Feedback loop: Support tells developers about recurring issues (fix root causes)

✅ Runbooks: Clear documentation for support on how to handle common issues

For IT Leadership:

✅ Metrics and visibility: Know response times, resolution times, satisfaction

✅ Predictable: Support operates to SLAs, no surprises

✅ Continuous improvement: Support gets better over time (knowledge grows, recurring issues fixed)

✅ Cost-effective: Right people doing right work (expensive developers not doing Tier 1 support)

### Application Support Structure - Your Organization

Three-Tier Support Model (Standard Best Practice)

┌─────────────────────────────────────────────────────────┐

│ USER (Business Employee, Customer via Portal)           │

└─────────────────────┬───────────────────────────────────┘

│

↓

┌─────────────────────────────────────────────────────────┐

│ TIER 1: SERVICE DESK (Front Line)                      │

│ - First contact, incident logging                       │

│ - Password resets, basic how-to                         │

│ - Triage and route to Tier 2 if needed                 │

│ - Goal: Resolve 30-40% at Tier 1                       │

│ Team: 4-6 people (Service Desk Agents)                 │

│ Skills: Customer service, basic IT, all systems aware   │

└─────────────────────┬───────────────────────────────────┘

│ (Escalate if can't resolve)

↓

┌─────────────────────────────────────────────────────────┐

│ TIER 2: APPLICATION SUPPORT (Technical Support)        │

│ - Complex troubleshooting                               │

│ - System configuration issues                           │

│ - Data fixes, integrations                              │

│ - EDI failures (common in logistics)                    │

│ - Goal: Resolve 50-60% of escalated issues             │

│ Team: 10-12 people (Application Support Engineers)     │

│ Skills: System knowledge, SQL, integrations, debugging  │

│                                                          │

│ Organized by domain:                                    │

│ ├─ Shipping/Ports Support (3-4 people)                 │

│ ├─ Cargo Support (2 people)                            │

│ ├─ Customer/Commercial/Billing Support (2-3 people)    │

│ ├─ HR/Finance Support (1-2 people)                     │

│ └─ EDI/Integration Support (2-3 people) ⭐ CRITICAL     │

└─────────────────────┬───────────────────────────────────┘

│ (Escalate if needs code fix or architecture)

↓

┌─────────────────────────────────────────────────────────┐

│ TIER 3: DEVELOPMENT TEAMS (Stream-Aligned Teams)       │

│ - Code defects (bugs)                                   │

│ - Architecture issues                                   │

│ - Complex business logic problems                       │

│ - New feature requests (not support, goes to PO)       │

│ Goal: Handle 10-20% of issues (only what Tier 2 can't) │

│ Team: On-call rotation from development teams          │

│ Skills: Development, architecture, deep system knowledge│

└─────────────────────────────────────────────────────────┘

## Potential Design choices

### Architecture Patterns for Your New World

Since you're moving to SaaS + custom + integration, here are key patterns:

Integration Patterns

1. API-First Architecture:

- Every system exposes well-documented APIs

- No direct database access across system boundaries

- API gateway as single entry point

- Versioning strategy for APIs

2. Event-Driven Architecture:

- Systems publish events when state changes

- Other systems subscribe to events they care about

- Loose coupling between systems

- Use for: real-time data sync, workflow automation

Example: Order-to-Cash team creates order → publishes "OrderCreated" event → Supply Chain, Finance, Customer Experience teams all react appropriately.

3. Data Integration Patterns:

- Batch ETL: For large data volumes, nightly sync (ERP → Data Warehouse)

- Real-time streaming: For time-sensitive data (IoT sensors → Analytics)

- API-based: For on-demand data access (Customer portal → CRM)

- CDC (Change Data Capture): For efficient database replication

4. Service Mesh/API Gateway:

- Centralized authentication and authorization

- Rate limiting and throttling

- Logging and monitoring

- Circuit breakers for resilience

SaaS Integration Patterns

1. iPaaS-Centric:

- Use Integration Platform as a Service (MuleSoft, Dell Boomi, Workato, Zapier)

- Pre-built connectors for common SaaS

- No-code/low-code for simple integrations

- Your Integration Platform team provides this

2. Embedded iPaaS:

- Some SaaS platforms have built-in integration (Salesforce, ServiceNow)

- Use their native tools when integrating within that ecosystem

- Use your iPaaS for cross-ecosystem integration

3. Vendor APIs:

- Understand vendor API limits and costs

- Cache data when appropriate

- Handle rate limiting gracefully

Data Architecture Patterns

1. Data Lake + Data Warehouse Hybrid:

- Data Lake: Raw data, all sources, cheap storage (S3, Azure Blob)

- Data Warehouse: Curated, modeled data for analytics (Snowflake, Azure Synapse, Databricks)

- Stream data into lake, transform and load into warehouse

2. Domain-Oriented Data Ownership:

- Each stream-aligned team owns data for their domain

- They publish data to central data lake/warehouse

- Data platform team ensures quality and accessibility

3. Single Source of Truth:

- For each data entity, designate one system as source of truth

- Example: Salesforce is source of truth for customers, ERP for products

- Other systems sync from source of truth

4. Data Mesh (advanced, for later):

- Treat data as products

- Domain teams own their data products

- Federated governance

- Self-serve data platform

### Governance Model

With more autonomy (stream-aligned teams) comes need for governance.

Architecture Governance:

- Architecture Review Board: Approves significant technical decisions

- Technology Radar: Approved, trial, and deprecated technologies

- Architecture principles: Guide decisions without needing approval

- Reference architectures: Standard patterns teams should follow

Data Governance:

- Data Governance Board: Sets policies, resolves conflicts

- Data ownership: Every data domain has a business owner

- Data quality standards: Minimum acceptable quality levels

- Data access policies: Who can access what data

Vendor Governance:

- Vendor selection process: How to evaluate and choose vendors

- Contract standards: Minimum acceptable terms

- Security requirements: What vendors must provide

- Performance management: How vendors are monitored

Portfolio Governance:

- Investment decisions: How to prioritize across teams

- Build-vs-buy framework: When to build custom vs. buy SaaS

- Business case requirements: What's needed to approve projects

- Benefits realization: Tracking if projects deliver promised value

### Technology Stack Recommendations

Based on your transformation:

Integration Platform:

- MuleSoft (powerful, enterprise-grade, expensive)

- Dell Boomi (good balance of power and cost)

- Azure Logic Apps / Power Automate (if Microsoft-centric)

- Workato (good for SaaS-to-SaaS)

Data Platform:

- Snowflake (pure play, excellent for data warehouse)

- Azure Synapse / Fabric (if Microsoft-centric)

- Databricks (if heavy AI/ML focus)

- AWS Redshift + S3 (if AWS-centric)

API Management:

- Azure API Management (if Microsoft-centric)

- AWS API Gateway (if AWS-centric)

- Kong or Apigee (cloud-agnostic)

Data Catalog:

- Collibra (enterprise-grade, expensive)

- Alation (good balance)

Data Catalog (continued):

- Azure Purview (if Microsoft-centric, good value)

- AWS Glue Catalog (if AWS-centric)

- Open source: Apache Atlas, DataHub (requires more maintenance)

iPaaS/Workflow Automation:

- Zapier/Make (simple automations, citizen developers)

- n8n (open source alternative, self-hosted)

- Use for tactical integrations, not strategic ones

Event Streaming:

- Apache Kafka (industry standard, requires expertise)

- Azure Event Hub (managed Kafka, easier)

- AWS EventBridge (serverless, good for event-driven)

- RabbitMQ (simpler message queue for basic needs)

DevOps/Platform:

- GitHub/GitLab (source control + CI/CD)

- Azure DevOps (if Microsoft-centric, includes boards)

- Jenkins (CI/CD, more configuration needed)

- Terraform (infrastructure as code - essential)

- Kubernetes (container orchestration - only if you need it)

AI/ML Platform:

- Azure ML (if Microsoft-centric, well-integrated)

- AWS SageMaker (if AWS-centric, comprehensive)

- Databricks (excellent for ML + data engineering)

- Vertex AI (if Google Cloud)

Monitoring & Observability:

- Datadog (comprehensive, expensive)

- New Relic (APM + infrastructure)

- Dynatrace (AI-powered, enterprise)

- Azure Monitor + Application Insights (if Microsoft-centric)

- Grafana + Prometheus (open source, requires setup)

- ELK Stack (Elasticsearch, Logstash, Kibana - for logging)

BI/Analytics:

- Power BI (if Microsoft-centric, good value, easy adoption)

- Tableau (powerful visualization, intuitive)

- Looker (good for technical users, Git-based)

- Qlik (powerful analytics engine)

Data Quality:

- Great Expectations (open source, code-based)

- Monte Carlo (data observability, ML-powered)

- Talend Data Quality (enterprise-grade)

- Built into some data platforms (dbt tests, Databricks expectations)

Master Data Management:

- Informatica MDM (enterprise leader, expensive)

- Profisee (Microsoft-centric, more affordable)

- Consider simpler approaches first (golden records in data warehouse)

Recommendation: Start with cloud-native tools from your primary cloud provider (Azure, AWS, or GCP) for faster time-to-value and lower operational complexity. Add best-of-breed tools where there are significant gaps.

## Implementation Roadmap: Transition from current to future state

### Current State Assessment

First, understand what you have:

Skills inventory:

- Survey your developers: What technologies do they know? What do they want to learn?

- Identify hidden talents (someone who's been experimenting with Python/ML on side projects)

- Assess business domain knowledge (developers who deeply understand finance, operations, etc.)

System inventory:

- Map all current systems

- Document all integrations (formal and informal)

- Identify technical debt hotspots

- List all SaaS tools (even shadow IT)

Workload analysis:

- How much time on new development vs. maintenance?

- How much time fighting integration issues?

- How much time on manual processes that should be automated?

### Transition Roadmap

Phase 1: Foundation (Months 1-6)

Key hires:

- Enterprise Architect (month 1) - This person helps design the rest

- 2 Solution Architects (months 2-3)

- Data Architect (month 3)

- 2 Integration Specialists (months 3-4)

- Head of Vendor Management (month 4)

- 2 Business Analysts (months 4-5)

Organizational changes:

- Form Architecture Review Board

- Establish architecture practice

- Don't restructure teams yet - add architects and BAs to existing teams

- Start documenting system landscape

Technical initiatives:

- Select and deploy integration platform (iPaaS)

- Select and begin implementing data warehouse/lake

- Create initial architecture principles

- Document current integration patterns

- Conduct security review of all SaaS tools

Quick wins:

- Consolidate overlapping SaaS tools

- Document and standardize integration patterns

- Create API catalog

- Implement API gateway for existing APIs

Phase 2: Reorganization (Months 6-12)

Key hires:

- 1-2 more Business Analysts

- 3-4 Data Engineers

- 2 Product Owners (promote from within or hire)

- 2 Integration Platform engineers

Organizational changes:

- Pilot stream-aligned team structure with 1-2 domains

  - Choose domains with clear boundaries

  - Choose teams with enthusiastic leaders

  - Provide heavy architecture support

  - Learn and adjust

- Form Data Governance Board

- Establish Vendor Management process

- Create career paths for new roles

Technical initiatives:

- Build initial data pipelines for key data domains

- Implement data catalog

- Migrate first integrations to new platform

- Establish data quality monitoring

- Create first "golden records" (customer, product)

Team evolution:

- Some functional analysts become BAs

- Some developers specialize in integration

- Some developers become configuration specialists (SaaS)

- Some senior developers become solution architects

- Team Success Managers evolve into Product Owners or remain as Scrum Masters

Phase 3: Scale (Months 12-18)

Key hires:

- 2-3 more Solution Architects

- 2-3 Data Scientists

- 2 ML Engineers

- 1-2 more Product Owners

- Security Architect

Organizational changes:

- Roll out stream-aligned structure to all teams

- Form platform teams (Integration, Data, DevOps)

- Establish AI Center of Excellence

- Mature vendor management practice

Technical initiatives:

- Data warehouse/lake fully operational

- Self-service analytics enabled

- First AI/ML pilots

- Integration platform handling majority of integrations

- Comprehensive monitoring and observability

Phase 4: Optimize (Months 18-24)

Focus:

- Refine team boundaries based on learning

- Mature platform teams

- Scale AI capability

- Continuous improvement of architecture and processes

### Overview: 24-Month Transformation

Philosophy:

- Start small (pilots)

- Prove value

- Learn and adjust

- Scale gradually

- Never big bang

### Month-by-Month Roadmap

MONTH 1: Launch & Foundation

Week 1-2: Initiation

- [ ] CTO announces transformation (all-hands meeting)

- [ ] Share vision, rationale, timeline

- [ ] Form transformation steering committee

  - Members: CTO, Head of IT Apps, Ops Manager, 2 business VPs, 2 team leads

  - Meets: Bi-weekly

- [ ] Conduct current state assessment

  - Systems inventory

  - Integration documentation

  - Skills inventory (survey all IT staff)

  - Workload analysis

Week 3-4: First Hires & Planning

- [ ] Post Enterprise Architect job description

  - Use executive recruiter

  - Target: hire in 30-45 days

  - Budget: €130K + 20% recruiting fee

- [ ] Engage external consulting partner (optional)

  - Architecture advisory

  - Change management support

  - 6-12 month engagement

- [ ] Begin stakeholder interviews

  - 10-15 business leaders

  - What's working / not working with IT?

  - Critical business initiatives?

  - Data/insights needs?

- [ ] Communication launch

  - Transformation intranet hub

  - Weekly email update started

  - Monthly all-hands scheduled

Deliverables:

- Current state documentation

- Transformation steering committee formed

- EA hiring in progress

- Communication channels established

MONTH 2: Architecture Foundation

Week 5-6: EA Onboarding

- [ ] Enterprise Architect hired and starts

- [ ] EA onboarding:

  - Meet all teams and stakeholders

  - Review current state documentation

  - Understand business context

- [ ] Form Architecture Review Board (initial)

  - EA (chairs)

  - Head of IT Apps

  - 2 senior developers

  - Ops Manager

Week 7-8: Architecture Practice Launch

- [ ] ARB first meeting

- [ ] Initial architecture assessment by EA

  - System landscape

  - Integration patterns

  - Technical debt hotspots

  - Security concerns

- [ ] Define initial architecture principles

  - API-first, Cloud-first, Buy before build, etc.

- [ ] Begin platform vendor research

  - Integration platform: MuleSoft, Boomi, Azure Logic Apps

  - Data platform: Snowflake, Databricks, Azure Synapse

Deliverables:

- EA hired and productive

- ARB operational

- Architecture principles defined

- Platform vendor shortlist

MONTH 3: Platform Selection & Pilot Planning

Week 9-10: Platform Evaluation

- [ ] Integration platform demos (3 vendors)

- [ ] Data platform demos (3 vendors)

- [ ] Evaluation criteria defined

- [ ] POCs for top 2 candidates (each platform)

- [ ] Hire Solution Architects (post jobs)

  - 2 Solution Architects

  - Target start: Month 4-5

Week 11-12: Pilot Team Selection

- [ ] Identify pilot stream-aligned teams (1-2 domains)

  - Criteria:

    - Clear business domain boundaries

    - Motivated team lead

    - Business sponsor identified

    - Not too complex for first pilot

  - Candidates: Customer Experience, Order-to-Cash

- [ ] Pilot team design

  - Define team boundaries

  - Identify Product Owner candidates

  - Map current staff to teams

- [ ] ARB platform decisions

  - Integration platform selected

  - Data platform selected

  - Procurement initiated

Deliverables:

- Platforms selected

- Pilot teams identified

- Solution Architect hiring in progress

- Platform procurement underway

MONTH 4: Team Formation & Platform Deployment

Week 13-16: Pilot Teams Launch

- [ ] Pilot team #1: Customer Experience

  - Product Owner identified/hired (from Sales org)

  - BA assigned (from current functional analysts)

  - 4-5 developers assigned

  - 1-2 testers assigned

  - Solution Architect allocated (20-40%)

  - Team kickoff and charter

- [ ] Pilot team #2: Order-to-Cash (if doing 2 pilots)

  - Similar structure

- [ ] Platform deployment begins

  - Integration platform: Initial setup

  - Data platform: Infrastructure provisioning

  - DevOps: CI/CD pipeline setup for pilots

- [ ] Additional hiring

  - 2 Business Analysts hired

  - 2 Integration Specialists hired

  - Data Architect hired

  - Head of Vendor Management hired

Deliverables:

- 1-2 pilot teams operational

- Platforms deploying

- Key roles hired

MONTH 5: Pilot Teams Delivering

Week 17-20: First Value Delivery

- [ ] Pilot teams delivering working software

  - Using new team structure

  - PO prioritizing backlog

  - BA refining requirements

  - Architects embedded

- [ ] Integration platform operational

  - First 2-3 integrations migrated

  - Team training on platform

- [ ] Data platform receiving data

  - First data sources connected

  - Data quality monitoring established

- [ ] Vendor management processes

  - Vendor inventory completed

  - Vendor tiering defined

  - Security assessment process established

Week 21: Mid-Pilot Review

- [ ] Assess pilot team progress

  - What's working well?

  - What's challenging?

  - Team satisfaction survey

  - Business stakeholder feedback

- [ ] Adjust approach based on learning

- [ ] Prepare for scale-up

Deliverables:

- Pilot teams delivering value

- Platforms operational (initial capabilities)

- Vendor management framework established

- Learning captured and adjustments made

MONTH 6: Expansion Planning

Week 22-24: Pilot Showcase & Planning

- [ ] Pilot team showcase

  - Demo to all IT staff

  - Share successes and challenges

  - Q&A and discussion

- [ ] Transformation mid-point review

  - Present to steering committee

  - Business case progress

  - Metrics: delivery speed, team satisfaction, business feedback

  - Celebrate wins

- [ ] Plan expansion

  - Which teams convert next? (2-3 teams in Month 7-9)

  - Hiring needs for expansion

  - Platform capability roadmap

- [ ] Data governance launch

  - Data Governance Board first meeting

  - Data ownership model defined

  - Data quality standards published

Deliverables:

- Pilot success demonstrated

- Expansion plan approved

- Data governance framework established

- 6-month wins communicated

MONTHS 7-9: Expansion Wave 1

Activities:

- [ ] Convert 2-3 more teams to stream-aligned model

  - Supply Chain team

  - Product Data team

  - Finance & Reporting team

- [ ] Platform teams forming

  - Integration Platform team (5-7 people)

  - Data Platform team (4-6 people initial)

  - DevOps/Platform team evolving

- [ ] Architecture practice maturing

  - Solution Architects embedded with all teams

  - ARB reviewing weekly (more proposals)

  - Reference architectures published

- [ ] Data engineering team building

  - 3-4 Data Engineers hired

  - Data pipelines for key sources

  - Data catalog implementation begins

- [ ] Vendor management active

  - Contract reviews and negotiations

  - Vendor consolidation initiatives

  - Security assessments for top vendors

Key Milestones:

- [ ] Month 7: 3-4 stream-aligned teams operational

- [ ] Month 8: Integration platform handling 10+ integrations

- [ ] Month 9: Data warehouse with 3-5 data sources, self-service analytics piloting

Deliverables:

- 50% of teams in new model

- Platforms adoption growing

- Data foundation solid

MONTHS 10-12: Scale & Data Maturity

Activities:

- [ ] Remaining teams convert to stream-aligned model (if not already)

- [ ] Platform teams fully operational

  - Self-service capabilities mature

  - Documentation and training comprehensive

  - Adoption tracking and optimization

- [ ] Data platform maturity

  - Data quality >90% for tier 1 data

  - Data catalog comprehensive

  - Self-service analytics broadly adopted

  - Analytics use cases delivering value

- [ ] AI/ML planning

  - Data readiness assessment

  - AI use case identification and prioritization

  - ML platform selection

  - Hire first Data Scientist (Month 12)

Key Milestones:

- [ ] Month 10: All teams in stream-aligned model

- [ ] Month 11: Integration platform standard for all new integrations

- [ ] Month 12: Data platform enabling analytics across organization

Deliverables:

- Transformation 50% complete

- New operating model embedded

- Data-driven culture emerging

- Ready for AI/ML phase

Year 1 Review:

- [ ] Comprehensive review of transformation

- [ ] Metrics:

  - Lead time reduced 30%+?

  - Team satisfaction improved?

  - Business stakeholder satisfaction up?

  - Quick wins delivered and communicated?

- [ ] Lessons learned

- [ ] Adjust Year 2 plans

- [ ] Celebrate Year 1 achievements

MONTHS 13-18: AI/ML Capability & Optimization

Activities:

- [ ] AI/ML Center of Excellence launch

  - 2-3 Data Scientists

  - 2 ML Engineers

  - AI Product Manager

  - ML platform deployed

- [ ] First AI/ML pilots

  - 2-3 high-value use cases

  - Months 15-18: Development and deployment

  - Examples: Customer churn prediction, demand forecasting, predictive maintenance

- [ ] Architecture optimization

  - Security Architect hired

  - Reference architectures comprehensive

  - Technical debt reduction initiatives

  - Platform capabilities expanded

- [ ] Vendor portfolio optimization

  - Vendor consolidation complete

  - Contract renegotiations (savings realized)

  - Strategic vendor partnerships developed

Key Milestones:

- [ ] Month 15: First AI model in production

- [ ] Month 16: ML platform operational, data scientists productive

- [ ] Month 18: 2-3 AI models delivering business value

Deliverables:

- AI/ML capability operational

- Architecture practice mature

- Vendor management delivering value

- Technical debt reducing

MONTHS 19-24: Maturity & Continuous Improvement

Activities:

- [ ] Fine-tune team boundaries based on 18 months experience

- [ ] Platform teams optimizing

  - Self-service adoption >70%

  - Platform innovation and new capabilities

  - Customer satisfaction high

- [ ] AI/ML scaling

  - 5+ models in production

  - Measurable business value (€ impact)

  - MLOps practices mature

  - Expanding to more use cases

- [ ] Data mesh exploration (if appropriate)

  - Domain-oriented data ownership

  - Federated data governance

  - Data as product mindset

- [ ] Organization evolution

  - Internal promotions to new roles

  - Career paths clear and active

  - Talent retention strong

  - Culture transformation evident

Key Milestones:

- [ ] Month 24: Transformation substantially complete

- [ ] New operating model the "new normal"

- [ ] Business outcomes demonstrable

- [ ] Team and stakeholder satisfaction high

Deliverables:

- Transformation complete (80-90%)

- Continuous improvement embedded

- Measurable business value

- Sustainable operating model

### Critical Path & Dependencies

The critical path (things that must happen in sequence):

- EA hire (Month 1-2) → Blocks everything else

- Platform selection (Month 3) → Blocks platform deployment

- Platform deployment (Month 4-6) → Blocks platform team formation

- Pilot success (Month 4-6) → Blocks expansion

- Data foundation (Month 6-12) → Blocks AI/ML

- Team expansion (Month 7-12) → Blocks full organizational transformation

Parallel tracks (can happen simultaneously):

- Hiring (ongoing throughout)

- Architecture practice building (Month 2+)

- Vendor management (Month 4+)

- Data platform (Month 4+)

- Integration platform (Month 4+)

Risks to timeline:

- ⚠️ EA hire delays → Everything delays (mitigate: use recruiter, start Month 1)

- ⚠️ Platform selection takes too long → Use time-boxed evaluation (6 weeks max)

- ⚠️ Pilot teams struggle → Provide heavy support, adjust quickly

- ⚠️ Key people leave → Retention bonuses, clear growth paths

- ⚠️ Business loses patience → Quick wins, constant communication

### Quick Wins (First 6 Months)

Critical to maintain momentum and build credibility:

Month 2-3: Vendor Consolidation

- Identify and eliminate duplicate SaaS tools

- Target: €50-100K annual savings

- Example: 3 project management tools → 1

- Communication: "Vendor consolidation saves €80K/year"

Month 3-4: Architecture Prevents Mistake

- EA catches team about to buy wrong platform

- Calculate avoided cost

- Example: Team wanted to build custom vs. buy SaaS (€500K saved)

- Communication: "Architecture review saved €500K on avoided custom build"

Month 5-6: Pilot Team Delivers Faster

- Measure lead time improvement

- Target: 30% faster than before

- Example: Feature that took 8 weeks now takes 5 weeks

- Communication: "New team model delivers 30% faster"

Month 5-6: First Integration on Platform

- Complete integration faster than custom code

- More reliable

- Example: Salesforce-ERP integration in 3 days vs. 3 weeks custom

- Communication: "Integration platform delivers in days, not weeks"

Total Quick Wins Value: €600K+ in first 6 months

- Builds business case

- Generates enthusiasm

- Maintains stakeholder support

## Managing the Transition

### Communication Strategy

This is massive change. Communicate constantly:

To current IT team:

- "We're not replacing you, we're evolving our capabilities"

- "New roles are opportunities - many will be filled internally"

- "We're investing in training and development"

- Be honest about which roles might change

To business stakeholders:

- "We're transforming to better serve your needs"

- "You'll have dedicated teams for your domain"

- "We'll be faster with SaaS and integration"

- "You'll have better data and insights"

Monthly all-hands:

- Progress updates

- Celebrate wins

- Address concerns

- Share vision

### Training and Development

Massive investment needed:

For developers:

- SaaS configuration (Salesforce, ServiceNow, etc.)

- API development and integration patterns

- Cloud platforms (Azure, AWS, GCP)

- DevOps practices

- Data engineering basics

- Domain-Driven Design

For functional analysts → BAs:

- Requirements elicitation techniques

- Process modeling

- SaaS evaluation frameworks

- Change management

- Business case development

For Team Success Managers → Product Owners:

- Product management fundamentals

- Roadmap planning

- Stakeholder management

- Metrics and KPIs

- Strategic thinking

Budget: Allocate 5-10% of IT budget to training during transition.

### Dealing with Resistance

Expect resistance from:

Developers: "I want to code, not configure Salesforce"

- Response: "We still build custom software where it adds value. But we also need to embrace SaaS. You can specialize."

- Create specialization paths: custom development, SaaS configuration, integration, data engineering

Current managers: "This undermines my authority"

- Response: Involve them in design. Some may become Product Owners, some may lead platform teams, some may move to architecture.

Business: "Why is IT reorganizing? Just deliver faster!"

- Response: "This reorganization is specifically to deliver faster and align with your needs."

### Metrics for Success

Track these to know if transformation is working:

Delivery metrics:

- Lead time (idea to production): Should decrease 30-50%

- Deployment frequency: Should increase significantly

- Change failure rate: Should decrease

- Time to integrate new SaaS: Track this explicitly

Team health metrics:

- Employee satisfaction: Regular surveys

- Turnover: Should not spike (some is expected)

- Skills growth: Track certifications, training completion

Business value metrics:

- Business stakeholder satisfaction: Quarterly surveys

- Features delivered per quarter

- Percentage of work that's new features vs. maintenance

- Cost of ownership (infrastructure + licenses + people)

Data/AI metrics (once that capability is built):

- Data quality scores

- Time to insight (question to answer)

- Number of AI models in production

- Business value delivered by AI projects

### Change Management

The People Side of Transformation

This is 70% people change, 30% technical change. Don't underestimate this.

Common failure modes:

- Great technical plan, but people resist

- New structure, but old behaviors persist

- New roles defined, but people don't understand them

- Platforms built, but teams don't adopt them

Stakeholder Analysis

Map all stakeholders by:

- Power (influence on transformation)

- Interest (how much they care)

Stakeholder Matrix:

High Power, High Interest (MANAGE CLOSELY):

- CTO, Business VPs, CFO

- Head of IT Applications, EA

- Key team leads

High Power, Low Interest (KEEP SATISFIED):

- CEO, Board

- Other executives not directly affected

- Brief them, don't overwhelm

Low Power, High Interest (KEEP INFORMED):

- IT team members

- Business users

- Communicate frequently

Low Power, Low Interest (MONITOR):

- Peripheral stakeholders

- Minimal communication needed

For each stakeholder group, define:

- Current state (supporter, neutral, resistor?)

- Desired state (where do we need them?)

- Gap and strategy to close it

Stakeholder Analysis

Supporters (leverage them):

- Business leaders frustrated with slow IT delivery

- IT staff excited about new technologies

- Current functional analysts who want to grow into BA roles

- Developers interested in architecture

Neutral (convince them):

- IT staff comfortable with status quo

- Business stakeholders who don't understand why change is needed

- Finance concerned about investment

Resistors (address their concerns):

- Developers who only want to code in their favorite language

- Managers who feel threatened by new structure

- Business units that have worked around IT with shadow IT

Engagement Strategy by Stakeholder:

For IT Staff:

- Town halls every month: Vision, progress, Q&A

- Working groups: Involve them in designing new processes

- Pilots: Let them volunteer for stream-aligned team pilots

- Training roadmaps: Personal development plans for everyone

- Success stories: Celebrate early wins

- Transparency: Share both successes and challenges

For Business Stakeholders:

- Executive briefings: Quarterly updates for business leaders

- Business case: Clear ROI and timeline

- Pilot selection: Choose business-critical domains for pilots to show value

- Regular feedback: Surveys and one-on-ones

- Showcases: Demo days showing new capabilities

For Leadership/Board:

- Strategic alignment: Connect IT transformation to business strategy

- Benchmarking: Show what industry leaders are doing

- Risk assessment: What happens if we don't transform?

- Phased investment: Not everything at once

- Governance: Clear oversight and decision rights

Change Strategy by Stakeholder Group

IT Leadership Team

Current concerns:

- "Is this just another reorganization?"

- "Will I still have a role?"

- "What if this fails?"

Strategy:

- Involve early and often: They help design transformation

- Clear roles: Document their role in future state (Month 1)

- Empower: Give them ownership of transformation workstreams

- Support: Training, coaching, resources

- Communicate: Weekly 1:1s with CTO during transformation

Target state: Champions and active drivers of transformation

IT Team Members (Developers, Testers, FAs)

Current concerns:

- "Will I lose my job?"

- "Do I have to learn everything new?"

- "What if I don't fit in new structure?"

- "Will this be more bureaucracy?"

Strategy:

- Transparency: Honest about what's changing and why

- Opportunities: "New roles are opportunities, many filled internally"

- Skills development: Heavy investment in training

- Career paths: Show growth opportunities in new structure

- Choice where possible: "Want to become BA, PO, or Architect? Let's talk"

- Safety net: "Try new role for 6 months, can adjust"

- Involvement: Let them volunteer for pilot teams

Communication:

- Monthly all-hands (CTO presents)

- Weekly email update

- Team-level Q&A sessions

- Office hours with EA and leadership

Target state: Engaged, cautiously optimistic, willing to try new approach

Business Stakeholders (VPs, Department Heads)

Current concerns:

- "Will IT deliver faster?"

- "What do I need to do?"

- "Product Owner? What's that?"

- "Don't slow down current work"

Strategy:

- Frame as serving them better: "This is about delivering value to you faster"

- Product Owner concept: "You'll have dedicated IT partner (PO) for your domain"

- Show, don't just tell: Pilot team demos, early wins

- Business metrics: Speak their language (revenue, cost, time)

- Minimal disruption: Pilot approach means not everything changes at once

Communication:

- Monthly business stakeholder briefing

- Pilot team showcases

- 1:1s with their future Product Owners

- Quarterly business review of transformation

Target state: Supportive, willing to allocate Product Owner from their team

Executive Team & Board

Current concerns:

- "What's the ROI?"

- "What's the risk?"

- "How long until we see results?"

- "What if this doesn't work?"

Strategy:

- Business case: Clear ROI (170% over 3 years)

- Benchmarking: "Industry leaders do this" (Amazon, Google, Netflix)

- Phased approach: "Start small (pilots), prove value, scale"

- Quick wins: Show progress in first 6 months

- Risk mitigation: "Here's our risk register and mitigations"

- External validation: Industry analyst reports, consultant support

Communication:

- Quarterly transformation updates (30 min)

- Brief monthly email from CTO

- Annual deep dive with board

Target state: Informed, supportive, patient

### Communication Plan

Channels:

- Monthly all-hands (IT department): 1 hour, vision + progress + Q&A

- Weekly email update: Brief wins and upcoming changes

- Transformation hub (intranet): Documentation, FAQs, resources

- Office hours: Architecture office hours, vendor management office hours

- Showcase sessions: Teams demo new capabilities

- Leadership briefings: Monthly for IT leadership, quarterly for executives

Messages (repeat consistently):

- Why: Business needs are changing, we must evolve to serve them

- What: Moving from pure development to orchestration of build+buy+integrate

- How: Phased approach, starting with foundation

- WIIFM (What's In It For Me): Growth opportunities, modern technologies, clearer impact

- Safety: We're investing in people, not replacing them

Key Milestones to Communicate:

- Architecture practice established

- First stream-aligned team launched

- Integration platform live

- Data warehouse operational

- First AI model in production

- SaaS consolidation completed

Cadence & Channels:

Daily:

- Slack/Teams channels for transformation questions

- Ad-hoc discussions and support

Weekly:

- Email update from CTO (5-minute read)

  - What happened this week

  - What's coming next week

  - Highlight: One success story or learning

  - Link to details on intranet

Bi-weekly:

- Transformation steering committee meeting

- Architecture Review Board (for technical governance)

Monthly:

- All-hands meeting (IT department, 1 hour)

  - CTO presents: Progress, wins, challenges

  - Guest speaker: Business leader, team showcase

  - Q&A (anonymous questions welcome)

  - Recording available for those who miss it

- Business stakeholder briefing (30 min)

- Pilot team demos (showcase progress)

Quarterly:

- Executive team update

- Board update (if appropriate)

- Transformation town hall (broader organization)

- Deep-dive workshops on specific topics

Transformation Intranet Hub:

- Home: Vision, roadmap, FAQ

- Progress: Metrics and dashboards

- Teams: Stream-aligned team info

- Roles: Job descriptions and career paths

- Resources: Training, documentation

- News: Updates and announcements

- Feedback: Survey and suggestion box

### Resistance Management

Expect resistance. It's normal and healthy.

Common Objections & Responses:

"We don't need architects, they'll slow us down"

- Response: "Our architects are enablers, not gatekeepers. They provide patterns and guidance so you can move faster. Think of them as experienced consultants embedded in your teams."

- Evidence: Show examples from pilot teams moving faster with architecture support

"I'm a developer, I don't want to configure Salesforce"

- Response: "We still need custom development. You can specialize in what you're passionate about. Or you can learn SaaS configuration - it's a valuable skill. Your choice."

- Action: Create clear specialization tracks

"This is just the latest reorganization fad"

- Response: "This isn't about org charts, it's about capabilities we're missing. We can't succeed with SaaS and AI without these skills. The structure follows the capabilities."

- Evidence: Show industry research, benchmark competitors

"We're Agile, why do we need project managers?"

- Response: "We're not going back to waterfall. But when we implement a new ERP or do a major SaaS rollout, we need program coordination. That's different from team-level Scrum."

- Action: Show how Agile and project management complement each other

"Business analysts will create bureaucracy"

- Response: "BAs are here to bridge business and IT, not add process. They'll make requirements clearer, evaluate SaaS solutions, and handle change management - things developers shouldn't have to do."

- Action: Show time savings for developers

Dealing with Attrition:

Some people will leave. That's okay.

- Expected: 10-15% attrition during transformation (some voluntary, some managed)

- Acceptable: People who don't want to evolve or can't adapt

- Unacceptable: Losing your best people due to poor change management

Retention strategies for key people:

- Clear growth paths: Show them their future

- Training investment: Send them to conferences, certifications

- Salary adjustments: Market-rate people appropriately

- Involvement: Give them meaningful roles in transformation

- Recognition: Celebrate their contributions publicly

Common Resistance Patterns:

1. "We don't need to change"

Symptoms:

- "Current structure works fine"

- "This is just the latest fad"

- "We tried this before and it failed"

Response:

- Acknowledge: "I understand the current model has served us well"

- Context: "Business needs are changing (SaaS, AI, data), we must evolve"

- Data: Show pain points with data (slow delivery, business dissatisfaction)

- Risk of not changing: "If we don't change, here's what happens..." (competitors outpace us)

- Respect: "Your experience is valuable in designing new approach"

Action:

- Involve resistors in solution design

- Show industry benchmarks and trends

- Connect to business strategy (not just IT preference)

2. "I'll lose my job/role"

Symptoms:

- Anxiety about future

- Disengagement

- Passive resistance

Response:

- Clarity: "We're not eliminating roles, we're evolving capabilities"

- Opportunities: "Many new roles will be filled internally"

- Examples: "Functional Analysts can become BAs, developers can become architects"

- Support: "Heavy training investment, career development"

- Honesty: "Some roles will change, but we're investing in people"

Action:

- Career conversations with everyone (first 3 months)

- Clear career paths published

- Training budgets allocated

- Internal-first hiring policy (fill 60%+ internally)

3. "This is too much change"

Symptoms:

- Overwhelmed

- Change fatigue

- Burnout risk

Response:

- Pace: "We're doing this over 24 months, not overnight"

- Pilots: "Starting small with 1-2 teams, learning, then scaling"

- Support: "Extra support during transition - coaching, training, resources"

- Simplify: Maybe we tried to do too much at once, can we phase differently?

Action:

- Monitor team stress levels (surveys, 1:1s)

- Adjust pace if needed (better slow and successful than fast and failed)

- Provide support resources (coaching, counseling if needed)

- Celebrate small wins to build momentum

4. "Architects/PMs will slow us down"

Symptoms:

- "We don't need governance"

- "Just let us code"

- "Architecture Review Board is a bottleneck"

Response:

- Reframe: "Architects are enablers, not gatekeepers"

- Evidence: Show examples where architecture caught costly mistakes

- Speed: "With architecture, you move faster in long run (less rework, better patterns)"

- Involvement: "Solution Architects embedded in teams, not ivory tower"

- Pragmatism: "Architecture provides guardrails, not gates"

Action:

- Architects earn trust through value-add (not bureaucracy)

- ARB focuses on strategic decisions, teams make most decisions

- Track ARB decision speed (should be fast)

- Architects pair-program, show hands-on value

5. "Product Owners will micromanage us"

Symptoms:

- Developers worried about autonomy

- "We don't need someone telling us what to do"

Response:

- Clarify: "PO decides WHAT to build and WHEN, team decides HOW"

- Autonomy: "Teams have MORE autonomy on technical decisions"

- Partnership: "PO is partner, not manager"

- Examples: Show successful PO-team relationships from pilots

Action:

- Clear decision rights documentation

- PO training includes "how to work with development teams"

- Team feedback on PO relationship (anonymous survey)

- Coaching for POs who micromanage

6. "Business stakeholders going around Product Owner"

Symptoms:

- Stakeholders calling developers directly

- PO decisions undermined

- Confusion about priorities

Response:

- Expectation setting: Business VPs must reinforce PO authority

- Redirect: "Please work through the Product Owner"

- PO credibility: Ensure PO has domain expertise and business credibility

Action:

- Business VP explicitly empowers PO (public statement)

- PO office hours for stakeholders

- Escalation path when stakeholders disagree with PO (but PO decides)

- Track and address bypass incidents

### Training & Development Plan

Massive investment needed. Budget: €200-400K/year.

Training by Role:

For Developers:

- Cloud platforms (Azure, AWS): 3-day workshops + certifications

- API development and integration patterns: 2-day workshop

- SaaS configuration (Salesforce, ServiceNow): Vendor training

- DevOps practices: CI/CD, infrastructure as code (2 days)

- Domain-Driven Design: 2-day workshop

- Agile/Scrum refresher: 1 day (if needed)

- Cost per developer: €3-5K/year

- Timeline: First 6 months for foundational training

For Functional Analysts → Business Analysts:

- Business Analysis certification (CBAP track): Self-paced + exam

- Requirements elicitation techniques: 2-day workshop

- Process modeling and improvement: 2 days

- SaaS evaluation frameworks: 1-day workshop

- Agile Business Analysis: 2 days

- Change management fundamentals: 1 day

- Cost per BA: €4-6K/year

- Timeline: First 3 months intensive

For Team Success Managers → Product Owners (if transitioning):

- Product Management fundamentals: 3-day workshop or online course

- Certified Scrum Product Owner (CSPO): 2 days + cert

- Roadmap planning and strategy: 2 days

- Stakeholder management: 1 day

- Business case development: 1 day

- Metrics and OKRs: 1 day

- Cost per PO: €5-7K/year

- Timeline: First 3 months before taking full PO role

For New Architects:

- TOGAF certification: 5 days + exam (€3-4K)

- Cloud architect certifications: AWS/Azure/GCP (€2-3K)

- Domain-Driven Design: 3-day workshop

- Architecture decision-making: 2 days

- Communication and facilitation: 2 days

- Cost per architect: €8-10K/year

- Timeline: First 6 months

For Data Engineers:

- Cloud data platform training: Snowflake, Databricks, or Synapse (€2-3K)

- Data modeling: 2-day workshop

- ETL/ELT best practices: 2 days

- Data quality frameworks: 1 day

- Cost per data engineer: €4-6K/year

- Timeline: First 3-6 months

For Data Scientists:

- ML platform training (Azure ML, SageMaker, etc.): Vendor training

- MLOps practices: 2-day workshop

- Responsible AI: 1-day workshop

- Cost per data scientist: €3-5K/year

- Timeline: Ongoing

For Everyone:

- Team Topologies overview: Half-day workshop for all IT staff (Month 2)

- New operating model: Half-day session explaining changes (Month 1)

- Architecture principles: Half-day workshop (Month 3)

- Security awareness: Annual requirement

- Cost: €300-500 per person for foundational training

Training Delivery Methods:

- External vendors: Specific skills (cloud, certifications)

- Internal workshops: Run by EA, architects, consultants

- Online learning: LinkedIn Learning, Pluralsight, Coursera

- Conferences: 1-2 per year for architects and senior staff (€2-3K each)

- Books and resources: Company library, book allowance

- Peer learning: Architecture guild, communities of practice

Training Schedule Example (First Year):

| Month | Training Focus |
| --- | --- |
| 1-2 | Transformation overview, new operating model for all |
| 3-4 | Role-specific foundational training (BA, PO, Architecture) |
| 5-6 | Cloud and platform training for developers |
| 7-8 | Advanced topics, certifications |
| 9-10 | SaaS configuration training |
| 11-12 | Year 1 review, identify Year 2 needs |

### Culture Transformation

Current Culture (likely):

- Technology-focused ("we're developers")

- Siloed ("not my team's problem")

- Process-heavy or ad-hoc (either extreme)

- Reactive ("fire-fighting")

- IT as order-takers ("business tells us what to build")

Target Culture:

- Business outcome-focused: "We deliver business value"

- Collaborative: "We work across teams"

- Product mindset: "We own products, not just projects"

- Proactive: "We anticipate needs and opportunities"

- Partnership: "We partner with business, not take orders"

- Data-driven: "We use data to make decisions"

- Continuous learning: "We constantly improve"

Culture Change Levers:

1. Leadership Behaviors:

- CTO models new behaviors

  - Talks about business outcomes, not just technology

  - Asks "what business problem are we solving?"

  - Celebrates collaboration and learning

  - Makes data-driven decisions

- Other leaders follow suit

2. Metrics and Recognition:

- What gets measured gets done

- Measure and celebrate:

  - Business value delivered (not just features shipped)

  - Collaboration (team dependencies resolved)

  - Learning (certifications, skills developed)

  - Quality (not just speed)

- Recognition in all-hands meetings

- Awards for exemplars

3. Rituals and Ceremonies:

- Monthly all-hands: Reinforces culture

- Quarterly showcases: Teams demo business outcomes

- Retrospectives: Learning and improvement

- Architecture guild: Knowledge sharing

- These rituals embed new culture

4. Stories and Heroes:

- Tell stories of success in new model

- Make heroes of those who exemplify new culture

- Examples:

  - "Sarah (PO) partnered with Sales to reduce cycle time by 40%"

  - "John (Architect) saved us €500K by catching early mistake"

  - "Data team enabled executives to make data-driven decision that increased margin"

- Stories spread new culture

5. Hiring and Promotion:

- Hire for culture fit (collaborative, business-focused, learning mindset)

- Promote people who exemplify new culture

- Make clear: this is how you succeed here

6. Physical/Virtual Environment:

- Team spaces (if co-located) organized by business domain

- Collaboration spaces

- Virtual collaboration tools

- Make collaboration easy

Culture transformation takes time: 18-24 months to feel real, 3-5 years to fully embed

### Dealing with Attrition

Expect 10-15% attrition during transformation. Some is healthy, some is concerning.

Healthy Attrition (5-10%):

- People who don't want to change

- Poor performers who couldn't adapt

- People whose skills don't fit future needs

- Managed exits with support and dignity

Concerning Attrition (want to prevent):

- High performers leaving due to uncertainty

- Key people leaving due to poor change management

- Domain experts leaving (lose business knowledge)

- Attrition >15% (indicates serious problems)

Retention Strategies:

For High Performers:

- Early conversations: "You're valued, here's your future"

- Growth opportunities: Clear path in new structure

- Involvement: Give them important roles in transformation

- Compensation: Retention bonuses (if needed)

- Challenge: Interesting problems and opportunities

For Key Domain Experts:

- Respect their knowledge: "Your expertise is critical"

- Product Owner path: Natural fit for domain experts

- Influence: Involved in designing their domain's future

- Recognition: Public acknowledgment of their value

For Everyone:

- Transparency: Honest about changes and reasons

- Fairness: Consistent treatment, no favoritism

- Support: Training, coaching, resources

- Patience: Time to adapt

- Communication: Constant, open, two-way

When Key Person Gives Notice:

- Understand why: Exit interview to learn

- Counter-offer if appropriate: But don't over-rely on this

- Knowledge transfer: Ensure knowledge documented and transferred

- Learn: What does this tell us about transformation?

- Adjust: If pattern emerges, change approach

Red Flags (indicate attrition risk):

- Drop in employee engagement scores

- Increase in sick days or PTO usage

- Team members disengaging (quiet, not participating)

- Increase in LinkedIn activity (updating profiles)

- Complaints or negative feedback increasing

Monitor proactively:

- Monthly pulse surveys (2-3 questions)

- 1:1s with team leads

- Anonymous feedback channels

- Watch for patterns

### Common Pitfalls & How to Avoid Them

Let me share mistakes I've seen in similar transformations:

Pitfall 1: "Big Bang" Reorganization

Mistake: Announcing new structure and reshuffling everyone on Day 1.

Why it fails:

- Chaos and confusion

- Existing work disrupted

- People don't understand new roles yet

- No proof the model works

How to avoid:

- Start with pilots

- Prove the model before scaling

- Give people time to transition

- Evolve structure over 12-18 months

Pitfall 2: Hiring Architects Too Late

Mistake: Trying to design the future without architecture expertise.

Why it fails:

- Without architects, you'll make costly technology decisions

- Platform selections without proper evaluation

- Integration patterns that don't scale

- Technical debt increases

How to avoid:

- Enterprise Architect is first hire (Month 1-2)

- Don't make major technology decisions before EA joins

- Use external consultants temporarily if needed

- Architects help design rest of transformation

Pitfall 3: Ignoring Vendor Management

Mistake: Assuming SaaS vendors take care of themselves.

Why it fails:

- Duplicate purchases (3 teams buy same tool)

- Poor contracts (no exit clause, bad SLAs)

- Vendor lock-in

- Costs spiral out of control

- Security risks

How to avoid:

- Hire Vendor Manager by Month 3-4

- Immediate vendor inventory

- Centralized SaaS purchasing policy

- Contract reviews for all vendors

- Architecture Review Board must approve new vendors

Pitfall 4: Building AI Team Before Data Foundation

Mistake: Hiring data scientists immediately, promising AI results quickly.

Why it fails:

- Data isn't ready (quality, access, integration)

- Data scientists spend 80% of time on data engineering

- Projects fail, disillusionment sets in

- Expensive hires leave frustrated

How to avoid:

- Data platform and data engineering first (6-12 months)

- Data quality to 90%+ before heavy AI investment

- Start with analytics, then predictive models

- Hire 2-3 data engineers before first data scientist

- Manage expectations: AI value in 18-24 months, not 6

Pitfall 5: Platform Teams That Become Bottlenecks

Mistake: All integrations must go through platform team, no self-service.

Why it fails:

- Platform team backlog grows

- Stream teams blocked waiting for integrations

- Frustration and shadow IT

- Platform team seen as obstacle

How to avoid:

- Self-service capabilities from day one

- Reusable connectors and templates

- Stream teams can do simple integrations themselves

- Platform team focuses on complex work and standards

- Clear SLAs (standard integration in 3-5 days)

- Office hours and pairing sessions

Pitfall 6: Product Owners Without Authority

Mistake: Product Owners who can't actually make decisions.

Why it fails:

- Decisions still escalate to committees

- Team gets blocked

- PO becomes just another BA

- No benefit from role

How to avoid:

- POs must have budget authority

- POs must be able to say "no" to features

- POs empowered by leadership

- Business stakeholders respect PO decisions

- If PO can't decide, find someone who can

Pitfall 7: Wrong Team Boundaries

Mistake: Stream-aligned teams with unclear or overlapping boundaries.

Why it fails:

- Constant handoffs between teams

- Who owns what is unclear

- Integration complexity doesn't decrease

- Teams step on each other

How to avoid:

- Use Domain-Driven Design to find boundaries

- Expect to adjust boundaries after 6-12 months

- Clear ownership documented

- APIs between teams (not shared databases)

- Architecture Review Board mediates boundary disputes

Pitfall 8: Forgetting the Business

Mistake: IT transformation designed by IT for IT.

Why it fails:

- Business doesn't see value

- Perceived as internal IT shuffle

- Business support wanes

- Budget cuts when value isn't clear

How to avoid:

- Business stakeholders on transformation steering committee

- Product Owners from business side

- Regular business showcases (monthly)

- Measure business value explicitly

- Business satisfaction surveys

- Frame everything as "serving business better"

Pitfall 9: Underestimating Change Management

Mistake: Treating this as technical transformation only.

Why it fails:

- People resist

- Key staff leave

- Teams don't adopt new ways

- Culture doesn't shift

How to avoid:

- 40% of transformation effort is change management

- Constant communication (monthly all-hands minimum)

- Address concerns proactively

- Celebrate wins publicly

- Support people through transitions

- Consider external change management consultant

Pitfall 10: No Quick Wins

Mistake: All benefits appear in 18-24 months.

Why it fails:

- People lose faith

- Leadership patience runs out

- "See, the new model doesn't work"

- Hard to maintain momentum

How to avoid:

- Identify quick wins in first 3-6 months

- Consolidate duplicate SaaS tools (immediate cost savings)

- Standardize one integration (immediate reliability improvement)

- Pilot team delivers visible value (3-6 months)

- Architecture prevents one major mistake (calculate savings)

- Communicate quick wins loudly

## Metrics & Success Criteria

### Team-Level KPIs

Stream-Aligned Teams:

- Delivery velocity: Story points or features per sprint (track trend)

- Lead time: Idea to production (target: 2-4 weeks for medium features)

- Deployment frequency: Daily or weekly (target: daily)

- Change failure rate: % of deployments causing incidents (target: <5%)

- MTTR (Mean Time To Restore): When things break (target: <1 hour)

- Business value delivered: Measured with Product Owner (qualitative)

- Team health: Quarterly survey (engagement, autonomy, mastery, purpose)

Platform Teams:

- Platform availability: Uptime (target: 99.9%)

- Request fulfillment time: Average days to complete requests (target: 3-5 days)

- Customer satisfaction: Stream teams rate platform team (target: 4.5/5)

- Adoption rate: % of potential use cases using platform (target: 80%+)

- Reusability: % of integrations using standard connectors (target: 70%+)

- Cost per transaction: Integration cost (track trend - should decrease)

Data Platform Team:

- Data pipeline reliability: % of pipelines running on time (target: 99%)

- Data quality score: Automated quality checks (target: 95%+)

- Time to insight: Question to answer for analysts (target: <1 day)

- Data accessibility: % of data in catalog (target: 100% of Tier 1 data)

- Self-service adoption: % of data requests self-served (target: 60%+)

AI/ML Team:

- Models in production: Number of deployed models (track growth)

- Model performance: Accuracy vs. baseline (target: defined per model)

- Business value: $ impact of AI models (measured with business)

- Time to production: Model development to deployment (target: 2-3 months)

- Model health: % of models meeting performance SLAs (target: 90%+)

### Organization-Level KPIs

Delivery Excellence:

- Overall lead time: Requirements to production (target: 50% reduction in 18 months)

- % of time on new features: vs. maintenance (target: 70% new, 30% maintenance)

- Business satisfaction: Quarterly survey of business stakeholders (target: 4/5)

- Project delivery: % of projects on time and on budget (target: 80%+)

Architecture & Technical Health:

- System integration health: % of integrations on standard platform (target: 80%+)

- Technical debt ratio: Measured via code analysis (target: <30%)

- Architecture compliance: % of systems following standards (target: 90%+)

- API adoption: % of system access via APIs vs. direct DB (target: 100% API)

- Security incidents: Number and severity (target: zero critical)

Data & Analytics:

- Data coverage: % of business processes with data in warehouse (target: 90%+)

- Data quality: Overall data quality score (target: 95%+)

- Analytics adoption: % of employees using BI tools (track growth)

- AI value: $ value delivered by AI initiatives (track)

- Data democratization: % of data accessible via self-service (target: 80%+

Vendor Management:

- Vendor performance: Average vendor scorecard rating (target: 4/5)

- SLA compliance: % of vendors meeting SLAs (target: 95%+)

- Contract value optimization: Savings vs. list price (track annually)

- Vendor consolidation: Reduction in number of vendors (track trend)

- Time to onboard new SaaS: Days from selection to production (target: 30-45 days)

- Shadow IT reduction: Unapproved tools discovered and consolidated (track trend)

Financial:

- IT cost as % of revenue: Track trend (should stabilize or decrease)

- Cost per business transaction: IT cost efficiency (track trend)

- ROI of IT investments: Measured value vs. investment (target: >150% over 3 years)

- License optimization: Cost savings from license management (track annually)

- Cloud cost optimization: Monthly cloud spend vs. usage (target: <10% waste)

People & Culture:

- Employee engagement: IT team satisfaction (target: 4/5)

- Retention rate: % of key staff retained (target: 90%+)

- Skills growth: Certifications, training hours per person (target: 40 hours/year)

- Internal mobility: % of new roles filled internally (target: 60%+)

- Diversity: Track and improve

### Dashboard & Reporting

Executive Dashboard (Monthly review with CTO + business leaders):

- Business value delivered (features, $$ impact)

- Delivery speed (lead time trend)

- Business satisfaction

- Key initiatives status

- Budget vs. actual

- Strategic risks

IT Leadership Dashboard (Weekly review):

- All team health metrics

- Platform availability

- Delivery velocity trends

- Incidents and issues

- Resource utilization

- Hiring status

Team Dashboards (Daily visibility):

- Current sprint/work progress

- Deployment frequency

- System health metrics

- Integration queue (for platform teams)

- Data quality metrics (for data teams)

### Transformation Metrics Dashboard

Three Categories:

- Delivery Metrics (Are we delivering better?)

- Health Metrics (Are teams healthy?)

- Business Metrics (Are we delivering business value?)

1. Delivery Metrics (Technical Excellence)

Lead Time (Idea to Production):

- Definition: Time from work item starting development to deployed in production

- Baseline: Measure current state (likely 4-8 weeks)

- Target: Reduce by 30-50% (to 2-4 weeks)

- Measurement: Track in Azure DevOps/Jira

- Frequency: Monthly average

- Why it matters: Speed of value delivery

Deployment Frequency:

- Definition: How often code is deployed to production

- Baseline: Current state (weekly? monthly?)

- Target: Daily or multiple times per day

- Measurement: Automated from CI/CD pipeline

- Frequency: Weekly average

- Why it matters: Ability to release quickly and frequently

Change Failure Rate:

- Definition: % of deployments causing production incident

- Baseline: Current state (measure for 3 months)

- Target: <5% (elite performers <15%)

- Measurement: Incidents tagged as deployment-related / total deployments

- Frequency: Monthly

- Why it matters: Quality of releases

Mean Time to Restore (MTTR):

- Definition: Time from incident detection to resolution

- Baseline: Current state (hours? days?)

- Target: <1 hour for critical issues

- Measurement: Incident tracking system

- Frequency: Monthly average

- Why it matters: Resilience and recovery capability

Flow Efficiency:

- Definition: Active work time / total elapsed time

- Baseline: Current state (likely 20-30%)

- Target: >40%

- Measurement: Time tracking in work management tool

- Frequency: Monthly

- Why it matters: How much time is productive vs. waiting

Technical Debt Ratio:

- Definition: % of development capacity spent on technical debt

- Baseline: Current (likely 40-60%)

- Target: 20-30%

- Measurement: Tag work items as technical debt

- Frequency: Quarterly

- Why it matters: Team capacity available for new value

2. Health Metrics (Team & Organization)

Team Satisfaction:

- Definition: How satisfied are team members with work environment?

- Measurement: Quarterly survey (10 questions, 5-point scale)

- Sample questions:

  - I have clarity on team goals and priorities

  - I have the tools and resources I need

  - I can collaborate effectively with my team

  - I'm learning and growing in my role

  - I would recommend this team to others

- Target: Average 4/5 or higher

- Frequency: Quarterly

- Why it matters: Team health predicts performance

Business Stakeholder Satisfaction:

- Definition: How satisfied are business stakeholders with IT?

- Measurement: Quarterly survey (5-7 questions, 5-point scale)

- Sample questions:

  - IT understands my business needs

  - IT delivers value in a timely manner

  - IT communicates progress effectively

  - My Product Owner is responsive and helpful

  - I would recommend my IT team to peers

- Target: Average 4/5 or higher (up from likely 3/5 baseline)

- Frequency: Quarterly

- Why it matters: Business partnership quality

Employee Turnover:

- Definition: % of employees leaving (voluntary + involuntary)

- Baseline: Current rate

- Target: <10% annual turnover for key staff

- Measurement: HR data

- Frequency: Quarterly review, annual calculation

- Why it matters: Retention of talent and knowledge

Skills Growth:

- Definition: Training, certifications, skill development

- Metrics:

  - Training hours per person (target: 40/year)

  - Certifications earned

  - Internal mobility (promotions, role changes)

- Frequency: Quarterly review

- Why it matters: Organizational capability growth

Psychological Safety:

- Definition: Team members feel safe to take risks, speak up

- Measurement: Included in team satisfaction survey

- Sample questions:

  - I feel comfortable raising concerns or disagreements

  - When I make a mistake, it's not held against me

  - Team members value my opinions

  - I can ask for help when needed

- Target: High scores (4.5/5+)

- Frequency: Quarterly

- Why it matters: Foundational for high performance

3. Business Metrics (Value Delivered)

These vary by domain, but examples:

Overall IT:

- % Capacity on New Features: Track time on new features vs. maintenance

  - Baseline: 20% new features

  - Target: 65%+ new features

- Business Value Delivered: Estimated value of delivered features (€)

  - Track quarterly with Product Owners

  - Target: 100% increase year over year

Customer Experience Team:

- Customer Satisfaction (CSAT, NPS)

- Self-service adoption (% of inquiries self-served)

- Customer portal usage (active users, session time)

Order-to-Cash Team:

- Order processing time (hours or days to process order)

- Invoice accuracy (% of invoices without errors)

- Days Sales Outstanding (DSO - how fast customers pay)

Supply Chain Team:

- Inventory turnover (how efficiently inventory used)

- Stockout rate (% of time out of stock)

- Procurement cycle time (days from PO to receipt)

Product Data Team:

- Time to launch new product (days from concept to available)

- Product data quality score (% complete and accurate)

- Pricing accuracy (% of quotes with correct pricing)

Data Platform Team:

- Data quality scores (% of data meeting quality standards)

  - Target: 95%+ for tier 1 data

- Self-service adoption (% of data requests self-served)

  - Target: 60%+

- Time to insight (days from question to answer for analysts)

  - Target: <1 day

AI/ML Team:

- Models in production (count)

- Model accuracy (vs. baseline)

- Business value from AI (€ impact)

  - Example: Churn prediction reduced churn by 20% = €15M value

Integration Platform Team:

- Platform availability (uptime)

  - Target: 99.9%+

- Integration delivery time (days to complete standard integration)

  - Target: 3-5 days

- Adoption rate (% of integrations using platform)

  - Target: 80%+

### Success Criteria by Milestone

Month 6 Success Criteria:

- ✅ EA hired and Architecture Review Board operational

- ✅ Platforms selected and deploying

- ✅ 1-2 pilot teams operational and delivering

- ✅ Quick wins delivered (€600K+ value or savings)

- ✅ Team satisfaction stable or improving

- ✅ Architecture practice established

- ✅ Communication and change management active

Month 12 Success Criteria:

- ✅ 50%+ of teams in stream-aligned model

- ✅ Integration platform handling 15+ integrations

- ✅ Data warehouse operational with 5+ sources

- ✅ Lead time reduced 30%+

- ✅ Team and stakeholder satisfaction improving

- ✅ Platform teams formed and operational

- ✅ Data quality at 90%+ for tier 1 data

Month 18 Success Criteria:

- ✅ All teams in stream-aligned model

- ✅ First AI models in production

- ✅ Platform adoption >70%

- ✅ Lead time reduced 40%+

- ✅ Business value delivery doubled

- ✅ Architecture and data practices mature

- ✅ Vendor portfolio optimized

Month 24 Success Criteria (Transformation Complete):

- ✅ New operating model the "new normal"

- ✅ Lead time reduced 50%

- ✅ 65%+ capacity on new features (vs. 20% baseline)

- ✅ Team satisfaction 4/5+

- ✅ Business stakeholder satisfaction 4/5+

- ✅ 5+ AI models delivering business value

- ✅ Self-service platforms widely adopted

- ✅ Data-driven decision making embedded

- ✅ Technical debt ratio <30%

- ✅ €10M+ incremental business value per year

### Metrics Dashboard

Executive Dashboard (Monthly review):

- Lead time trend (graph)

- Deployment frequency trend

- Business value delivered (€, quarterly)

- Team satisfaction (score, trend)

- Business stakeholder satisfaction (score, trend)

- Transformation progress (% complete)

- Key risks (red/amber/green)

IT Leadership Dashboard (Weekly review):

- All delivery metrics (detailed)

- Team health metrics by team

- Platform adoption and performance

- Incidents and issues

- Hiring and skill development status

- Budget vs. actual

Team Dashboards (Daily visibility):

- Current sprint progress

- Work in progress (WIP)

- Lead time (current items)

- Deployment frequency

- Quality metrics (bugs, technical debt)

Reporting Cadence:

- Daily: Teams review own metrics

- Weekly: IT leadership reviews aggregate

- Monthly: CTO reviews with executive team

- Quarterly: Deep dive with board

## Risk Management

### Top Risks & Mitigations:

Risk 1: Transformation takes too long, business loses patience

- Mitigation:

  - Focus on quick wins in first 6 months

  - Phased approach with visible milestones

  - Pilot teams show value early

  - Regular communication of progress

- Probability: Medium | Impact: High

Risk 2: Key people leave during transformation

- Mitigation:

  - Retention bonuses for critical staff

  - Clear growth opportunities

  - Involve them in decisions

  - Heavy investment in training

- Probability: Medium | Impact: High

Risk 3: Budget overruns

- Mitigation:

  - Phased investment approach

  - Start with must-haves, add nice-to-haves later

  - Build business case with buffer

  - Track spending monthly

- Probability: Medium | Impact: Medium

Risk 4: Platform selections don't work out

- Mitigation:

  - Thorough POCs before commitment

  - Start with vendor trials

  - Get reference customers

  - Plan for multi-year contracts but with exit clauses

- Probability: Low | Impact: High

Risk 5: Stream-aligned teams don't work (boundaries are wrong)

- Mitigation:

  - Start with pilot teams

  - Expect to adjust boundaries after 6-12 months

  - Use Domain-Driven Design to find natural boundaries

  - Keep teams flexible initially

- Probability: Medium | Impact: Medium

Risk 6: Data quality is worse than expected

- Mitigation:

  - Start with data quality assessment

  - Plan for significant data cleansing

  - Build data quality monitoring from day one

  - Don't promise AI/ML until data is ready

- Probability: High | Impact: Medium

Risk 7: Vendor lock-in with SaaS platforms

- Mitigation:

  - Data portability in all contracts

  - Standard data formats

  - API-first integration (not vendor-specific)

  - Regular reviews of vendor value

- Probability: Medium | Impact: Medium

Risk 8: Integration platform becomes bottleneck

- Mitigation:

  - Invest in Integration Platform team early

  - Create reusable templates

  - Self-service capabilities for stream teams

  - Clear SLAs for integration requests

- Probability: Medium | Impact: High

Risk 9: Business doesn't adopt new ways of working

- Mitigation:

  - Embed BAs in stream teams

  - Product Owners from business side

  - Regular showcases and demos

  - Business representation in governance boards

- Probability: Medium | Impact: High

Risk 10: Scope creep (trying to do everything at once)

- Mitigation:

  - Strict phasing with clear gates

  - Architecture Review Board controls scope

  - Say "no" or "later" frequently

  - Focus on foundations first

- Probability: High | Impact: Medium

### Risk Register

Top 10 Risks with mitigation strategies:

RISK 1: Enterprise Architect Hire Delays

Description: Can't find or hire EA quickly, delays entire transformation

Probability: Medium
Impact: High
Risk Score: HIGH

Mitigation:

- Use executive recruiter (start Month 1)

- Expand search geographically (remote OK)

- Consider interim consultant EA while searching

- Pre-approve competitive compensation

- Fast-track interview process (2-3 weeks max)

Contingency:

- If not hired by Month 3: Engage external EA consultant (6-month contract)

- Continue recruiting in parallel

RISK 2: Key People Leave During Transformation

Description: High performers or domain experts leave due to uncertainty, change fatigue

Probability: Medium
Impact: High
Risk Score: HIGH

Mitigation:

- Early career conversations (Month 1-3)

- Clear growth paths and opportunities

- Retention bonuses for critical staff (top 10-15 people)

- Heavy involvement in transformation (ownership)

- Transparent communication

- Quick wins to build confidence

Contingency:

- Knowledge transfer documentation

- Cross-training and redundancy

- External contractors to backfill temporarily

- Accelerated hiring for replacements

Monitor: Monthly 1:1s, pulse surveys, engagement scores

RISK 3: Pilot Teams Struggle or Fail

Description: Pilot teams don't show improvement, undermines entire transformation

Probability: Medium
Impact: High
Risk Score: HIGH

Mitigation:

- Choose pilot teams carefully (motivated, clear boundaries)

- Heavy support for pilots (architects, coaching, resources)

- Clear success criteria

- Weekly check-ins with pilots

- Adjust quickly based on feedback

- Start with easier domains (not most complex)

Contingency:

- If struggling at Month 3: Intensive intervention (more resources, coaching)

- If failing at Month 5: Pivot approach, learn lessons, try different team

- Be transparent about challenges and adjustments

RISK 4: Platform Selection Wrong or Takes Too Long

Description: Selected platform doesn't meet needs or evaluation drags on

Probability: Medium
Impact: Medium-High
Risk Score: MEDIUM-HIGH

Mitigation:

- Time-boxed evaluation (6 weeks max)

- Clear evaluation criteria upfront

- POCs with real use cases

- Reference customers

- EA leads evaluation (expert judgment)

- Start with good-enough, can adjust later

Contingency:

- If platform doesn't work: Switch platforms (costly but possible)

- Multi-platform strategy if one platform can't do everything

- Build internal tools as last resort (but avoid if possible)

RISK 5: Business Loses Patience or Support

Description: Business stakeholders lose faith, pull support, reduce funding

Probability: Medium
Impact: High
Risk Score: HIGH

Mitigation:

- Quick wins in first 6 months (visible value)

- Constant communication (monthly business updates)

- Involve business in transformation (steering committee)

- Show metrics and progress

- Pilot teams in business-critical domains

- Product Owners from business side (skin in the game)

Contingency:

- If support waning: Executive intervention, showcase successes

- Adjust timeline or scope if needed (deliver less faster)

- Focus on highest-value initiatives

Early Warning: Business stakeholder satisfaction scores, steering committee feedback

RISK 6: Data Quality Worse Than Expected

Description: Data quality so poor that analytics and AI impossible

Probability: Medium-High
Impact: Medium
Risk Score: MEDIUM-HIGH

Mitigation:

- Data quality assessment early (Month 3-4)

- Plan for significant data cleansing (time and budget)

- Data quality monitoring from day one

- Start with best-quality data sources

- Don't promise AI until data ready

- Communicate realistic timelines

Contingency:

- If data quality <70%: Delay AI initiatives, focus on data foundation

- Invest more in data cleansing

- Source data improvements at origin (fix root causes)

- Adjust expectations and timeline

RISK 7: Budget Overruns

Description: Costs exceed budget, need additional funding

Probability: Medium
Impact: Medium
Risk Score: MEDIUM

Mitigation:

- 10-15% contingency buffer built in

- Monthly budget tracking

- Forecast to complete each quarter

- Phased investment (can slow if needed)

- Quick wins fund some costs (self-funding)

- Prioritize must-haves over nice-to-haves

Contingency:

- If overrun likely: Present to CFO early with justification

- Identify scope that can be deferred

- Slow hiring or delay less critical hires

- Reduce external consulting

Track: Monthly actuals vs. budget, quarterly forecasts

RISK 8: Change Fatigue and Resistance

Description: Teams overwhelmed, resist change, morale drops

Probability: Medium-High
Impact: Medium
Risk Score: MEDIUM-HIGH

Mitigation:

- Phased approach (not big bang)

- Heavy change management (communication, support)

- Celebrate wins frequently

- Address concerns proactively

- Provide support resources

- Adjust pace if needed

- Make it safe to raise concerns

Contingency:

- If fatigue high: Slow transformation pace

- Provide more support (coaching, counseling)

- Give teams recovery time

- Focus on team health before pushing forward

Monitor: Team satisfaction surveys, 1:1 feedback, sick days/PTO usage

RISK 9: Integration Platform Becomes Bottleneck

Description: Platform team can't keep up with demand, teams blocked

Probability: Medium
Impact: Medium
Risk Score: MEDIUM

Mitigation:

- Self-service capabilities from day one

- Reusable connectors and templates

- Clear SLAs and prioritization

- Office hours for teams

- Add platform team capacity if needed

- Measure and optimize request fulfillment time

Contingency:

- If bottleneck occurs: Hire additional integration specialists

- Prioritize ruthlessly (most impactful integrations first)

- Teams can do simple integrations themselves (training)

- External contractors temporarily

Track: Platform team backlog, request fulfillment time, team complaints

RISK 10: Vendor Lock-In or Vendor Failure

Description: Become too dependent on vendor, or vendor goes out of business

Probability: Low-Medium
Impact: Medium-High
Risk Score: MEDIUM

Mitigation:

- Data portability in all contracts

- Standard data formats and APIs

- Exit clauses in contracts

- Regular vendor health checks

- Don't over-customize proprietary platforms

- Multi-vendor strategy where appropriate

Contingency:

- If vendor failing: Accelerate exit plans

- Data extraction and migration

- Alternative vendor already evaluated

- Can build internal solution as last resort

Monitor: Vendor financial health, market position, customer references

### Risk Management Process

Monthly Risk Review (Transformation Steering Committee):

- Review risk register

- Update probability and impact

- Assess mitigation effectiveness

- Identify new risks

- Escalate high risks

- Track risk trends

Risk Dashboard:

- Risk heat map (probability x impact)

- Top 5 risks highlighted

- Mitigation status for each

- Risk trend (increasing/stable/decreasing)

Risk Escalation:

- Low/Medium risks: Managed by transformation team

- High risks: Escalated to steering committee

- Critical risks: Escalated to CTO/Executive team

### Red Flags to Watch For

As you execute, watch for these warning signs:

Transformation Risks

🚩 Architects become ivory tower

- Sign: Teams complaining architects slow them down

- Fix: Architects embedded in teams, pair programming, office hours

🚩 Platform teams become bottlenecks

- Sign: 2-3 week backlog for simple integrations

- Fix: Self-service capabilities, better tooling, more staff

🚩 Product Owners are POs in name only

- Sign: Still escalating every decision to committees

- Fix: Give them real authority or find different people

🚩 Stream teams aren't really independent

- Sign: Constant dependencies, waiting on other teams

- Fix: Revisit team boundaries, improve APIs

🚩 Data quality isn't improving

- Sign: Still at 70% quality after 12 months

- Fix: Stronger data governance, ownership accountability, tooling

🚩 Business doesn't see value

- Sign: Satisfaction scores declining or flat

- Fix: Better communication, more showcases, measure business metrics

🚩 Key people leaving

- Sign: Losing senior developers, good managers

- Fix: Career conversations, retention bonuses, address concerns

🚩 Change fatigue setting in

- Sign: People disengaging, cynicism increasing

- Fix: Celebrate wins, show progress, address concerns, pace yourself

🚩 Costs growing faster than value

- Sign: Spending ahead of plan, value behind plan

- Fix: Ruthless prioritization, cut nice-to-haves, focus on fundamentals

🚩 Pilot teams not delivering

- Sign: 6 months in, no visible improvement

- Fix: Understand why, adjust model, provide more support

Technical Risks

🚩 Integration platform not being adopted

- Sign: Teams still building point-to-point integrations

- Fix: Make platform easier, provide templates, mandate usage

🚩 Data warehouse is "garbage in, garbage out"

- Sign: Analysts don't trust the data

- Fix: Data quality initiatives, governance, ownership

🚩 Cloud costs spiraling

- Sign: Monthly bills 30%+ over budget

- Fix: Cost monitoring, optimization, governance

🚩 Security incidents increasing

- Sign: More breaches, audit findings

- Fix: Accelerate security architect hire, vendor reviews

🚩 Technical debt not decreasing

- Sign: Still spending 50% time on maintenance

- Fix: Dedicated technical debt sprints, architecture improvements

## Budget & Business Case

### Investment overview

Let's be realistic about costs. This transformation requires investment.

New Headcount Costs (Year 1-2)

Using rough annual costs (salary + benefits + overhead):

Year 1 New Hires (~€1.5-2M):

- Enterprise Architect: €120-150K

- 2 Solution Architects: €200-240K

- Data Architect: €110-140K

- 2 Integration Specialists: €160-200K

- Head of Vendor Management: €110-140K

- 2 Business Analysts: €140-180K

- 3 Data Engineers: €210-270K

- Product Owner: €90-120K

Year 2 Additional Hires (~€1.2-1.5M):

- 2 Solution Architects: €200-240K

- 2 Business Analysts: €140-180K

- 2 Data Scientists: €180-240K

- 2 ML Engineers: €180-240K

- Security Architect: €110-140K

- 2 Product Owners: €180-240K

Total new headcount investment: €2.7-3.5M over 2 years

Platform & Tools Costs (Annual)

Integration Platform: €100-300K/year

- Depends heavily on volume and connectors

- MuleSoft/Informatica at high end, Boomi/Workato mid-range

Data Platform: €150-400K/year

- Snowflake/Databricks: consumption-based

- Can start small and scale

- Storage costs separate (relatively cheap)

AI/ML Platform: €50-150K/year

- Mostly compute costs

- Starts low, scales with usage

API Management: €30-100K/year

Monitoring/Observability: €50-150K/year

- Scales with infrastructure size

BI/Analytics: €50-200K/year

- Power BI cheapest (included in M365 often)

- Tableau/Qlik more expensive

Data Catalog/Governance: €50-200K/year

Total platform costs: €480K-1.5M/year (wide range based on scale)

Training & Development: €200-400K/year

- Budget €2-5K per person per year

- Critical during transformation

Consulting/Advisory: €200-500K (one-time or Year 1-2)

- Architecture advisory

- Integration patterns

- Change management

- Accelerates transformation

Total Investment Summary:

- Year 1: €3-4.5M (headcount + platforms + training + consulting)

- Year 2: €3.5-5M (more headcount + platforms + training)

- Ongoing: €2.5-4M/year (platforms + training + ongoing hires)

ROI Expectations:

This is significant investment. Where does payback come from?

Faster delivery (30-50% improvement):

- If your IT org currently delivers €10M/year in business value

- 40% improvement = €4M/year additional value

- Payback in ~18 months

Reduced integration costs:

- Currently: point-to-point integrations, custom code, fragile

- Future: standardized platform, reusable patterns

- Typical reduction: 40-60% of integration effort

- If you spend €1M/year on integration, save €400-600K

Better SaaS decisions:

- Avoid duplicate purchases: €100-300K/year

- Better negotiations: 10-20% savings on contracts

- Faster implementations: 30% reduction in project costs

Data/AI value:

- Hard to quantify initially

- Typical payback: 3-5X investment over 3 years

- Examples: churn reduction, pricing optimization, process automation

Reduced technical debt:

- Currently: likely spending 40-60% of capacity on maintenance

- Target: 20-30% on maintenance, 70-80% on new features

- Unlocks significant capacity

Business case template:

- Investment: €3-4.5M Year 1, €3.5-5M Year 2

- Returns:

  - Faster delivery: +€4M/year value

  - Integration savings: €500K/year

  - SaaS optimization: €300K/year

  - Reduced technical debt: +€2M/year capacity

- Payback: 12-18 months

- 3-year NPV: Significantly positive

### Total Investment Summary

Year 1: €3.0-4.5M

- New headcount: €1.5-2M

- Platforms & tools: €480K-1M

- Training & development: €200-400K

- Consulting & advisory: €200-500K

- Contingency: €200-400K

Year 2: €3.5-5M

- Additional headcount: €1.2-1.5M

- Platforms & tools (full year): €600K-1.2M

- Training & development: €200-400K

- Consulting (reduced): €100-200K

- Contingency: €200-400K

Year 3+ (Steady State): €2.5-4M/year

- Incremental headcount: €1-1.5M

- Platforms & tools: €600K-1.2M

- Training & development: €200-400K

- Continuous improvement: €200-400K

### Detailed Budget Breakdown

New Headcount Costs (Fully-loaded: salary + benefits + overhead):

Year 1 Hires (~€1.5-2M):

| Role | Count | Cost Each | Total |
| --- | --- | --- | --- |
| Enterprise Architect | 1 | €130-160K | €130-160K |
| Solution Architects | 2 | €95-125K | €190-250K |
| Data Architect | 1 | €100-130K | €100-130K |
| Integration Specialists | 2 | €75-100K | €150-200K |
| Head of Vendor Mgmt | 1 | €100-130K | €100-130K |
| Business Analysts | 2 | €70-95K | €140-190K |
| Data Engineers | 3 | €75-100K | €225-300K |
| Product Owners | 2 | €85-110K | €170-220K |
| Security Architect | 1 | €100-130K | €100-130K |
| Year 1 Total | 15 |  | €1,305-1,710K |

Year 2 Additional Hires (~€1.2-1.5M):

| Role | Count | Cost Each | Total |
| --- | --- | --- | --- |
| Solution Architects | 2 | €95-125K | €190-250K |
| Business Analysts | 2 | €70-95K | €140-190K |
| Data Scientists | 2 | €85-115K | €170-230K |
| ML Engineers | 2 | €85-115K | €170-230K |
| Integration Engineers | 2 | €75-100K | €150-200K |
| Product Owners | 2 | €85-110K | €170-220K |
| Platform Engineers | 2 | €85-110K | €170-220K |
| Year 2 Total | 14 |  | €1,160-1,540K** |

Platform & Tools Costs (Annual):

| Platform/Tool | Year 1 | Year 2+ |
| --- | --- | --- |
| Integration Platform (MuleSoft, Boomi, etc.) | €100-250K | €150-300K |
| Data Platform (Snowflake, Databricks, etc.) | €100-300K | €200-500K |
| AI/ML Platform (Azure ML, SageMaker) | €0-50K | €75-150K |
| API Management | €20-80K | €30-100K |
| Monitoring/Observability | €30-100K | €50-150K |
| BI/Analytics | €30-150K | €50-200K |
| Data Catalog | €30-150K | €50-200K |
| DevOps Tools | €20-50K | €30-70K |
| Collaboration & PM | €20-50K | €30-70K |
| Security Tools | €30-80K | €40-100K |
| Training Platforms | €10-30K | €15-40K |
| TOTAL Platforms | €390-1,290K | €720-1,880K |

Note: Costs vary widely based on:

- Usage (consumption-based pricing)

- Number of users/licenses

- Feature tiers

- Cloud provider chosen

- Negotiated discounts

Training & Development:

| Category | Year 1 | Year 2 | Year 3+ |
| --- | --- | --- | --- |
| External training (courses, bootcamps) | €80-150K | €60-120K | €60-120K |
| Certifications (exams, prep) | €40-80K | €40-80K | €40-80K |
| Conferences (registration, travel) | €40-80K | €50-100K | €50-100K |
| Online learning platforms | €15-30K | €15-30K | €15-30K |
| Internal training (consultants) | €25-60K | €15-40K | €10-30K |
| TOTAL Training | €200-400K | €180-370K | €175-360K |

Consulting & Advisory:

| Service | Year 1 | Year 2 |
| --- | --- | --- |
| Architecture advisory | €80-200K | €30-80K |
| Change management consulting | €60-150K | €30-70K |
| Platform implementation support | €40-100K | €20-50K |
| Executive coaching | €20-50K | €10-30K |
| TOTAL Consulting | €200-500K | €90-230K |

### Value Realization (Benefits)

Faster Delivery (Primary benefit):

- Current: 20% capacity on new features = 10 person-years = €1M direct cost, enables ~€3M business value

- Future: 65% capacity on new features = 49 person-years = €4.9M direct cost, enables ~€15M business value

- Incremental value: ~€12M/year business value enabled

- Conservative estimate: €6M/year (50% success rate)

Integration Cost Reduction:

- Current: Point-to-point integrations, €1M/year estimated

- Future: Platform-based, 60% effort reduction = €400K/year

- Savings: €600K/year

SaaS Optimization:

- Duplicate elimination: €200K/year

- Better negotiations: €100K/year

- License optimization: €100K/year

- Savings: €400K/year

Technical Debt Reduction:

- Free up capacity from 50% to 25% maintenance

- 25% × 75 people = 18.75 person-years freed

- Value: €1.9M/year additional capacity

- Conservative: €1M/year

Data & Analytics Value:

- Better business decisions

- Operational efficiency

- Inventory optimization

- Customer insights

- Conservative estimate: €2M/year

AI Value (Year 3+):

- Churn reduction

- Demand forecasting

- Predictive maintenance

- Pricing optimization

- Conservative estimate: €3M/year (Year 3+)

### ROI Calculation

| Year | Investment | Annual Value | Cumulative Value | Cumulative Investment | Net Benefit |
| --- | --- | --- | --- | --- | --- |
| 0 (Baseline) | €0 | €0 | €0 | €0 | €0 |
| 1 | €3.5M | €3M | €3M | €3.5M | -€0.5M |
| 2 | €4.5M | €7M | €10M | €8.0M | +€2.0M |
| 3 | €3.0M | €13M | €23M | €11.0M | +€12.0M |
| 4 | €3.0M | €13M | €36M | €14.0M | +€22.0M |
| 5 | €3.0M | €13M | €49M | €17.0M | +€32.0M |

Value Breakdown (Conservative Estimates):

- Year 1: Faster delivery (€2M) + SaaS optimization (€400K) + Integration savings (€600K) = €3M

- Year 2: All Year 1 + Technical debt (€1M) + Data/Analytics (€2M) = €7M

- Year 3+: All Year 2 + AI value (€3M) + Scale benefits (€3M) = €13M/year

Key Metrics:

- Payback Period: 18 months

- 3-Year ROI: 109% ((€23M - €11M) / €11M)

- 5-Year ROI: 188% ((€49M - €17M) / €17M)

- 5-Year NPV (10% discount rate): ~€20M

Risk-Adjusted ROI (Apply 70% probability to all benefits):

- 3-Year Risk-Adjusted ROI: 46%

- 5-Year Risk-Adjusted ROI: 102%

- Still highly positive

### Phased Investment Approach

To manage cash flow and risk:

Minimum Viable Investment (If budget constrained):

- Year 1: €2.5M (essential hires + one platform + minimal training)

  - Enterprise Architect, 2 Solution Architects, Data Architect

  - Integration Platform OR Data Platform (pick one)

  - Basic training

- Year 2: Add what was deferred

- Risk: Slower transformation, less capability

Recommended Investment:

- Year 1: €3.5M (as detailed above)

- Year 2: €4.5M (scale up)

- Year 3+: €3M/year (steady state)

- Best balance of speed and investment

Aggressive Investment (If appetite for faster transformation):

- Year 1: €5M (hire faster, both platforms simultaneously, heavy consulting)

- Year 2: €5M (full team quickly)

- Benefit: Faster value realization (6 months sooner)

- Risk: Change fatigue, harder to absorb change

### Cost Avoidance

In addition to direct benefits, transformation avoids future costs:

Technical Debt Compounding:

- Current trajectory: Technical debt grows 15%/year

- Without transformation: €1M tech debt cost becomes €1.5M in 3 years

- With transformation: Managed and reduced

- Avoidance: €500K+/year

Failed Projects:

- Historical failure rate: 30% of projects fail or significantly delayed

- Without architecture: Failures continue or worsen

- With architecture: Catch mistakes early

- Example: One avoided failed project = €500K-1M saved

Vendor Lock-In:

- Without vendor management: Locked into unfavorable terms

- With vendor management: Exit options and negotiating power

- Avoidance: €200K+/year in better contracts

Security Incidents:

- Without security architecture: Higher breach risk

- Average data breach cost: €3-5M

- With security architecture: Reduced risk

- Avoidance: Difficult to quantify but significant

Talent Loss:

- Without modern practices: Harder to recruit/retain top talent

- Cost of backfill: 1.5-2X salary + lost productivity

- With modern practices: Competitive employer

- Avoidance: €500K+/year in reduced turnover costs

Total Cost Avoidance: €2M+/year (conservative)

### Sensitivity Analysis

What if benefits are 50% lower than projected?

| Scenario | Year 3 Value | 3-Year ROI | Still Worth It? |
| --- | --- | --- | --- |
| Base Case | €23M | 109% | ✅ Yes |
| 50% of Benefits | €11.5M | 5% | ✅ Yes (breakeven) |
| 30% of Benefits | €6.9M | -37% | ⚠️ Marginal |

Conclusion: Even at 50% of projected benefits, transformation breaks even. Need at least 35-40% of benefits to justify investment.

What if transformation takes 50% longer?

| Scenario | Payback | 3-Year ROI | Impact |
| --- | --- | --- | --- |
| Base Case | 18 months | 109% | Base |
| 50% Slower | 27 months | 65% | Still positive |
| 100% Slower | 36 months | 35% | Still positive, but less attractive |

Conclusion: Even with significant delays, transformation still delivers positive ROI, just slower.

### Funding Model

Option 1: Centralized IT Budget (Traditional)

- All costs come from IT budget

- CTO controls allocation

- Pros: Simple, clear accountability

- Cons: IT seen as cost center

Option 2: Business-Funded Product Teams (Recommended)

- Stream-aligned teams funded by business units

  - Customer Experience team: Sales budget

  - Order-to-Cash team: Finance budget

  - Supply Chain team: Operations budget

- Platform teams: Shared IT budget

- Architecture and governance: IT budget

- Pros: Business ownership, product thinking

- Cons: More complex budgeting

Option 3: Hybrid (Pragmatic)

- Year 1-2: Centralized (transformation investment)

- Year 3+: Transition to business-funded teams

- Pros: Simpler during transformation, evolves to product model

- Cons: Transition complexity

Recommendation: Start with Option 1, evolve to Option 2 by Year 3

### Budget Approval Process

Month 1: Initial Approval

- Present transformation vision to executive team

- Request approval for Year 1 budget (€3.5M)

- Approval from: CTO, CFO, CEO

- Board awareness (if needed)

Month 6: Checkpoint

- Review progress and spending

- Request continuation approval

- Adjust if needed based on learnings

Month 12: Year 2 Budget

- Present Year 1 results and ROI progress

- Request Year 2 budget (€4.5M)

- Show quick wins and momentum

- Approval from: CTO, CFO, CEO

Quarterly: Budget Reviews

- Track actuals vs. budget

- Forecast to complete

- Adjust allocations as needed

- Report variances and reasons

### Quick Wins to Fund Transformation

Self-funding opportunities (partially offset transformation costs):

Vendor Consolidation (Months 1-6):

- Eliminate duplicate SaaS tools

- Target: €100-200K annual savings

- Reinvest in transformation

License Optimization (Months 3-9):

- Reclaim unused licenses

- Downgrade over-provisioned users

- Target: €100-200K annual savings

Contractor Reduction (Months 6-12):

- As internal capability builds, reduce contractor spend

- Target: €200-400K annual savings

Cloud Cost Optimization (Months 6-12):

- Right-size infrastructure

- Reserved instances

- Eliminate waste

- Target: €100-200K annual savings

Total Self-Funding: €500K-1M/year

- Offsets 15-30% of transformation costs

- Makes business case even stronger

### Business Case

Let me provide a detailed business case template.

Current State Costs (Annual)

IT Personnel: €5M

- Developers, testers, functional analysts, managers

- Current headcount: ~50 people

- Average fully-loaded cost: €100K

Infrastructure & Operations: €1.5M

- Servers, hosting, cloud services

- Network, security tools

- Maintenance, support contracts

SaaS Subscriptions: €800K

- Various SaaS tools (some duplicates)

- Likely underreported (shadow IT)

Projects/Contractors: €1M

- External consultants

- Project-based contractors

- System integrators

Total Current IT Spend: €8.3M/year

Current Capacity Allocation:

- 50% Maintenance / technical debt / keeping lights on

- 30% Small enhancements / fixes

- 20% New features / projects

Business Value Delivered: ~€10M/year

- Rough estimate based on new capabilities

- 20% of capacity × 50 people × €100K productivity = €1M direct

- Enabling business outcomes: ~€10M

Future State Costs (Annual, Steady State Year 3)

IT Personnel: €7.5M

- 75 people (50 existing + 25 new hires)

- Includes architects, BAs, data scientists, platform engineers, POs, etc.

- Some attrition offset by internal promotions

Infrastructure & Platforms: €2.5M

- Integration platform: €200K

- Data platform: €300K

- AI/ML platform: €150K

- API management: €100K

- Monitoring/observability: €150K

- BI/Analytics: €100K

- Cloud infrastructure: €1M (increased usage)

- Data catalog, security tools, etc.: €500K

SaaS Subscriptions: €500K

- Consolidated from €800K (savings from eliminating duplicates)

- Better negotiated rates

Training & Development: €300K

- Ongoing investment in skills

Total Future State IT Spend: €10.8M/year

Future Capacity Allocation:

- 25% Maintenance (reduced from 50%)

- 10% Technical debt (reduced from included in 50%)

- 65% New features / projects (increased from 20%)

Business Value Delivered: €20M/year

- 65% of capacity × 75 people × €100K productivity = €4.9M direct

- Enabling business outcomes: ~€20M (faster time to market, better data, AI value)

Investment Summary

Year 1:

- Incremental cost: €3M

- New hires: 15 people (phased)

- Platforms: initial investments

- Consulting: €500K

- Training: €300K

Year 2:

- Incremental cost: €2M

- New hires: 10 more people

- Platforms: full annual costs

- Training: €300K

Year 3+:

- Incremental cost: €2.5M/year (steady state)

- Ongoing platform costs

- Continuous hiring/training

Total 3-Year Investment: €7.5M

Value Realization

Faster Delivery (Primary benefit):

- Current: 20% capacity on new features = €2M value/year

- Future: 65% capacity on new features = €6.5M value/year

- Incremental value: €4.5M/year

Reduced Integration Costs:

- Current: €1M/year on integration projects (estimated)

- Future: €400K/year (60% reduction via platform)

- Savings: €600K/year

SaaS Optimization:

- Eliminate duplicates: €200K/year

- Better contract negotiations: €100K/year

- Savings: €300K/year

Technical Debt Reduction:

- Freeing capacity from 50% to 25% maintenance = 25% × 75 people = 18.75 person-years

- Value: €1.9M/year in freed capacity

Data & Analytics Value:

- Better business decisions

- Operational efficiency improvements

- Conservative estimate: €2M/year value

- (Examples: inventory optimization, churn reduction, pricing optimization)

AI Value (Year 3+):

- First AI models in production

- Conservative estimate: €3M/year value

- (Examples: predictive maintenance, demand forecasting, lead scoring)

Total Annual Value (Year 3+): €12.3M/year

ROI Calculation

| Year | Investment | Annual Value | Cumulative Value | Cumulative Investment | Net |
| --- | --- | --- | --- | --- | --- |
| 1 | €3.0M | €2M | €2M | €3.0M | -€1.0M |
| 2 | €2.0M | €6M | €8M | €5.0M | +€3.0M |
| 3 | €2.5M | €12.3M | €20.3M | €7.5M | +€12.8M |

Payback Period: 18 months

3-Year ROI: (€20.3M - €7.5M) / €7.5M = 170%

5-Year NPV (using 10% discount rate): €32M

Risk-Adjusted ROI

Apply probability to value realization:

- Faster delivery (90% probability): €4.5M × 0.9 = €4.05M

- Integration savings (80%): €600K × 0.8 = €480K

- SaaS optimization (95%): €300K × 0.95 = €285K

- Technical debt (70%): €1.9M × 0.7 = €1.33M

- Data/Analytics (60%): €2M × 0.6 = €1.2M

- AI value (50%): €3M × 0.5 = €1.5M

Risk-Adjusted Annual Value: €8.85M/year

Risk-Adjusted 3-Year ROI: 118%

Still very attractive.

Intangible Benefits (not monetized but significant):

- Business satisfaction: Happier business stakeholders

- Employee satisfaction: Modern skills, clearer roles, better tools

- Competitive advantage: Faster innovation, data-driven decisions

- Risk reduction: Better security, vendor management, data governance

- Scalability: Organization ready for growth

- Agility: Can respond faster to market changes

## Conclusion

This comprehensive guide provides everything needed to transform your IT organization from a development-focused structure to a modern orchestration model capable of managing SaaS, custom development, integrations, data, and AI.

Your transformation from a pure development shop to a modern IT organization is both necessary and achievable. Here's what success looks like:

What You're Building:

- An organization that can orchestrate internal development, SaaS platforms, and AI/ML capabilities seamlessly

- Teams that own business outcomes, not just write code

- Platforms that make integration and data access self-service and reliable

- Architecture that provides guardrails without gatekeeping

- Data capabilities that enable insight-driven decisions and competitive advantage

Critical Path:

- Architecture first → hire EA, establish ARB, select platforms

- Platforms second → deploy integration and data platforms

- Team evolution third → pilot stream-aligned teams, then scale

- Data maturity fourth → quality, governance, analytics

- AI last → only after data foundation is solid

Investment Required: €7.5M over 3 years Value Expected: €20M+ over 3 years ROI: 170% (risk-adjusted: 118%) Payback: 18 months

Based on everything we've discussed, here's my advice prioritized:

Critical Success Factors (Must do):

- Hire Enterprise Architect first (Month 1-2)

  - This person helps design everything else

  - Don't make major technology decisions without them

  - Worth paying premium to get right person

- Start with pilots, not big bang

  - Prove stream-aligned model with 1-2 teams

  - Learn and adjust before rolling out

  - Reduces risk, builds confidence

- Invest in platforms early (Months 3-6)

  - Integration platform is foundation for SaaS strategy

  - Data platform is foundation for AI ambitions

  - Don't try to build everything custom

- Data before AI (12-18 months)

  - Get data quality to 90%+ first

  - Build data engineering capability

  - Don't hire data scientists until data is ready

  - Most AI projects fail due to data, not algorithms

- Heavy change management

  - 40% of effort is people, not technology

  - Constant communication

  - Support people through transitions

  - Expect and plan for 10-15% attrition

- Business engagement from day 1

  - Product Owners from business side

  - Business sponsors for transformation

  - Regular showcases and feedback

  - Business value metrics, not just IT metrics

Quick Wins (First 6 months):

- Consolidate duplicate SaaS (Months 1-3)

  - Immediate cost savings

  - Shows vendor management value

  - Easy to communicate

- Architecture prevents one major mistake

  - EA catches team about to buy wrong platform

  - Calculate avoided cost

  - Demonstrates architecture value

- One pilot team delivers faster

  - Measurable lead time improvement

  - Business stakeholder testimonial

  - Proof the model works

- First integration on new platform

  - Faster than custom code would have been

  - More reliable

  - Shows platform value

Common Mistakes to Avoid:

- ❌ Hiring data scientists before data is ready

- ❌ Big bang reorganization on Day 1

- ❌ Platform selections without proper evaluation

- ❌ Underinvesting in change management

- ❌ Product Owners without real authority

- ❌ Platform teams that become bottlenecks

- ❌ Ignoring vendor management until problems arise

- ❌ No quick wins in first 6 months

Key Success Factors

- Start with Architecture - EA hire is critical path

- Prove with Pilots - Don't reorganize everyone at once

- Invest in Platforms - Integration and data platforms are foundational

- Data Before AI - 12-18 months of data foundation before heavy AI investment

- People Over Process - 70% of transformation is change management

- Business Partnership - Product Owners from business side, business outcomes focus

Critical Timeline

- Month 1-3: Foundation (EA, ARB, platform selection)

- Month 4-6: Pilots launch, platforms deploy, quick wins

- Month 7-12: Scale to 50%+ teams, data maturity

- Month 13-18: All teams converted, AI capability building

- Month 19-24: Optimization, AI scaling, continuous improvement

Expected Outcomes (24 Months)

- ✅ Lead time reduced 50% (from 6-8 weeks to 3-4 weeks)

- ✅ 65% capacity on new features (from 20%)

- ✅ Team satisfaction 4/5+ (from 3/5)

- ✅ Business stakeholder satisfaction 4/5+ (from 2.5/5)

- ✅ Self-service platforms widely adopted

- ✅ Data quality 95%+ for tier 1 data

- ✅ 5+ AI models in production delivering value

- ✅ €10M+ incremental annual business value

- ✅ ROI: 170% over 3 years

Key Metrics to Track:

Delivery Metrics:

- Lead time (idea to production): Target 50% reduction

- Deployment frequency: Target daily

- Change failure rate: Target <5%

Business Metrics:

- Business stakeholder satisfaction: Target 4/5

- Features delivered per quarter: Track growth

- Time on new features vs maintenance: Target 70/30

Platform Metrics:

- Integration platform adoption: Target 80% of integrations

- Data quality: Target 95%

- Platform availability: Target 99.9%

Financial Metrics:

- IT cost per business transaction: Track trend

- ROI of transformation: Target >150% in 3 years

- SaaS cost optimization: Track savings

Timeline Summary:

- Months 1-6: Foundation (architecture, platforms, pilots)

- Months 7-12: Expansion (more teams, data maturity, quick wins)

- Months 13-18: Scale (all teams, advanced analytics, AI planning)

- Months 19-24: Optimize (AI delivery, continuous improvement)

Year 3+: Mature state, continuous evolution

Investment

- Total 3-Year Investment: €11M

- Total 3-Year Value: €23M

- Net Benefit: €12M

- Payback: 18 months

The Journey Ahead

This transformation is ambitious but achievable. Organizations globally have successfully made this journey. With clear vision, strong leadership, phased execution, and relentless focus on people and value, your IT organization will emerge as a strategic partner capable of driving business outcomes through technology.

Good luck on your transformation journey!

Remember:

- This is a marathon, not a sprint - 24 months minimum to full maturity

- People before technology - 70% of this is organizational change

- Prove with pilots - Don't bet everything on unproven model

- Quick wins matter - People need to see progress

- Communication is never enough - You'll think you over-communicated, but you haven't

- Data before AI - Don't skip foundations

- Platforms enable autonomy - Done right, they free teams up

- Business partnership is critical - IT transformation only succeeds if business sees value

You've got this. The fact that you're thinking this through carefully, asking the right questions, and willing to make the investment shows you understand what's needed.

My recommendation for Day 1: Schedule a 2-hour session with your IT leadership team. Share the vision from our conversation. Get their input and buy-in. Then start the 30-day plan.

## Reading List & Resources

### Essential Reading (Priority Order)

Tier 1: READ THESE FIRST (Must-Read - Next 3 Months)

These are foundational to your transformation. Read in this order.

1. "Team Topologies" by Matthew Skelton & Manuel Pais ⭐⭐⭐⭐⭐

Why this is #1:

- This IS the blueprint for stream-aligned teams

- Everything we discussed about team structure comes from this book

- You'll reference it constantly during your transformation

- Your leadership team should read this too

What you'll learn:

- Four team types: stream-aligned, platform, enabling, complicated subsystem

- How to design team boundaries using Conway's Law

- Team cognitive load and why teams fail

- Interaction modes between teams

- Organizational sensing and evolution

How to use it:

- Read: Chapters 1-5 (core concepts)

- Skim: Chapters 6-8 (implementation details you can return to)

- Focus on: Chapter 3 (Team-First Thinking), Chapter 5 (Four Team Types)

Action after reading:

- Use their team design templates to map your current teams

- Identify which teams should be stream-aligned, platform, etc.

- Share relevant chapters with your leadership team

Time investment: 8-10 hours ROI: Extremely high - this is your transformation blueprint

2. "The Phoenix Project" by Gene Kim, Kevin Behr, George Spafford ⭐⭐⭐⭐⭐

Why read this:

- It's a novel, easy and engaging read

- You'll see yourself in the protagonist (VP of IT Operations)

- Shows the transformation journey (where you are → where you want to be)

- Great for building empathy and understanding the pain points

- Excellent to share with business stakeholders (they'll finally understand IT challenges)

What you'll learn:

- DevOps principles through story

- Theory of Constraints applied to IT

- Why traditional IT structures fail

- How to identify bottlenecks

- The transformation journey (realistic, with setbacks)

How to use it:

- Read straight through (it's compelling, hard to put down)

- Note parallels to your situation

- Use stories to explain problems to stakeholders

Action after reading:

- Identify your organization's bottlenecks

- Share with business VPs: "This is what we're trying to avoid"

- Use as conversation starter with IT team

Time investment: 6-8 hours (can read in 2-3 sittings) ROI: High - builds understanding and motivation

Bonus: There's a sequel, "The Unicorn Project" (from developer's perspective) - also excellent but optional.

3. "Accelerate" by Nicole Forsgren, Jez Humble, Gene Kim ⭐⭐⭐⭐⭐

Why read this:

- Science-backed research (not opinions)

- Proves that high-performing IT organizations deliver better business outcomes

- Gives you metrics to track transformation success

- Ammunition for business case: "Research shows this works"

What you'll learn:

- Four key metrics: lead time, deployment frequency, MTTR, change failure rate

- 24 capabilities that predict high performance

- Link between IT performance and business outcomes

- Why architecture matters

- Culture and leadership practices

How to use it:

- Part 1 (Research findings): Read carefully, take notes

- Part 2 (Research methods): Skim unless you need to defend methodology

- Focus on: Chapter 4 (Technical Practices), Chapter 10 (Architecture)

Action after reading:

- Baseline your four key metrics today

- Identify which 24 capabilities you're weak on

- Use data to build business case

Time investment: 6-8 hours ROI: High - provides measurable foundation

Tier 2: READ THESE NEXT (Important - Months 2-6)

After you understand the foundation, these add depth in specific areas.

4. "Domain-Driven Design Distilled" by Vaughn Vernon ⭐⭐⭐⭐

(NOT the original Eric Evans book - that's 500+ pages. This is the 176-page practical version)

Why read this:

- Shows how to identify team boundaries (bounded contexts)

- Critical for getting stream-aligned team boundaries right

- Prevents the #1 failure mode: wrong team boundaries

What you'll learn:

- How to identify business domains

- Bounded contexts (team boundaries)

- Context mapping (how teams interact)

- Ubiquitous language (business and IT speaking same language)

How to use it:

- Focus on: Chapters 1-2 (DDD concepts), Chapter 5 (Bounded Contexts)

- Work through exercises: map your business domains

Action after reading:

- Run domain modeling workshop with business + IT

- Define bounded contexts = stream-aligned team boundaries

- Document team interfaces

Time investment: 4-5 hours ROI: High if you're struggling with team boundaries

5. "Good Strategy Bad Strategy" by Richard Rumelt ⭐⭐⭐⭐⭐

Why read this:

- You need a coherent strategy, not just goals

- Helps you articulate transformation strategy clearly

- Teaches how to diagnose challenges and design responses

What you'll learn:

- What makes strategy good vs. bad

- The kernel: diagnosis, guiding policy, coherent action

- How to focus (saying no to good ideas)

- Why "we want to be innovative/agile/data-driven" isn't a strategy

How to use it:

- Read: Part 1 (Good and Bad Strategy) and Part 2 (Sources of Power)

- Apply kernel framework to your transformation

Action after reading:

- Write your transformation strategy using kernel framework:

  - Diagnosis: "Our IT org built for custom dev, now need SaaS/AI capability"

  - Guiding policy: "Move to stream-aligned teams with platform approach"

  - Coherent actions: [your roadmap]

Time investment: 8-10 hours ROI: Very high - sharpens your strategic thinking

6. "Escaping the Build Trap" by Melissa Perri ⭐⭐⭐⭐

Why read this:

- Critical for understanding Product Owner role

- Shifts from output thinking (features) to outcome thinking (value)

- Great for training your future Product Owners

What you'll learn:

- Product-led vs. sales-led vs. visionary-led organizations

- Product management vs. project management

- Product strategy and roadmaps

- Product operations and metrics

How to use it:

- Read entire book (it's accessible and practical)

- Share with your future Product Owners

- Use frameworks for product thinking

Action after reading:

- Assess: Are we in the build trap? (building features nobody uses)

- Create product strategy framework for POs

- Train POs on outcome-based thinking

Time investment: 5-6 hours ROI: High if you're hiring/developing Product Owners

7. "Project to Product" by Mik Kersten ⭐⭐⭐⭐

Why read this:

- Explains shift from project funding to product funding

- Flow Framework for measuring value delivery

- Shows economic model for product-centric organizations

What you'll learn:

- Why project-based funding fails for continuous delivery

- Product value streams

- Flow metrics (alternative to traditional project metrics)

- How to fund product teams

How to use it:

- Focus on: Part 1 (The Age of Software), Part 2 (Flow Framework)

- Skim: Part 3 (detailed implementation)

Action after reading:

- Shift budget conversation from projects to product teams

- Implement Flow Framework metrics

- Educate CFO/Finance on product funding

Time investment: 6-7 hours ROI: Medium-High (depends on your funding model flexibility)

Tier 3: DEPTH IN SPECIFIC AREAS (As Needed - Months 6-12)

Read these based on your specific challenges or interests.

Architecture

8. "Fundamentals of Software Architecture" by Mark Richards & Neal Ford ⭐⭐⭐⭐

- For you and your Enterprise Architect

- Architecture characteristics, styles, and patterns

- How to make architecture decisions

- Read if: You're hiring architects or want to understand their world

- Time: 15-20 hours (it's comprehensive)

9. "Building Evolutionary Architectures" by Neal Ford, Rebecca Parsons, Patrick Kua ⭐⭐⭐⭐

- Architecture that supports change (not rigid)

- Fitness functions for architecture governance

- Read if: Your architecture is brittle and resists change

- Time: 6-8 hours

Data & Analytics

10. "Creating a Data-Driven Organization" by Carl Anderson ⭐⭐⭐⭐

- Practical guide to becoming data-driven

- Building analytics teams

- Data culture and literacy

- Read if: Starting data/analytics transformation

- Time: 6-7 hours

11. "Data Management at Scale" by Piethein Strengholt ⭐⭐⭐

- Modern data architecture patterns

- Data mesh concepts

- Read if: Building data platform capability

- Time: 10-12 hours (technical)

12. "The AI-First Company" by Ash Fontana ⭐⭐⭐

- How to build AI capability

- Data strategy for AI

- Avoiding AI pitfalls

- Read if: Serious about AI transformation

- Time: 5-6 hours

Agile & Product Management

13. "User Story Mapping" by Jeff Patton ⭐⭐⭐⭐

- Excellent practical technique

- Your Business Analysts and Product Owners should read

- Read if: Teams struggle with backlog and prioritization

- Time: 6-8 hours

14. "Inspired" by Marty Cagan ⭐⭐⭐⭐

- Product management at tech companies

- Product discovery and delivery

- Read if: Want to understand best-in-class product management

- Time: 5-6 hours

Change Management & Leadership

15. "Switch: How to Change Things When Change Is Hard" by Chip Heath & Dan Heath ⭐⭐⭐⭐⭐

- Practical framework for change

- Direct the rider, motivate the elephant, shape the path

- Read if: Concerned about resistance to change

- Time: 5-6 hours

- Very accessible and immediately applicable

16. "Leading Change" by John Kotter ⭐⭐⭐⭐

- Classic change management framework

- 8-step process

- Read if: Want structured change approach

- Time: 4-5 hours

17. "Turn the Ship Around!" by L. David Marquet ⭐⭐⭐⭐⭐

- Leadership model: leader-leader vs. leader-follower

- Intent-based leadership

- True story of transforming worst submarine to best

- Read if: Want to build empowered teams

- Time: 5-6 hours

- Highly engaging, practical wisdom

Platform Engineering

18. "Platform Engineering" by Camilla Crispim & Gareth Anderson ⭐⭐⭐

- New book (2023) specifically on platform teams

- Self-service developer platforms

- Read if: Building platform teams

- Time: 6-8 hours

Tier 4: OPTIONAL BUT VALUABLE (When You Have Time)

DevOps & Technical

19. "The DevOps Handbook" by Gene Kim et al. ⭐⭐⭐⭐

- Comprehensive DevOps practices

- Three Ways: Flow, Feedback, Continual Learning

- Skip if: Already read Phoenix Project and Accelerate (some overlap)

- Time: 12-15 hours

20. "Continuous Delivery" by Jez Humble & David Farley ⭐⭐⭐⭐

- Deployment pipeline and automation

- More technical than you need as CTO

- Read if: Want deep technical understanding

- Time: 15-20 hours

Organizational Design

21. "An Everyone Culture" by Robert Kegan & Lisa Lahey ⭐⭐⭐⭐

- Deliberately developmental organizations

- Creating learning culture

- Read if: Focusing on culture transformation

- Time: 8-10 hours

22. "The Lean Startup" by Eric Ries ⭐⭐⭐⭐

- Build-measure-learn cycle

- MVP thinking

- Classic but: Concepts are mainstream now, may already know

- Time: 5-6 hours

Articles & Papers (Free, High-Value)

These are shorter but impactful reads:

23. "How to Win in Software" by Patrick McKenzie (Stripe)

- Free online essay

- Software as competitive advantage

- Link: stripe.com/guides/atlas/how-to-win-in-software

- Time: 30 minutes

- ROI: Very high for understanding software importance to business

24. "How Google Works" articles by Eric Schmidt

- Product management and OKRs at scale

- Engineering culture

- Google re:Work website has excellent resources

- Time: 2-3 hours browsing

- ROI: Learn from best practices

25. State of DevOps Reports (DORA)

- Annual research on DevOps practices

- Free download

- Link: dora.dev or cloud.google.com/devops

- Time: 1-2 hours per year's report

- ROI: Current benchmarks and trends

26. ThoughtWorks Technology Radar

- Quarterly publication

- What technologies are worth adopting

- Link: thoughtworks.com/radar

- Time: 30 minutes per quarter

- ROI: Stay current on technology landscape

27. Martin Fowler's Blog (martinfowler.com)

- Architecture patterns

- Microservices, APIs, testing

- Browse topics: Architecture, Agile, Refactoring

- Time: Ongoing reference

- ROI: Free wisdom from industry thought leader

### Additional Resources

Online Resources:

Martin Fowler's Blog (martinfowler.com)

- Architecture patterns, microservices, refactoring

- Browse: Microservices, APIs, Architecture

ThoughtWorks Technology Radar (thoughtworks.com/radar)

- Quarterly publication on technology trends

- Adopt/Trial/Assess/Hold framework

- Good model for your own tech radar

State of DevOps Reports (dora.dev)

- Annual research on DevOps practices and performance

- Free benchmarking data

- Latest trends and capabilities

Team Topologies Resources (teamtopologies.com)

- Additional resources, workshops, case studies

- Team interaction patterns

- Community and discussions

Communities:

- DDD Community (Domain-Driven Design)

- Platform Engineering Community

- Data Engineering groups on LinkedIn

- Local CTO/IT leadership forums

Conferences (send your architects when hired):

- QCon - Software architecture and development

- Data+AI Summit - Databricks conference (if using)

- AWS re:Invent / Azure Ignite / Google Next - Cloud platforms

- Gartner IT Symposium - Strategic IT leadership

Certifications (budget for these):

- TOGAF - Enterprise Architecture framework

- AWS/Azure/GCP Architect certifications

- CBAP - Business Analysis

- Scrum Product Owner / Product Management

- Cloud certifications for platform teams

### Your Reading Plan (First 6 Months)

Month 1: Foundation

- Week 1-2: "The Phoenix Project" (weekend reading)

- Week 3-4: "Team Topologies" Part 1

Month 2: Core Framework

- Week 1-2: "Team Topologies" Part 2

- Week 3-4: "Accelerate"

Month 3: Strategy & Depth

- Week 1-2: "Good Strategy Bad Strategy"

- Week 3-4: "Domain-Driven Design Distilled"

Month 4-5: Product & Change

- "Escaping the Build Trap"

- "Switch"

Month 6: Leadership

- "Turn the Ship Around!"

- "Project to Product"

Ongoing: Articles and updates

- Martin Fowler blog

- ThoughtWorks Tech Radar

- DORA reports

Reading Tactics:

- Early morning: 1 hour, 3 days/week = 12 hours/month = 1-2 books

- Audiobooks: Commute time (if applicable)

- Weekend: 2-3 hours Saturday morning

- Leadership book club: Read together, discuss monthly

Book Club with Your Team

Highly recommend:

- Choose 1 book per quarter for leadership team

- Q1: "Team Topologies"

- Q2: "Accelerate"

- Q3: "Escaping the Build Trap" (when hiring POs)

- Q4: "Good Strategy Bad Strategy"

Format:

- Everyone reads the book (4-6 weeks)

- 90-minute discussion session

- Facilitated discussion questions

- Action items: "What do we apply?"

Benefits:

- Shared vocabulary ("stream-aligned team" means same thing to everyone)

- Aligned understanding

- Builds leadership team cohesion

- Accountability (people actually read)

What NOT to Read (Save Your Time)

Books I considered but don't recommend for you right now:

❌ "The Mythical Man-Month" by Fred Brooks

- Classic but dated (1975)

- Concepts are now mainstream

- Historical interest only

❌ "Clean Code" / "Clean Architecture" by Robert Martin

- Too technical for CTO level

- Your architects should read these

- Not strategic enough for your role

❌ "Scrum Guide" / Most Agile certification books

- Too process-focused

- Scrum Masters should read these

- You need strategic view, not ceremony details

❌ "The Goal" by Eliyahu Goldratt

- Theory of Constraints classic

- Concepts covered better in Phoenix Project

- Manufacturing context, harder to apply

❌ Most vendor-specific books (Salesforce architecture, AWS patterns, etc.)

- Your architects and developers should read these

- Too detailed for your strategic role

Online Courses & Resources (Beyond Books)

Video Learning

1. LinkedIn Learning / Pluralsight

- "DevOps Foundations" course

- "Product Management Fundamentals"

- Time: 2-4 hours per course

- When: Complement book reading

2. YouTube Channels

- GOTO Conferences: Software architecture talks (free)

- InfoQ: Software engineering trends

- 15-30 min videos: Good for quick learning

Podcasts (During Commute)

3. Software Engineering Radio

- Technical deep dives

- Architecture, DevOps, platforms

4. CTO Connection

- CTO interviews and experiences

- War stories and lessons learned

5. The Changelog

- Open source and software development

- Industry trends

Conferences (Once/Year)

6. QCon (Software Architecture)

- Two locations: London, San Francisco

- Excellent speakers, cutting edge

- ROI: High for architecture strategy

7. DevOps Enterprise Summit

- Large enterprise transformations

- Case studies from companies like you

ROI: High for transformation insights

My Top 5 If You Only Read Five

If I could only recommend 5 books for your transformation:

- "Team Topologies" - The blueprint

- "The Phoenix Project" - The motivation and context

- "Accelerate" - The metrics and evidence

- "Good Strategy Bad Strategy" - The strategic thinking

- "Switch" - The change management

Total time: ~30-35 hours Can complete in: 8-10 weeks with 3-4 hours/week

Result: You'll be better equipped for your transformation than 95% of CIOs.

Reading vs. Doing

Critical mindset:

Books give you frameworks and ideas, but transformation happens through action.

Balance:

- 10% Reading and learning

- 20% Planning and designing

- 70% Executing and adapting

Don't fall into:

- Reading 10 books before starting (analysis paralysis)

- Reading but never applying (intellectual exercise)

- Thinking reading = transformation (doing ≠ reading about doing)

Do this instead:

- Read "Team Topologies" → Design your team structure → Launch pilot

- Read "Switch" → Apply framework to change initiative → Monitor results

- Read "Accelerate" → Baseline metrics → Improve metrics → Measure again

Every book should lead to action within 2 weeks of finishing.

### Final Recommendations

Month 1: Start Here

- Read "The Phoenix Project" this weekend (Saturday + Sunday, 3-4 hours each day)

- Start "Team Topologies" next week (3 hours/week for 3 weeks)

- Subscribe to ThoughtWorks Tech Radar and Martin Fowler's blog

- Set up 1-hour weekly reading block on your calendar

Month 2: Build Momentum

- Finish "Team Topologies" and take notes

- Read "Accelerate" (baseline your metrics while reading)

- Start leadership team book club with "Team Topologies"

Month 3: Apply Learning

- Read "Good Strategy Bad Strategy"

- Write your transformation strategy using frameworks learned

- Choose next book based on your specific challenge

Month 4+: Sustain

- One book per month (4-6 hours/week reading time)

- Monthly leadership team book club

- Quarterly conference or deep-dive course

- Weekly article/blog reading

You've got this!

The fact that you're asking for reading recommendations shows you're committed to learning and growing. That mindset will serve you well in this transformation.

One more thing: As you read, remember that these books are written about tech companies, startups, or idealized scenarios. Your context is different.

Take the principles and frameworks, but adapt them to your reality:

- Your industry

- Your company culture

- Your constraints

- Your opportunities

The best CIOs read widely, think critically, and apply selectively.

Good luck with your transformation! 🚀

## Your Personal Leadership Journey

As CTO leading this transformation, your role evolves too.

Current CTO Role (likely):

- Firefighting technical issues

- Approving technology purchases

- Managing team managers

- Dealing with escalations

- Protecting team from business pressure

Future CTO Role:

- Setting strategic direction

- Building organizational capability

- Developing leaders (architects, POs, managers)

- Partnering with business on initiatives

- Representing IT at executive level

- Measuring and communicating value

Your Leadership Focus Areas:

Months 1-6: Architect and Launch

- 60% - Transformation design and initiation

- 20% - Hiring key roles

- 10% - Communication and change management

- 10% - Keeping current operations running

Months 7-12: Guide and Support

- 40% - Supporting pilot teams and early adopters

- 30% - Building platform capabilities

- 20% - Hiring and developing leaders

- 10% - Managing up (executives, board)

Months 13-24: Scale and Optimize

- 40% - Strategy and portfolio management

- 30% - Developing leaders and organization

- 20% - Business partnership and value realization

- 10% - Industry engagement and innovation

Year 3+: Lead and Innovate

- 50% - Business strategy partnership

- 30% - Talent and culture

- 10% - Industry thought leadership

- 10% - Innovation and future capabilities

Personal Development:

- Delegate technical decisions: That's what architects are for

- Build your leadership team: Head of EA, Head of Data & AI, Head of Apps, Head of Vendor Mgmt

- Think business, not just IT: Speak in business outcomes, not technology features

- Tell the story: Constantly communicate vision and progress

- Develop political capital: You'll need executive support when things get hard

## Next steps for implementing

### Concrete Implementation Plan: First 90 Days

Let me give you a very specific plan for the first 3 months.

Week 1-2: Foundation & Assessment

Day 1-5:

- CTO announces transformation: All-hands meeting, share vision

- Form small transformation leadership team (Head of IT Apps, Ops Manager, 2 team leads)

- Begin documenting current state:

  - All systems inventory

  - All integrations (documented and undocumented)

  - All SaaS subscriptions

  - Current team structures and skills

Day 6-10:

- Skills inventory survey: Every IT person completes

  - Current skills (technologies, domains)

  - Desired skills (what they want to learn)

  - Career aspirations

  - Feedback on current model

- Begin system architecture mapping sessions

- Identify quick wins (duplicate SaaS tools, obvious consolidation opportunities)

Week 3-4: Initial Hiring & Planning

- Post job descriptions:

  - Enterprise Architect (priority 1)

  - 2 Solution Architects

  - Data Architect

  - 2 Integration Specialists

- Select external consulting partner (if using):

  - Architecture advisory

  - Change management support

- Conduct business stakeholder interviews:

  - What's working / not working with IT?

  - What are critical business initiatives?

  - What data/insights do they need?

- Finalize current state assessment:

  - System landscape documented

  - Technical debt quantified

  - Integration complexity mapped

  - Skills gaps identified

Month 2: Architecture Foundation

Weeks 5-6:

- Hire Enterprise Architect (aggressive timeline - use recruiters)

- Form Architecture Review Board (initial members):

  - Head of IT Apps (chairs temporarily)

  - 2 senior developers

  - Ops Manager

  - External consultant (if engaged)

- First architecture initiatives:

  - Define initial architecture principles

  - Create system landscape diagram

  - Document current integration patterns

  - Identify highest-priority integration pain points

Weeks 7-8:

- Enterprise Architect starts (hopefully!)

- Architecture practice kickoff:

  - EA takes over ARB chair

  - EA conducts detailed architecture assessment

  - Define architecture vision and roadmap

  - Prioritize architecture initiatives

- Begin vendor inventory:

  - All SaaS vendors documented

  - Contract terms captured

  - Usage and costs analyzed

  - Initial consolidation opportunities identified

Month 3: Platform Selection & Pilot Planning

Weeks 9-10:

- Platform evaluation begins:

  - Integration Platform: shortlist 3 vendors, request demos

  - Data Platform: shortlist 3 vendors, request demos

  - Involve key technical staff in evaluation

  - Define evaluation criteria with ARB

- Solution Architects and Data Architect hiring:

  - Interviews and offers

  - Target start dates in Month 4

- Pilot team selection:

  - Choose 1-2 domains for stream-aligned team pilot

  - Criteria: clear boundaries, motivated team lead, business sponsorship

  - Announce pilot teams and explain goals

- Communication cadence established:

  - Weekly transformation update email

  - Monthly all-hands

  - Transformation hub on intranet launched

Weeks 11-12:

- Platform decisions:

  - Integration Platform selected (ARB decision)

  - Data Platform selected (ARB decision)

  - Begin procurement process

  - Plan POC/pilot implementations

- First Business Analysts hired:

  - Post job descriptions

  - Can hire from internal functional analysts who show interest

  - Target 2 BAs by end of Month 4

- Pilot team design:

  - Work with Enterprise Architect to define pilot team structure

  - Identify Product Owner for pilot (likely from business)

  - Define team boundaries and interfaces

  - Plan pilot timeline (3-6 months)

Quick Wins Delivered by Day 90:

- ✅ Architecture practice established with ARB meeting regularly

- ✅ Enterprise Architect hired and active

- ✅ Current state fully documented

- ✅ Integration and data platforms selected

- ✅ 2-3 duplicate SaaS tools consolidated

- ✅ Pilot team(s) identified and designed

- ✅ Hiring pipeline for key roles filled

- ✅ Communication and change management active

### Months 4-6: Platform Deployment & Pilot Launch

Month 4:

- Integration Platform deployment begins

- Data Platform deployment begins

- Solution Architects start

- Integration Specialists start

- Business Analysts start

- Pilot teams formally launch

- Head of Vendor Management hired

Key Activities:

- Platform setup:

  - Integration Platform: environment setup, first connectors

  - Data Platform: infrastructure setup, first data sources

  - DevOps: CI/CD pipelines for pilot teams

- Pilot team onboarding:

  - Team training on new ways of working

  - Product Owner and BA embedded

  - Solution Architect assigned (20-40% time)

  - First sprint planning using new model

- Architecture patterns:

  - API standards published

  - Integration patterns documented

  - Data modeling standards defined

  - Reference architectures for common scenarios

Month 5:

- First integrations on new platform

- Data warehouse receiving first data feeds

- Pilot teams delivering working software

- Vendor management processes defined

- Data Governance Board formed (initial meeting)

Key Activities:

- Platform adoption:

  - Migrate 2-3 existing integrations to new platform

  - Load historical data into data warehouse

  - Create first reusable integration connectors

  - Platform team established (from Ops + new hires)

- Pilot team showcase:

  - Pilot teams demo progress

  - Share learning with rest of organization

  - Gather feedback and adjust

- Vendor management:

  - Complete vendor inventory

  - Conduct security reviews for top 10 vendors

  - Initiate contract consolidation opportunities

  - Establish vendor tiering and review schedule

Month 6:

- Platform maturity increasing

- Pilot teams demonstrating value

- Data quality work begins

- Additional hiring continuing (Data Engineers, more BAs)

Key Activities:

- Mid-transformation review:

  - Assess pilot team success

  - Adjust model based on learnings

  - Plan rollout to additional teams

  - Celebrate wins and address concerns

- Data foundation:

  - Data catalog implementation begins

  - Data quality monitoring tools deployed

  - First "golden records" created (e.g., customer master)

  - Data governance policies published

- Architecture maturity:

  - Architecture Decision Records (ADRs) process working

  - Technology radar published

  - Multiple solution designs reviewed and approved

  - Team culture shifting (architects seen as enablers)

Deliverables by Month 6:

- ✅ Integration platform operational with 5+ integrations

- ✅ Data warehouse receiving data from 3+ sources

- ✅ Pilot team(s) delivering value in new model

- ✅ Architecture practice mature and respected

- ✅ 10+ new roles hired and onboarded

- ✅ Vendor management processes active

- ✅ Measurable quick wins (faster delivery, business satisfaction up)

### Months 7-12: Scale & Data Maturity

Month 7-9: Expand Stream-Aligned Teams

- Roll out stream-aligned model to 2-3 more domains

- Platform teams fully formed and operational

- Data engineering team built out

- Integration platform handling 15-20 integrations

- Data warehouse expanded to 5-7 major data sources

Month 10-12: Data & Analytics Value

- Data catalog comprehensive

- Data quality at 90%+ for tier 1 data

- Self-service analytics launched

- First analytics use cases delivering value

- Begin AI/ML planning (assessment, use case prioritization)

### Measuring Progress: 90-Day Checkpoints

End of Month 3:

- ✅ Enterprise Architect hired? (critical)

- ✅ Platforms selected? (integration + data)

- ✅ Pilot teams identified?

- ✅ Current state documented?

- ✅ €50K+ in quick wins identified?

- ✅ Team morale stable or improving?

If 4+ boxes checked: On track ✓ If 3 boxes: At risk - investigate delays If <3 boxes: Red alert - major intervention needed

End of Month 6:

- ✅ Solution Architects hired? (2+)

- ✅ Integration platform operational? (5+ integrations)

- ✅ Data platform receiving data? (3+ sources)

- ✅ Pilot teams launched and delivering?

- ✅ Platform teams formed?

- ✅ Quick wins delivered and communicated?

If 5+ boxes: On track ✓ If 3-4 boxes: At risk If <3 boxes: Red alert

End of Month 12:

- ✅ 50%+ teams in stream-aligned model?

- ✅ Integration platform mainstream? (15+ integrations)

- ✅ Data quality >90% for tier 1 data?

- ✅ Business satisfaction improving?

- ✅ Lead time reduced by 30%+?

- ✅ No critical staff attrition?

If 5+ boxes: On track ✓ If 3-4 boxes: At risk If <3 boxes: Red alert

### What Success Looks Like (24 Months Out)

Let me paint a picture of what "good" looks like:

A Day in the Life of a Stream-Aligned Team:

9:00 AM - Daily Standup

- Product Owner shares: "Finance just approved the invoice automation project - it's top priority"

- Developers update on API integration progress

- BA mentions workshop with Finance this afternoon to refine requirements

- Solution Architect (20% allocated) notes: "Use the new invoice processing pattern from the integration platform"

- Team adjusts sprint plan

10:00 AM - Development

- Developer pulls pre-built Salesforce connector from integration platform

- Configures it using template (no custom code needed)

- Deploys via CI/CD pipeline (5 minutes)

- Integration is live and monitored

2:00 PM - BA Workshop with Finance

- BA runs workshop with Finance stakeholders

- Uses Miro board to map current invoice process

- Identifies pain points and opportunities

- Documents requirements in user stories

- Finance team feels heard and engaged

3:30 PM - Architecture Review

- Solution Architect reviews team's design for new feature

- Suggests using event-driven pattern instead of polling

- Points to reference architecture

- Decision documented in ADR

- 30-minute session, not a 2-week approval process

4:30 PM - Deployment

- Team deploys latest changes to production

- Automated tests pass

- Monitoring dashboards show everything healthy

- Feature flag enables for 10% of users initially

- No big deployment weekend needed

End of Day

- Team delivered value

- No blockers waiting for other teams

- Clear progress toward business goals

- Everyone knows what's next

What's Different from Today:

- Clear business focus (invoices) not just "work on the ERP"

- Self-service integration (platform provides connector)

- Fast deployment (minutes, not days)

- Business engagement (BA workshop)

- Architecture guidance without bureaucracy

- Team autonomy and ownership

A Day in the Life of the Data Platform Team:

9:00 AM - Team Sync

- Review platform health dashboard: all green

- New request from Sales team: need customer purchase history API

- Prioritize: can deliver in 2 days using existing patterns

10:00 AM - Building Data Product

- Data Engineer creates new data mart for Sales

- Uses existing customer and order data from warehouse

- Applies business logic (calculate LTV, purchase patterns)

- Creates API endpoint for easy access

- Documents in data catalog

1:00 PM - Office Hours

- Order-to-Cash team drops in: "How do we add shipping cost data?"

- 30-minute pairing session

- Team learns how to extend their domain data

- They can do it themselves next time

3:00 PM - Data Quality Review

- Weekly automated quality report reviewed

- One data source showing anomalies (order totals don't match)

- Root cause: currency conversion issue in source system

- Alert sent to owner (Order-to-Cash team)

- Track until resolved

4:00 PM - New Data Source Onboarding

- E-commerce team launching new website

- Data Engineer sets up pipeline: E-commerce DB → Data Warehouse

- Uses template (1 hour vs 1 week previously)

- Monitors initial data flow

- Adds to data catalog

What's Different:

- Requests fulfilled quickly (days not weeks)

- Self-service where possible (office hours enable teams)

- Proactive quality monitoring

- Reusable patterns and templates

- Clear service catalog

A Day in Architecture Review Board:

2:00 PM - Bi-weekly ARB Meeting

Case 1: New Project Management Tool

- Marketing team wants to buy Monday.com

- Vendor Manager presents: assessment completed, contract negotiated

- Enterprise Architect asks: "Don't we have Jira?"

- Discussion: Marketing needs different capabilities

- Decision: Approved, but limit to Marketing only, review in 6 months

Case 2: Customer Portal Redesign

- Customer Experience team presents design

- Solution Architect reviewed it already (detailed discussion happened earlier)

- ARB reviews high-level: authentication approach, API usage, data access

- Questions on scalability addressed

- Decision: Approved with recommendation to add caching layer

Case 3: AI Use Case - Lead Scoring

- Data Scientist presents ML model for lead scoring

- Data quality: ✓ (CRM data at 95% quality)

- Business process: ✓ (Sales will act on scores)

- Ethics review: ✓ (no bias concerns)

- Decision: Approved for pilot with 10% of leads

Meeting Done in 90 Minutes

- 3 significant decisions made

- Teams can proceed immediately

- Not a bottleneck, an enabler

What's Different:

- Decisions made quickly (not tabled for more analysis)

- Teams already did detailed work (ARB reviews, doesn't design)

- Mix of governance and enablement

- Business value considerations included

### Getting Started - Your First 30 Days Action Plan

Now that you have the complete blueprint, here's exactly what to do in your first 30 days to launch this transformation successfully.

Week 1: Foundation & Alignment (Days 1-5)

Day 1: Internal Alignment

Morning:

- [ ] Block 2 hours on your calendar

- [ ] Review this entire document

- [ ] Highlight sections most relevant to your context

- [ ] Note questions and concerns

Afternoon:

- [ ] Meet with your CFO (1 hour)

  - Share transformation vision

  - Discuss budget requirements (€3.5M Year 1)

  - Get preliminary buy-in

- [ ] Meet with CEO (30 minutes)

  - Brief on transformation need

  - Request support and sponsorship

  - Schedule deeper dive for Week 2

Evening:

- [ ] Draft transformation vision (1-page summary)

- [ ] Identify your transformation steering committee members

Day 2: Team Consultation

Morning:

- [ ] Meet with Head of IT Applications (1.5 hours)

  - Share transformation vision

  - Get their input and concerns

  - Discuss their role in future state

  - Request their support

Afternoon:

- [ ] Meet with Operations Manager (1 hour)

  - Similar discussion

  - Discuss platform team evolution

- [ ] Meet with 2-3 senior team leads (30 min each)

  - Pulse check on current challenges

  - Get their input on team structure ideas

Evening:

- [ ] Refine transformation vision based on feedback

- [ ] Start compiling current state data (systems, integrations)

Day 3: External Preparation

Morning:

- [ ] Contact executive recruiting firm

  - Brief them on Enterprise Architect role

  - Request proposals

  - Timeline: Hire within 45 days

- [ ] Research architecture consulting firms

  - For interim support and advisory

  - Request introductory calls

Afternoon:

- [ ] Start transformation business case

  - Use templates from Section 15

  - Gather current costs data

  - Estimate benefits

Evening:

- [ ] Draft Enterprise Architect job description

  - Use template from Section 5.2

  - Customize for your context

  - Review compensation market data

Day 4: Stakeholder Mapping

Morning:

- [ ] Create stakeholder map

  - List all key stakeholders (business VPs, IT team, executives)

  - Categorize by power/interest

  - Plan engagement strategy for each

Afternoon:

- [ ] Schedule 1:1s with business VPs

  - For Week 2-3

  - 30-45 minutes each

  - Goal: Understand their pain points and needs

Evening:

- [ ] Prepare communication plan

  - Channels, frequency, messaging

  - Draft initial announcement

Day 5: Planning & Preparation

Morning:

- [ ] Finalize transformation steering committee

  - Members identified

  - Send calendar invites for bi-weekly meetings (starting Week 2)

- [ ] Create transformation project plan (high-level)

  - Use roadmap from Section 12

  - Customize to your context

Afternoon:

- [ ] Prepare Week 2 activities:

  - Executive presentation deck

  - IT all-hands announcement

  - Initial assessment activities

- [ ] Set up transformation documentation space

  - Intranet hub or SharePoint

  - Start populating with vision, roadmap

Evening:

- [ ] Weekend reading: Start "The Phoenix Project"

  - Will help frame the transformation story

  - Engaging and motivational

Week 2: Launch & Assessment (Days 6-10)

Day 6: Executive Buy-In

Morning:

- [ ] Present to Executive Team (90 minutes)

  - Transformation vision and rationale

  - Business case (preliminary)

  - Investment required (€3.5M Year 1)

  - Timeline and milestones

  - Request: Approval to proceed

Afternoon:

- [ ] Incorporate executive feedback

- [ ] Confirm budget approval process and timeline

- [ ] Get CEO explicit sponsorship commitment

Evening:

- [ ] Prepare IT all-hands announcement

  - Deck with vision, why, what, how, timeline

  - Anticipate questions and concerns

  - Practice delivery

Day 7: IT Team Announcement

Morning:

- [ ] IT All-Hands Meeting (90 minutes)

  - Announce transformation

  - Share vision and rationale

  - Timeline and approach (pilots first)

  - What's in it for them (opportunities, growth)

  - Q&A (be open and honest)

  - Record for those who can't attend

Afternoon:

- [ ] Send follow-up email to all IT staff

  - Summary of announcement

  - Link to recording

  - Link to transformation hub (intranet)

  - How to provide feedback or ask questions

- [ ] Monitor reactions (informal conversations, Slack, etc.)

Evening:

- [ ] Reflect on reactions

  - Note concerns raised

  - Identify potential resistors and supporters

  - Plan how to address top concerns

Day 8: Current State Assessment Kickoff

Morning:

- [ ] Meet with IT leadership team (2 hours)

  - Form transformation steering committee formally

  - Assign workstreams:

    - Systems inventory → Operations Manager

    - Skills inventory → You + HR

    - Integration mapping → Senior developer + Ops

    - Vendor inventory → Ops Manager

  - Set deadline: Complete by end of Month 1

Afternoon:

- [ ] Launch skills inventory survey

  - Send to all IT staff

  - Questions: Current skills, desired skills, career aspirations, feedback

  - Use survey tool (Google Forms, SurveyMonkey, etc.)

  - Deadline: 1 week

Evening:

- [ ] Schedule business stakeholder interviews

  - 5-10 key business leaders

  - For Week 3-4

  - Questions prepared (pain points, needs, expectations)

Day 9: Recruiting Launch

Morning:

- [ ] Finalize EA job description

- [ ] Engage executive recruiter

  - Contract signed

  - JD provided

  - Target: First candidates in 2 weeks

  - Hire within 45 days

Afternoon:

- [ ] Post EA job on:

  - Company website

  - LinkedIn

  - Architecture job boards

  - Your network (LinkedIn post)

- [ ] Contact architecture consulting firm

  - For interim EA support if hire delays

  - Get proposal for 3-6 month engagement

Evening:

- [ ] Research platform vendors

  - Integration platforms: MuleSoft, Boomi, Azure Logic Apps

  - Data platforms: Snowflake, Databricks, Azure Synapse

  - Create vendor contact list

  - Plan to request demos in Month 2

Day 10: Communication Infrastructure

Morning:

- [ ] Set up transformation communication channels

  - Slack/Teams: #transformation channel

  - Email: transformation-updates@company.com

  - Intranet: Transformation hub (expand content)

Afternoon:

- [ ] Populate transformation hub with:

  - Vision and strategy

  - Roadmap (high-level)

  - FAQ (anticipated questions)

  - How to provide feedback

  - What's happening now (assessment phase)

  - Weekly updates section

Evening:

- [ ] Draft first weekly transformation email

  - What happened this week (announcement, assessment started)

  - What's coming next week (interviews, assessment continues)

  - How to get involved or provide feedback

  - Send Friday end of day

Week 3: Deep Dive & Planning (Days 11-15)

Day 11-13: Business Stakeholder Interviews

Each Day: 2-3 interviews (45-60 min each)

Interview Questions:

- What are your current pain points with IT?

- What's working well?

- What business initiatives need IT support in next 12 months?

- What data or insights would help you make better decisions?

- If IT could deliver one thing faster, what would it be?

- How would you rate IT responsiveness and partnership? (1-5)

- What does great IT partnership look like to you?

After Each Interview:

- [ ] Document themes and quotes

- [ ] Note potential Product Owner candidates

- [ ] Identify potential pilot domains

Evening (Day 13):

- [ ] Synthesize interview findings

  - Common themes

  - Top pain points

  - Priority business needs

  - Potential pilot domains

  - Update business case with findings

Day 14: Assessment Review

Morning:

- [ ] Review current state assessment progress

  - Systems inventory: % complete?

  - Skills inventory: Response rate?

  - Integration mapping: How's it going?

  - Vendor inventory: Any surprises?

- [ ] Course-correct if needed

Afternoon:

- [ ] EA hiring pipeline check

  - Any candidates yet?

  - Timeline on track?

  - Adjust if needed (expand search, interim consultant)

- [ ] Close skills inventory survey if not already

- [ ] Begin analyzing results

Evening:

- [ ] Draft pilot team selection criteria

  - Based on interview findings

  - Clear boundaries?

  - Motivated team?

  - Business sponsorship?

  - Right complexity (not too hard, not too easy)?

Day 15: Pilot Planning

Morning:

- [ ] Identify 2-3 pilot team candidates

  - Example: Customer Experience, Order-to-Cash

  - Validate against criteria

  - Map current people to potential teams

Afternoon:

- [ ] Meet with potential pilot team leads

  - Gauge interest and readiness

  - Explain pilot approach (heavy support, learning)

  - Get their input on team composition

- [ ] Identify potential Product Owner candidates

  - From business stakeholder interviews

  - From current team (if suitable)

Evening:

- [ ] Continue reading: Start "Team Topologies"

  - Will inform pilot team design

  - Read chapters 1-3 this weekend

Week 4: Finalization & Next Steps (Days 16-22)

Day 16: Business Case Finalization

Morning:

- [ ] Complete business case

  - Use template from Section 15

  - Include:

    - Current state costs and challenges

    - Future state vision

    - Investment required (detailed)

    - Expected benefits and ROI

    - Risk analysis

    - Phased approach

  - Get CFO to review

Afternoon:

- [ ] Finalize transformation roadmap

  - 24-month high-level

  - 6-month detailed

  - Key milestones

  - Resource needs

  - Dependencies

Evening:

- [ ] Prepare final executive approval presentation

  - For Day 18-19

  - Business case

  - Roadmap

  - Request: Formal approval and funding

Day 17: Pilot Design

Morning:

- [ ] Design pilot team structure

  - Pilot #1: [Domain name]

    - Product Owner: [Candidate identified]

    - Business Analyst: [From current FAs]

    - Developers: [Names]

    - Testers: [Names]

    - Solution Architect: [To be hired, interim support]

  - Pilot #2: [If doing 2 pilots]

Afternoon:

- [ ] Create pilot team charter draft

  - Use template from Appendix B

  - Scope, out of scope

  - Success criteria

  - Support plan (coaching, resources)

- [ ] Meet with pilot Product Owner candidates

  - Explain role

  - Gauge interest

  - Offer opportunity

Evening:

- [ ] Platform vendor research

  - Schedule demos for Month 2

  - 3 vendors each (integration platform, data platform)

  - Prepare evaluation criteria

Day 18-19: Executive Approval

Morning (Day 18):

- [ ] Present to Executive Team (Final Approval)

  - Complete business case

  - Roadmap and approach

  - Investment request

  - Expected outcomes

  - Risk mitigation

  - Q&A

Afternoon (Day 18):

- [ ] Receive feedback and questions

- [ ] Adjust if needed

- [ ] Confirm approval to proceed (hopefully!)

- [ ] Confirm budget allocation

Day 19:

- [ ] If approved: Celebrate internally with IT leadership! 🎉

- [ ] Begin detailed Month 2 planning

- [ ] Update transformation hub with approval and next steps

Day 20: Communication Blitz

Morning:

- [ ] Announce approval to IT staff

  - All-hands email

  - Town hall meeting (if appropriate)

  - We're going forward, here's what happens next

  - Celebrate this milestone

Afternoon:

- [ ] Announce to business stakeholders

  - Email to stakeholders interviewed

  - Thank them for input

  - Share how their input shaped plans

  - What they can expect

Evening:

- [ ] Post Month 1 transformation update

  - Intranet hub

  - What we accomplished

  - What we learned

  - What's coming in Month 2

Day 21-22: Month 2 Setup

Day 21 Morning:

- [ ] Finalize EA hiring

  - Review candidates in pipeline

  - Schedule interviews if candidates ready

  - Accelerate if needed

Day 21 Afternoon:

- [ ] Schedule Month 2 activities:

  - Platform vendor demos (6-8 demos over 2 weeks)

  - ARB kickoff meeting (once EA hired or interim in place)

  - Pilot team kickoff (end of Month 2 target)

Day 22 Morning:

- [ ] Review assessment findings

  - Systems inventory complete?

  - Skills inventory analyzed?

  - Integration map done?

  - Vendor inventory complete?

  - Create summary document

Day 22 Afternoon:

- [ ] Transformation steering committee meeting

  - Review Month 1 accomplishments

  - Review assessment findings

  - Approve pilot teams

  - Approve Month 2-3 plan

  - Assign Month 2 responsibilities

Evening:

- [ ] Reflect on Month 1

  - What went well?

  - What was harder than expected?

  - What to adjust in Month 2?

  - Celebrate progress

Days 23-30: Momentum Building

Remainder of Month 1:

- [ ] EA hiring: Interviews and offer (if candidates ready)

- [ ] Assessment: Finalize all workstreams

- [ ] Planning: Detailed Month 2-3 plans

- [ ] Communication: Weekly updates continue

- [ ] Platform vendors: Confirm demo schedule

- [ ] Pilot teams: Continue planning and preparation

- [ ] Reading: Finish "Team Topologies" Part 1

End of Month 1 Checklist:

- ✅ Transformation announced and approved

- ✅ Budget secured (€3.5M Year 1)

- ✅ Current state assessment complete

- ✅ Pilot teams identified

- ✅ EA hiring in progress (candidates in pipeline)

- ✅ Platform vendor demos scheduled

- ✅ Transformation steering committee operational

- ✅ Communication channels established

- ✅ Momentum and excitement building

Month 2 Preview: What's Coming

Focus: Architecture Foundation & Platform Selection

Key Activities:

- EA hire completes and onboards

- Architecture Review Board forms

- Platform vendor evaluation and selection

- Initial architecture principles defined

- Solution Architect hiring begins

- Pilot team detailed design

- Current state documentation completed

Key Hires:

- Enterprise Architect (Month 1-2)

- Post jobs for: Solution Architects (2), Data Architect, Integration Specialists (2)

Key Decisions:

- Integration platform selected

- Data platform selected

- Pilot teams formally approved

Your Month 1 Success Metrics

By end of Month 1, you should have:

Organizational:

- ✅ Executive approval and commitment

- ✅ €3.5M Year 1 budget secured

- ✅ Transformation steering committee operational

- ✅ Communication infrastructure established

Planning:

- ✅ Current state assessment complete

- ✅ Business case approved

- ✅ 24-month roadmap defined

- ✅ Pilot teams identified and designed

Hiring:

- ✅ EA hiring in active progress (candidates in pipeline)

- ✅ Job descriptions drafted for next roles

- ✅ Recruiting partnerships established

Momentum:

- ✅ IT team aware and generally supportive

- ✅ Business stakeholders engaged

- ✅ Quick win opportunities identified

- ✅ Energy and excitement present

Personal:

- ✅ Read "The Phoenix Project"

- ✅ Started "Team Topologies"

- ✅ Transformation hub launched

- ✅ Weekly communication established

If you achieve 80%+ of these by end of Month 1, you're on track for successful transformation.

Critical Success Factors for First 30 Days

DO:

- ✅ Move fast but not recklessly

- ✅ Communicate constantly (over-communicate)

- ✅ Listen to concerns and incorporate feedback

- ✅ Celebrate small wins

- ✅ Be transparent about challenges

- ✅ Get executive sponsorship locked in

- ✅ Secure budget early

- ✅ Start EA hiring immediately

- ✅ Build momentum and excitement

DON'T:

- ❌ Announce without executive buy-in

- ❌ Promise specific timelines without assessment

- ❌ Skip current state assessment

- ❌ Reorganize teams immediately

- ❌ Underestimate change management effort

- ❌ Delay EA hiring

- ❌ Make technology decisions before EA hired

- ❌ Forget to celebrate and recognize

Red Flags in First 30 Days

Watch for these warning signs:

🚩 Executive Team Lukewarm - If executives aren't enthusiastic, pause and build stronger case

🚩 IT Team Highly Resistant - More than 30% negative reaction requires addressing concerns before proceeding

🚩 Can't Find EA Candidates - Expand search geographically, increase compensation, engage interim consultant

🚩 Business Stakeholders Skeptical - Need to build business case stronger, show industry examples

🚩 Budget Uncertainty - Don't proceed without budget commitment, transformation will fail

🚩 You're Overwhelmed - Delegate more, get external help sooner

If you see 2+ red flags, pause and address before proceeding to Month 2.

Your Support System

You don't have to do this alone:

Internal:

- CFO (business case, funding)

- CEO (sponsorship, executive team alignment)

- Head of IT Applications (execution partner)

- HR (hiring, change management)

- Business VPs (Product Owners, business case)

External:

- Executive recruiter (EA hiring)

- Architecture consultant (interim EA, advisory)

- Change management consultant (if needed)

- Peers in industry (CTO network, LinkedIn)

Resources:

- This document (your blueprint)

- "Team Topologies" book (your team design guide)

- "The Phoenix Project" (your motivation)

- Industry analyst reports (Gartner, Forrester)

- Vendor resources (architecture patterns, case studies)

Community:

- CTO forums and groups

- LinkedIn IT Leadership groups

- Conferences (later months)

- Local CTO meetups

Personal Mindset for Success

As CTO leading this transformation:

Remember:

- This is a marathon, not a sprint (24 months)

- Perfection isn't required, progress is

- You'll make mistakes, learn from them

- Communication is never enough

- People before technology

- Celebrate small wins frequently

- Take care of yourself (this is intense)

Your Role:

- Vision: Keep the big picture clear

- Sponsorship: Champion and protect the transformation

- Decision-making: Make calls when needed

- Communication: Constant, transparent, bi-directional

- Coaching: Develop your leaders

- Patience: With yourself and others

What Success Looks Like for You:

- Year 1: "We've built solid foundation, momentum is building"

- Year 2: "New model is working, delivering value"

- Year 3: "This is how we work now, continuous improvement"

- Year 5: "We're a strategic partner driving business outcomes"

Final Words of Encouragement

You're about to embark on one of the most important and impactful initiatives in your career as CTO. This transformation will:

- Modernize your IT organization

- Enable your business to move faster

- Attract top talent

- Drive business outcomes with technology

- Position your company competitively

It won't always be easy. You'll face:

- Budget pressures

- Resistance to change

- Technical challenges

- People challenges

- Unexpected obstacles

But you can do this.

Thousands of organizations have successfully made this journey. You have:

- A comprehensive blueprint (this document)

- A clear roadmap (24 months, phased)

- Proven patterns (Team Topologies, etc.)

- Strong business case (170% ROI)

- The right mindset (reading this document shows commitment)

Start small. Prove value. Scale gradually. Keep learning.

In 24 months, you'll look back and be amazed at what you've built. Your teams will be happier, your business stakeholders will be thrilled, and you'll have transformed IT from a cost center to a strategic partner.

Now go make it happen! 🚀

Quick Reference: Key Documents to Create First

Week 1:

- Transformation Vision (1-pager)

- Stakeholder Map

- Communication Plan

Week 2: 4. EA Job Description 5. IT All-Hands Presentation 6. Assessment Workstreams Assignment

Week 3: 7. Business Stakeholder Interview Questions 8. Pilot Team Selection Criteria 9. Interview Findings Summary

Week 4: 10. Business Case (full) 11. Transformation Roadmap (24-month) 12. Pilot Team Charter (draft) 13. Executive Approval Presentation 14. Month 1 Wrap-Up / Month 2 Plan

All templates provided in this document. Customize to your context.

Checklist - Complete First 30 Days

Print this and check off as you go:

Week 1: Foundation

- [ ] Day 1: CFO and CEO alignment

- [ ] Day 2: IT leadership consultation

- [ ] Day 3: Recruiter engaged, consulting firms contacted

- [ ] Day 4: Stakeholder map created

- [ ] Day 5: Steering committee formed, planning complete

Week 2: Launch

- [ ] Day 6: Executive approval to proceed

- [ ] Day 7: IT all-hands announcement

- [ ] Day 8: Assessment kickoff, skills survey launched

- [ ] Day 9: EA job posted, recruiting active

- [ ] Day 10: Communication infrastructure established

Week 3: Deep Dive

- [ ] Day 11-13: Business stakeholder interviews (5-10 people)

- [ ] Day 14: Assessment progress review

- [ ] Day 15: Pilot teams identified

Week 4: Finalization

- [ ] Day 16: Business case finalized

- [ ] Day 17: Pilot design complete

- [ ] Day 18-19: Executive final approval and budget

- [ ] Day 20: Approval announced

- [ ] Day 21-22: Month 2 setup, steering committee meeting

By End of Month 1:

- [ ] Assessment complete

- [ ] Budget approved

- [ ] EA hiring in progress

- [ ] Pilots designed

- [ ] Communication established

- [ ] Momentum building

Reading:

- [ ] "The Phoenix Project" (finished)

- [ ] "Team Topologies" (Part 1 complete)

## THE END - You Have Everything You Need

This document contains:

- ✅ Complete organizational design (stream-aligned teams, platforms, architecture)

- ✅ Detailed job descriptions (every role in future state)

- ✅ 24-month roadmap (month-by-month plan)

- ✅ Budget and business case (€11M investment, €23M return)

- ✅ Change management strategy (communication, training, resistance handling)

- ✅ Risk management (top 10 risks with mitigations)

- ✅ Success metrics (how to measure progress)

- ✅ Templates and tools (ADRs, charters, communication)

- ✅ Reading list (books and resources)

- ✅ First 30 days action plan (exactly what to do)

You are ready to begin.

Go transform your IT organization and enable your business to thrive! 🎯

Document Version: 1.0
Date: October 2025
For: IT Transformation - Development to Orchestration Model

This document is a living guide. Adapt it to your context. Share it with your team. Use it as your transformation blueprint.

Questions? Stuck? Need help?

- Revisit relevant sections

- Consult with your steering committee

- Engage external advisors

- Trust the process

- Keep moving forward

You've got this. 💪

🎯 START HERE → DAY 1, MORNING, FIRST TASK:

Block 2 hours on your calendar right now. Read this document completely. Then schedule your first meeting: CFO, this week, 1 hour, "IT Transformation - Budget Discussion".

The journey of a thousand miles begins with a single step. Take that step today.

END OF DOCUMENT

# Customized IT Transformation Blueprint for Your Organization (IT Applications – IT Systems – BPM)

Based on your current structure, let me create a tailored transformation plan that respects your existing setup while evolving it toward the target state.

## Your Current State Analysis

### Current Structure

CEO

├── Head of IT Applications

│   ├── Operations Manager

│   │   ├── Development Teams (app-focused)

│   │   ├── Integration Development Team

│   │   └── Support Team

│   └── Head of Data (building team)

│

├── Head of IT Systems

│   ├── Infrastructure

│   ├── Hardware & Networks

│   ├── Security

│   └── Systems Support

│

└── BPM Department

├── Project/Change Intake

├── Prioritization

├── Business Analysis (high-level)

└── Project Management

### What's Working Well

- ✅ Clear separation: Applications vs. Infrastructure

- ✅ BPM function exists: Already doing intake and prioritization

- ✅ Data leadership: Head of Data already in place

- ✅ Integration team: Already have specialized integration capability

- ✅ Business alignment: BPM connects business and IT

### Current Challenges

- Silos: BPM, IT Applications, IT Systems all separate → coordination overhead

- Reporting to CEO: IT strategy fragmented, no unified CTO vision

- Application-centric teams: Not business-domain aligned

- Missing capabilities: Architecture, Product Owners, mature data/AI

- Support burden: Support teams in IT Applications → capacity drain

## Recommended Future State Structure

### Phase 1: Immediate Structure (Months 0-6)

Recommendation: Merge BPM + IT Applications, create unified IT leadership

CEO

├── CTO/CIO (NEW or promote Head of IT Applications)

│   │

│   ├── Head of Business Solutions (evolved from BPM + IT Applications)

│   │   ├── Portfolio & Demand Management (from BPM)

│   │   ├── Stream-Aligned Teams (6-7 teams)

│   │   ├── Head of Data & AI (existing)

│   │   └── Business Analysis Center of Excellence (from BPM)

│   │

│   ├── Head of Enterprise Architecture (NEW)

│   │   ├── Enterprise Architect (NEW)

│   │   ├── Solution Architects (NEW, 3-4)

│   │   └── Data Architect (NEW)

│   │

│   └── Head of Platform Engineering (evolved from current structure)

│       ├── Integration Platform Team (from existing integration team)

│       ├── Application Support (from IT Applications)

│       └── Coordinates with IT Systems on infrastructure

│

└── Head of IT Systems (STAYS SEPARATE - Reports to CEO)

├── Infrastructure & Cloud

├── Networks

├── Security (elevated importance)

├── Hardware

└── Systems Support

Rationale for keeping IT Systems separate:

- Infrastructure and security are foundational, enterprise-wide

- Different skillset and mindset (stability vs. agility)

- CEO maintains direct oversight of critical infrastructure and security

- BUT: Strong partnership and coordination mechanisms needed

### Why This Structure for Your Context

Alignment with Your Values:

✅ Flexibility: Stream-aligned teams can pivot quickly to business needs
✅ Entrepreneurship: Product Owners empowered to make decisions, teams own outcomes
✅ Agility: Small cross-functional teams, continuous delivery
✅ Lean: Eliminate handoffs, reduce waste, focus on value
✅ Robustness: Architecture practice ensures sound decisions, security embedded

## Mapping Your 3 Business Units to Stream-Aligned Teams

Your Business Structure (as I understand):

- 3 main operational business units (let's call them BU1, BU2, BU3)

- Supporting departments: Sales, Finance, HR, Legal, Claims

### Recommended Stream-Aligned Team Structure

Option A: Business Unit Aligned (If BUs are distinct)

Stream-Aligned Teams (6-7 teams):

1. Business Unit 1 Technology Team

- PO from BU1

- Owns: All applications and technology for BU1

- Systems: BU1-specific apps, integrations, data

2. Business Unit 2 Technology Team

- PO from BU2

- Owns: All applications and technology for BU2

- Systems: BU2-specific apps, integrations, data

3. Business Unit 3 Technology Team

- PO from BU3

- Owns: All applications and technology for BU3

- Systems: BU3-specific apps, integrations, data

4. Customer & Sales Technology Team

- PO from Sales

- Owns: CRM, sales tools, customer portal, e-commerce

- Systems: Salesforce/CRM, customer-facing apps

5. Finance & Claims Technology Team

- PO from Finance

- Owns: Financial systems, claims processing, reporting

- Systems: ERP/Finance modules, claims systems

6. HR & Internal Operations Team

- PO from HR/Operations

- Owns: HR systems, internal tools, collaboration

- Systems: HRIS, intranet, internal portals

7. Data & Analytics Platform Team

- Part of Head of Data & AI organization

- Serves all other teams with data capabilities

Option B: Functional Capability Aligned (If BUs share systems)

Stream-Aligned Teams:

1. Customer Experience & Sales Team

- Customer-facing technology

- CRM, portals, e-commerce

- Serves all BUs

2. Operations & Fulfillment Team

- Operational systems

- Order processing, inventory, logistics

- Serves all BUs

3. Finance, Billing & Claims Team

- Financial systems

- Billing, invoicing, claims processing

- Serves all BUs

4. Product & Pricing Team

- Product data, catalogs, pricing

- Configuration and rules

- Serves all BUs

5. Compliance & Reporting Team

- Regulatory reporting

- Legal/compliance systems

- Audit and controls

6. Employee & Internal Services Team

- HR, payroll, internal tools

- Employee experience

7. Data Platform Team (under Head of Data)

Which to Choose?:

- Option A if: BUs have very different systems, processes, customer types

- Option B if: BUs share most systems (common ERP, CRM, etc.)

- Hybrid: Most companies end up with a mix

Your Action: Map your actual systems and capabilities to determine which model fits best.

## Transition Plan: From Current to Future State

### Key Moves

1. Create CTO/CIO Role (Month 1)

Options:

- Option A: Promote current Head of IT Applications to CTO

  - Takes on enterprise IT strategy

  - Peer relationship with Head of IT Systems (both report to CEO initially)

  - Over 12-18 months, potentially Head of IT Systems reports to CTO

- Option B: Hire external CTO

  - Brings fresh perspective and transformation experience

  - Oversees both IT Applications and IT Systems eventually

  - Higher cost, but accelerates transformation

Recommendation: Option A (promote from within) given your values of entrepreneurship and internal development. External architecture expertise can come via architects and consultants.

2. Merge BPM into IT Applications (Months 1-3)

Current BPM Team Members:

| BPM Role | New Role | New Home |
| --- | --- | --- |
| Intake & Prioritization | Portfolio Analysts | Portfolio & Demand Management |
| High-level Business Analysts | Senior Business Analysts | BA Center of Excellence OR Stream Teams |
| Project Managers | Project Managers | Portfolio Management (pool) OR stream teams |

Transition Actions:

- BPM Manager → Head of Portfolio & Demand Management (new title, evolved role)

- Intake process stays but evolves (see below)

- BPM team doesn't disappear, it transforms and integrates

Benefits:

- ✅ End organizational silos

- ✅ BPM expertise embedded where work happens

- ✅ Faster decision-making (no handoffs between BPM and IT Apps)

- ✅ Product Owners and BAs work together seamlessly

3. Evolve Operations Manager Role (Months 1-6)

Current: Operations Manager → Teams (app-focused)

Future: Multiple reporting lines based on team type

Transition:

- Operations Manager evolves to Head of Delivery or Head of Business Solutions

- Stream-aligned teams report here

- Or: Stream teams report to Portfolio Management and Operations Manager becomes Head of Platform Engineering

Recommendation:

Head of Business Solutions (evolved Operations Manager)

├── Portfolio & Demand Management (from BPM)

├── 6-7 Stream-Aligned Teams

├── BA Center of Excellence (from BPM)

└── Coordinates with Platform Engineering

4. Create Architecture Practice (Months 1-3)

New: Head of Enterprise Architecture

This is NEW capability, not existing in current structure.

Hire Priority:

- Enterprise Architect (Month 1-2) - CRITICAL FIRST HIRE

- Solution Architects (Month 2-4) - 2 initially, grow to 3-4

- Data Architect (Month 3-4) - Partner with Head of Data

Where they sit:

- Report to CTO

- Peer to Head of Business Solutions

- Matrix to teams (Solution Architects embedded)

Why this is critical for you:

- Currently no one ensuring coherent architecture across BU1, BU2, BU3

- No one making strategic technology decisions (build vs. buy)

- Risk of each BU creating different solutions to same problems

- Integration complexity will explode without architecture

5. Elevate Security (Months 3-6)

Current: Security under Head of IT Systems

Future: Security Architect role created

Options:

Option A: Security Architect reports to Head of Enterprise Architecture

- Pro: Architecture and security tightly coupled

- Pro: Application security gets proper attention

- Con: IT Systems still owns infrastructure security

Option B: Split Security

- Infrastructure Security → stays with IT Systems

- Application/Data Security → Security Architect under EA

- Coordinate via Security Governance Board

Option C: Chief Information Security Officer (CISO)

- Reports to CEO (peer to CTO and Head of IT Systems)

- Owns all security (infrastructure + application)

- Security Architect supports CISO

Recommendation: Start with Option A (Security Architect under EA), evolve to Option C if security becomes more critical (regulatory, risk profile increases).

6. Handle Support Teams (Months 3-9)

Current Challenge: Support teams in IT Applications drain capacity from development

Options:

Option A: Support stays with stream teams (DevOps model)

- Teams support what they build ("You build it, you run it")

- Pro: Faster feedback, quality improvement

- Con: Takes capacity from new development (plan for this)

Option B: Dedicated Support Organization

- Create separate Application Support team (under Platform Engineering)

- Handles Tier 1-2 support

- Stream teams handle Tier 3 (complex issues)

- Pro: Frees stream teams for development

- Con: Potential disconnect between support and development

Option C: Hybrid

- Tier 1-2: Support team (under Platform Engineering)

- Tier 3 + Production issues: Stream teams (rotational on-call)

- Stream teams have SLAs for their domains

Recommendation: Option C (Hybrid)

- Move most support to Platform Engineering

- Stream teams maintain ownership and handle escalations

- Measure: Support should be <20% of stream team capacity

7. IT Systems Relationship (Ongoing)

Challenge: IT Systems stays separate but must coordinate closely

Coordination Mechanisms:

1. IT Leadership Team (Weekly):

- CTO (or Head of Business Solutions)

- Head of IT Systems

- Head of Enterprise Architecture

- Head of Data & AI

- Head of Portfolio Management

- Alignment on priorities, resources, dependencies

2. Architecture Review Board (Bi-weekly):

- Includes Head of IT Systems or delegate

- Infrastructure decisions (cloud, network, security)

- Application decisions that impact infrastructure

- Ensure alignment

3. Shared Services Agreement:

- IT Systems provides infrastructure "as a service" to Business Solutions

- SLAs defined (uptime, support response, provisioning time)

- Capacity planning coordinated

- Cost allocation transparent

4. Security Governance Board (Monthly):

- Head of IT Systems (or Security lead)

- Security Architect

- Compliance/Legal

- Ensures holistic security approach

5. Cross-functional Projects:

- Major initiatives (cloud migration, network upgrade, etc.) have representation from both organizations

- Joint steering committees

- Shared accountability

Potential Evolution:

- Year 1: Separate organizations, strong coordination

- Year 2-3: Evaluate if IT Systems should report to CTO

- Depends on: Business needs, leadership, strategic direction

## Your Customized Transformation Roadmap

### Month 1: Foundation & Structure

Week 1-2: Leadership Alignment

- [ ] CEO announces transformation and new structure

- [ ] Decide: Promote Head of IT Applications to CTO OR hire external

- [ ] Announce merge of BPM and IT Applications

- [ ] Form transformation steering committee:

  - CEO, CTO (new/promoted), Head of IT Systems, Head of Data, BPM Manager, CFO, 2 BU heads

Week 3-4: Structural Changes

- [ ] BPM moves into IT Applications organization

  - BPM Manager → Head of Portfolio & Demand Management

  - Project Managers → Project Management pool

  - Business Analysts → some to BA CoE, some to stream teams (TBD)

- [ ] Post Enterprise Architect job

  - Use executive recruiter

  - Target hire: 30-45 days

- [ ] Map current teams to future stream-aligned teams

  - Use your BU structure + functional capabilities

  - Identify 2-3 pilot teams

Deliverables:

- New org chart communicated

- EA hiring underway

- BPM integrated (people know new roles)

- Pilot teams identified

### Month 2-3: Architecture & Planning

Architecture Foundation:

- [ ] Enterprise Architect hired and onboarded

- [ ] Form Architecture Review Board

  - EA (chair), Head of Business Solutions, Head of IT Systems, Head of Data, 2 senior developers

- [ ] Define architecture principles

- [ ] Begin system landscape documentation

- [ ] Platform vendor evaluation (integration, data)

Portfolio Management Evolution:

- [ ] Current BPM intake process continues BUT

- [ ] Add stream-aligned team lens to prioritization

- [ ] Begin capacity modeling by team

- [ ] Pilot new intake categorization:

  - Domain-specific → Product Owner

  - Cross-domain → Portfolio Management

  - Strategic → Executive

Team Design:

- [ ] Design 2-3 pilot stream-aligned teams

  - Map current people to teams

  - Identify Product Owner candidates

  - Define boundaries and scope

- [ ] Begin Product Owner hiring/assignment

  - Ideal: Business people who step into PO role

  - Could promote from BPM business analysts

Deliverables:

- Architecture practice operational

- Platforms selected (integration, data)

- Pilot teams designed

- Portfolio management evolving

### Month 4-6: Pilot Launch

Pilot Teams Go Live:

- [ ] Launch 2 pilot stream-aligned teams

  - Example: BU1 Technology Team + Customer & Sales Team

  - Product Owners assigned

  - Business Analysts embedded

  - Developers/testers assigned

  - Solution Architect allocated (20-40% time)

- [ ] Heavy support for pilots

  - Weekly check-ins

  - Architecture support

  - Remove blockers aggressively

  - Celebrate early wins

Platform Deployment:

- [ ] Integration platform deployment begins

  - Move existing integration team to Integration Platform Team

  - Start building self-service capabilities

  - Migrate first 3-5 integrations to platform

- [ ] Data platform deployment begins

  - Head of Data leads

  - Initial data sources (3-5)

  - Data quality baseline

Support Transition:

- [ ] Begin transitioning support

  - Identify Tier 1-2 support that can move to Platform Engineering

  - Keep Tier 3 with stream teams

  - Pilot with one team, learn, adjust

Architecture Maturing:

- [ ] Solution Architects hired (2)

- [ ] Embedded with pilot teams

- [ ] First ADRs (Architecture Decision Records) created

- [ ] Technology radar published

Deliverables:

- 2 pilot teams delivering value

- Integration platform operational (initial)

- Data platform receiving data

- Support model piloted

- Architecture practice embedded

### Month 7-12: Expansion & Optimization

Scale Stream-Aligned Teams:

- [ ] Convert 3-4 more teams to stream-aligned model

- [ ] Based on pilot learnings

- [ ] All BUs now have dedicated teams

- [ ] Product Owners for each team (6-7 total)

Platform Teams Mature:

- [ ] Integration Platform Team: Self-service capabilities, 15+ integrations

- [ ] Data Platform Team: 5-7 data sources, data catalog, self-service analytics

- [ ] Application Support Team: Handling Tier 1-2 support effectively

Portfolio Management Fully Operational:

- [ ] Intake process smooth

- [ ] Capacity planning accurate

- [ ] Resource conflicts resolved systematically

- [ ] Quarterly portfolio reviews with executive team

Data & AI Progress:

- [ ] Head of Data team built out (4-6 people)

- [ ] Data quality at 90%+ for tier 1 data

- [ ] Analytics self-service launching

- [ ] First AI use case identified and scoped

IT Systems Coordination:

- [ ] IT Leadership Team meeting regularly

- [ ] ARB includes IT Systems representation

- [ ] Infrastructure-as-a-Service model working

- [ ] Joint projects coordinated well

Deliverables:

- 6-7 stream-aligned teams operational

- Platform teams mature and self-service

- Portfolio management effective

- Data foundation solid

- IT Systems and Business Solutions coordinating well

### Month 13-18: Maturation & AI

All Teams Transitioned:

- [ ] 100% of IT Applications in stream-aligned model

- [ ] Product Owners mature and effective

- [ ] Business stakeholder satisfaction improving

- [ ] Delivery metrics improving (lead time down 30-40%)

AI Capability Building:

- [ ] Data Scientists hired (2-3)

- [ ] ML Engineers hired (2)

- [ ] ML platform deployed

- [ ] First AI models in development

- [ ] AI use cases: Predictive analytics for each BU

Architecture Maturity:

- [ ] Security Architect hired

- [ ] Full architecture team (EA + 3-4 SAs + Data Arch + Security Arch)

- [ ] Reference architectures comprehensive

- [ ] Technical debt reducing

Vendor Management:

- [ ] If not already: Head of Vendor Management role created

- [ ] Vendor consolidation complete

- [ ] Strategic vendor partnerships

- [ ] Cost optimization realized

Deliverables:

- Transformation 75% complete

- AI capability operational

- Architecture mature

- Business value demonstrable

### Month 19-24: Optimization & Continuous Improvement

Fine-Tuning:

- [ ] Team boundaries adjusted based on 18 months experience

- [ ] Product Owner effectiveness high

- [ ] Platform teams innovating

- [ ] AI models in production (3-5)

Cultural Transformation:

- [ ] Business partnership model embedded

- [ ] Data-driven decision making normal

- [ ] Continuous improvement mindset

- [ ] Teams empowered and autonomous

Strategic Evolution:

- [ ] Evaluate: Should IT Systems report to CTO?

- [ ] Evaluate: Do we need CISO (separate security org)?

- [ ] Plan Year 3+ evolution

Deliverables:

- Transformation complete (90%)

- New operating model the "new normal"

- Business outcomes achieved

- Continuous improvement embedded

## Handling Your Specific Challenges

### Challenge 1: Three Business Units with Shared Systems

Scenario: BU1, BU2, BU3 all use same ERP, same CRM, same customer portal

Solution: Functional Stream Teams + BU Liaison Model

Structure:

Customer & Sales Team (owns CRM, portal)

├── Product Owner from Sales (cross-BU)

├── BU1 Liaison (BA from BU1)

├── BU2 Liaison (BA from BU2)

├── BU3 Liaison (BA from BU3)

└── Development team (builds for all BUs)

How it works:

- One team owns the system

- Each BU has a liaison (Business Analyst) who represents their needs

- Product Owner balances priorities across all three BUs

- Liaisons ensure BU-specific requirements are captured

Governance:

- Quarterly: All BU heads + PO review roadmap

- PO makes final prioritization decisions

- BU-specific customizations minimized (favor configuration)

### Challenge 2: Claims Department (Complex Domain)

Assumption: Claims is complex and critical

Recommendation: Dedicated Claims Technology Team

Structure:

Claims Technology Team

├── Product Owner (from Claims department)

├── Business Analyst (2 - Claims is complex)

├── Developers (4-5)

├── Testers (2 - quality critical for claims)

└── Solution Architect (40% - claims systems often complex)

Owns:

- Claims processing system

- Claims adjudication

- Claims reporting

- Fraud detection (if applicable)

- Integrations with external parties

Why dedicated team:

- Claims is business-critical

- Domain complexity requires focus

- Regulatory requirements

- Data sensitivity

### Challenge 3: Managing 200+ Change Request Backlog

Your Current BPM Process → Evolved Process:

Old (BPM-centric):

Request → BPM Intake → BPM Prioritization → BPM Assigns to IT Team → Development

New (Product Owner-centric):

Request → Portfolio Intake → Categorize → Route:

├── Domain-specific → Product Owner prioritizes → Team delivers

├── Cross-domain → Portfolio Management coordinates → Multiple teams

└── Strategic → Executive Portfolio → Decide

Transition Actions (Month 2-3):

Step 1: Categorize all 200+ requests

- BPM team (now Portfolio team) leads this

- Tag each request:

  - Domain: Which stream team?

  - Size: Small (<1 week), Medium (1-4 weeks), Large (1+ months)

  - Business value: Critical, High, Medium, Low

Step 2: Distribute to Product Owners

- Each PO receives their domain's requests

- PO re-prioritizes within domain

- PO decides: Yes/No/Defer/Need more info

Step 3: Communication Blitz

- Every requestor gets status update

  - "Your request assigned to [PO name], they will prioritize"

  - "Expected review by [date]"

- Set expectation: Transition period, be patient

Step 4: Product Owners Make Decisions (Month 3-6)

- Each PO works through their queue

- Accept ~30-40% (high value)

- Defer ~30-40% (to later quarters)

- Reject ~20-30% (low value, workarounds exist)

- Be transparent about decisions and rationale

Result: 200+ requests → ~80-100 in active backlog, rest deferred or rejected

### Challenge 4: Support Overhead Draining Development Capacity

Current Problem: Support teams in IT Applications consume development resources

Measurement (Month 1):

- Track: What % of developer time is support vs. new development?

- Likely finding: 40-50% on support (too high)

Target: <20% of development capacity on support

Solution - Phased Approach:

Phase 1 (Month 3-6): Create Application Support Team

- Move current support team → Platform Engineering

- Create Application Support Team:

  - Team Lead

  - 4-6 Support Engineers (existing support staff)

  - 2 Support Analysts (from BPM or new hires)

- They handle Tier 1-2 support across all applications

Phase 2 (Month 6-9): Define Support Model

- Tier 1 (How-to questions, password resets, basic issues)

  - Application Support Team handles

  - SLA: 4 hours response, 1 day resolution

- Tier 2 (Configuration, data issues, integration problems)

  - Application Support Team handles

  - Escalate to stream team if needed

  - SLA: 1 day response, 3 days resolution

- Tier 3 (Code bugs, architecture issues, complex problems)

  - Stream-aligned team handles

  - Rotational on-call (weekly rotation)

  - SLA: Same day response, varies on resolution

Phase 3 (Month 9-12): DevOps Improvements

- Stream teams improve monitoring and observability

- Proactive alerting reduces reactive support

- Better documentation reduces Tier 1-2 volume

- Automation of common support tasks

Expected Outcome:

- Developer time on support: 40-50% → 15-20%

- Capacity freed for new development

- Support quality improves (dedicated team)

### Challenge 5: BPM Project Managers in New Model

Current: BPM has Project Managers for big projects

Future: Where do they go?

Option A: Portfolio Management Pool

Head of Portfolio & Demand Management

├── Portfolio Analysts (2-3, from BPM intake)

└── Project Managers (2-3, from BPM PMs)

├── Assigned to major cross-domain projects

├── Assigned to large SaaS implementations

└── Coach Product Owners on delivery

Option B: Embedded with Largest Initiatives

- PM #1 → ERP/Large system project (if you have one)

- PM #2 → Digital transformation program

- PM #3 → Infrastructure modernization (coordinate with IT Systems)

Option C: Transition to Product Owners**

- Some PMs have business background → become Product Owners

- Requires training and mindset shift

- Works for PMs who want more business ownership

Recommendation: Hybrid

- 1-2 PMs → Portfolio Management pool (for major projects)

- 1-2 PMs → Transition to Product Owners (if interested and suitable)

- Not all PMs want or should be POs (different skill sets)

## Governance Structure for Your Organization

### IT Leadership Team (Weekly)

Members:

CTO/Head of Business Solutions (chair)

Head of IT Systems

Head of Enterprise Architecture

Head of Data & AI

Head of Portfolio & Demand Management

Head of Platform Engineering (if separate)

Purpose:

Alignment across IT

Resource coordination

Strategic decisions

Risk management

Continuous improvement

Agenda (60-90 min):

Business priorities and alignment (15 min)

Portfolio review (15 min)

Resource and capacity (15 min)

Architecture and technology (15 min)

IT Systems coordination (15 min)

Issues and decisions (15 min)

### Architecture Review Board (Bi-weekly)

Members:

Enterprise Architect (chair)

Solution Architects (2, rotating)

Data Architect

Security Architect

Head of IT Systems or Infrastructure Architect

1 senior developer (rotating)

Purpose:

Technology decisions

Architecture governance

Build vs. buy decisions

Vendor selection (technology aspects)

Meets: Bi-weekly, 2 hours

### IT Portfolio Review Board (Bi-weekly)

Members:

Head of Portfolio & Demand Management (chair)

Head of Business Solutions

Enterprise Architect (or delegate)

Head of Data & AI

CFO representative

2 rotating Product Owners

Purpose:

Prioritize cross-domain work

Resolve resource conflicts

Capacity planning

Project approvals

Meets: Bi-weekly, 90 min (off-week from ARB)

### Executive Portfolio Committee (Quarterly)

Members:

CEO (chair)

CTO/Head of Business Solutions

Head of IT Systems

CFO

3 BU Heads

Sales, HR, Finance leads (as needed)

Purpose:

Strategic portfolio decisions

Major investments (>€250K)

Annual and quarterly planning

Business-IT alignment

Meets: Quarterly, 2 hours

### Data Governance Board (Monthly)

Members:

Head of Data & AI (chair)

Data Architect

BU representatives (1 per BU)

Legal/Compliance

1 rotating Data Steward

Purpose:

Data policies and standards

Data ownership and access

Data quality oversight

Data privacy and compliance

Meets: Monthly, 90 min

## Your Specific Risks & Mitigations

### Risk 1: Resistance from BPM Team

Probability: Medium-High
Impact: Medium

Why they might resist:

Loss of organizational identity

Fear of diminished authority

"We've always done it this way"

Concern about Product Owner authority vs. BPM oversight

Mitigation:

Early involvement: BPM Manager in transformation steering committee

Clear future roles: Every BPM person has a defined role in new model

Respect expertise: "We're not eliminating BPM, we're evolving it"

Empower them: BPM becomes Portfolio Management (elevated, strategic)

Training: Help BPM people transition to new roles (PO, BA, Portfolio Analyst)

Communication:

"BPM's expertise in intake, prioritization, and business analysis is MORE valuable in the new model, not less"

"You'll be embedded where decisions happen, not coordinating from the side"

### Risk 2: Three BUs Competing for Resources

Probability: High
Impact: Medium-High

Scenario:

BU1: "We need this feature NOW for competitive reasons"

BU2: "Our revenue is bigger, we should get priority"

BU3: "We've been waiting 6 months already!"

Mitigation:

Portfolio Management function: Neutral arbitrator with clear prioritization framework

Executive Portfolio Committee: BU heads in the room, hash it out quarterly

Transparent criteria: Business value, strategic alignment, urgency (not politics)

Dedicated teams where possible: BU1 team, BU2 team, BU3 team (reduces conflicts)

Communication: Losers understand WHY they lost (data and rationale)

Escalation Path:

Product Owners try to resolve

Portfolio Management facilitates decision

IT Leadership Team decides

CEO decides (if BU heads can't agree)

### Risk 3: IT Systems Feels Left Out

Probability: Medium
Impact: Medium

Why:

IT Systems stays separate while Applications transforms

Might feel like "second class" or less strategic

Coordination overhead increases

Resource sharing becomes more complex

Mitigation:

CEO reinforces: IT Systems is equally strategic (infrastructure, security are foundational)

Include in governance: IT Systems represented on ARB, IT Leadership Team

Joint projects: Cloud migration, security improvements involve both orgs

Shared goals: Both organizations measured on business outcomes

Partnership messaging: "Two organizations, one IT mission"

Long-term:

Year 2-3: Re-evaluate if IT Systems should report to CTO

Based on: How well coordination works, strategic direction, leadership

### Risk 4: Product Owners Don't Have Business Credibility

Probability: Medium
Impact: High

Why this could happen:

POs hired from IT (not business)

POs too junior or inexperienced

Business units don't respect their authority

Mitigation:

Hire from business: First choice for POs is business people (from BU1, BU2, BU3, Sales, Finance)

Executive sponsorship: Each BU head explicitly empowers their PO

Senior enough: POs should be manager-level or above in business

Training: Product management training for all POs

Success stories: Early wins build credibility quickly

Ideal PO Profile for Your Org:

7-10 years in the business unit

Currently: Business Operations Manager, Process Manager, or Senior BA

Knows the domain deeply

Trusted by business leaders

Wants more impact and ownership

## Budget Adjustments for Your Context

### What You Already Have (Lower Costs)

Existing Capabilities (don't need to hire):

✅ Integration team (already exists) → becomes Integration Platform Team

✅ Head of Data (already exists) → no need to hire

✅ BPM team (already exists) → becomes Portfolio Management + BAs

✅ Support team (already exists) → moves to Platform Engineering

✅ IT Systems organization (already exists) → continues separately

Cost Savings vs. Base Blueprint:

Integration Specialists: -€150-200K (don't need to hire, already have team)

Head of Data & AI: -€130-160K (already have)

Portfolio/PM capability: -€200-300K (BPM team transitions)

Support team: €0 (already budgeted)

Estimated Savings: €480-660K vs. base blueprint

### What You Need to Add (New Costs)

Critical New Hires (Year 1):

| Role | Count | Cost Each | Total | Priority |
| --- | --- | --- | --- | --- |
| CTO/Unified IT Leader | 1 | €0-150K | €0-150K | If hiring external; €0 if promoting internally |
| Enterprise Architect | 1 | €130-160K | €130-160K | Month 1 - CRITICAL |
| Solution Architects | 2-3 | €95-125K | €190-375K | Month 2-4 |
| Data Architect | 1 | €100-130K | €100-130K | Month 3-4 |
| Security Architect | 1 | €100-130K | €100-130K | Month 6-9 (can wait) |
| Product Owners | 4-6 | €80-110K | €320-660K | Month 3-6 (from business ideally) |
| Business Analysts | 2-4 | €70-90K | €140-360K | Month 3-6 (some from BPM) |
| Data Engineers | 2-3 | €75-95K | €150-285K | Month 4-6 |
| Platform Engineers | 1-2 | €85-110K | €85-220K | Month 6-9 (support DevOps) |

Year 1 New Headcount: €1,315-2,470K

Adjustment: Some roles filled internally

2-3 Product Owners from BPM/Business (internal): -€160-330K

2 Business Analysts from BPM (internal): -€140-180K

Adjusted Year 1 Headcount: €1,015-1,960K

### Year 1 Total Budget (Your Organization)

| Category | Amount | Notes |
| --- | --- | --- |
| New Headcount | €1.0-2.0M | Architects, POs, BAs, Data Engineers |
| Platforms & Tools | €400-800K | Integration platform (may have), Data platform, Tools |
| Training & Development | €200-400K | All staff, heavy investment |
| Consulting & Advisory | €150-300K | Architecture advisory, change management |
| Contingency | €150-300K | 10-15% buffer |
| TOTAL YEAR 1 | €1.9-3.8M | Mid-point: ~€2.8M |

Compare to base blueprint: €3.0-4.5M
Your savings: €0.5-1.2M (due to existing capabilities)

### Year 2 Budget (Your Organization)

| Category | Amount | Notes |
| --- | --- | --- |
| Additional Headcount | €800K-1.5M | More SAs, BAs, Data Scientists, ML Engineers |
| Platforms (full year) | €600K-1.2M | Full year operation, expansion |
| Training | €200-400K | Ongoing development |
| Consulting | €50-150K | Reduced, specific needs |
| Contingency | €150-300K | Buffer |
| TOTAL YEAR 2 | €1.8-3.5M | Mid-point: ~€2.6M |

### 3-Year Investment (Your Organization)

Total: €8-12M (vs. €11-15M base blueprint)

Savings: €3M due to existing capabilities

ROI: Same business value (€23M+ over 3 years), lower investment = better ROI

## Customized Roles & Responsibilities

### Head of Business Solutions (Evolved Operations Manager)

Current: Operations Manager - manages development teams
Future: Head of Business Solutions - strategic business-IT partnership leader

Reports To: CTO (or CEO during transition)

Direct Reports:

Head of Portfolio & Demand Management (from BPM)

6-7 Product Owners (matrix: report to business, work with IT)

Lead Business Analyst (if creating BA Center of Excellence)

Solution Architects (matrix with Head of EA)

Key Responsibilities:

Strategic Partnership (30%):

Partner with BU heads and business leaders

Translate business strategy into technology roadmap

Ensure IT delivers business value

Business stakeholder satisfaction

Delivery Excellence (30%):

Stream-aligned teams delivering effectively

Quality, speed, and reliability

Team health and engagement

Continuous improvement

Portfolio Management (20%):

Work with Portfolio Management on prioritization

Capacity planning across teams

Resource optimization

Investment decisions

People Leadership (20%):

Build and develop teams

Recruit and retain talent

Career development

Culture and values

Success Metrics:

Business stakeholder satisfaction: 4/5+

Lead time: Reduced 40%+

Team engagement: 4/5+

Business value delivered: €X per quarter

Compensation: €110-140K + 20% bonus

### Head of Portfolio & Demand Management (Evolved BPM Manager)

Current: BPM Manager - intake, prioritization, PM
Future: Head of Portfolio & Demand Management - strategic portfolio orchestrator

Reports To: Head of Business Solutions (or CTO)

Direct Reports:

Portfolio Analysts (2-3, from BPM intake team)

Project Managers (2-3, from BPM PMs)

Business Analysis Lead (if centralizing BAs)

Key Responsibilities:

Demand Management (30%):

Single front door for all IT requests

Intake and categorization

Initial business case review

Route to appropriate Product Owner or keep for portfolio

Portfolio Prioritization (25%):

Chair IT Portfolio Review Board

Cross-domain initiative prioritization

Balance across business units

Transparent decision-making with clear rationale

Capacity Management (20%):

Track capacity across all teams

Identify bottlenecks and constraints

Recommend resource adjustments

Forecast future capacity needs

Program/Project Coordination (15%):

Assign Project Managers to major initiatives

Ensure cross-team coordination

Dependency management

Risk and issue escalation

Portfolio Reporting (10%):

Monthly portfolio dashboard

Quarterly executive reviews

Value delivered tracking

Pipeline and forecast

Success Metrics:

Request fulfillment time: <5 days for categorization

Portfolio health: 80%+ projects green/yellow

Resource utilization: 75-85% (not over/under)

Stakeholder satisfaction: 4/5+

Compensation: €95-125K + 15% bonus

### Product Owner - BU Technology Team

Example: Product Owner for Business Unit 1 Technology

Reports To: BU1 Head (Business side)
Works With: BU1 Technology Team (IT side)

Team:

Business Analyst (1-2)

Developers (4-5)

Testers (1-2)

Solution Architect (20-40% shared)

Key Responsibilities:

Product Strategy (30%):

Define technology vision for BU1

Align with BU1 business strategy

Identify technology opportunities

Build business cases for investments

Backlog Management (30%):

Prioritize all BU1 technology work

Manage product backlog

Define features and acceptance criteria

Balance quick wins and strategic work

Stakeholder Partnership (25%):

Daily partner with BU1 leadership

Understand business needs deeply

Manage expectations

Communicate progress and challenges

Team Collaboration (15%):

Sprint planning with team

Accept/reject completed work

Unblock team

Support team success

Domain Ownership:

All BU1-specific applications

BU1 integrations

BU1 data and reporting

BU1 process automation

Success Metrics (Business Outcomes):

BU1 specific KPIs (varies by BU - revenue, efficiency, customer satisfaction, etc.)

Technology adoption by BU1 users

Stakeholder satisfaction (BU1 leaders)

ROI of technology investments

Compensation: €85-110K + 20-25% bonus (tied to BU1 performance)

### Integration Platform Team Lead

Current: Integration Development Team Lead
Future: Integration Platform Team Lead - product mindset for integration platform

Reports To: Head of Platform Engineering

Team:

Integration Engineers (4-6, existing team)

Integration Architect (may need to hire or promote)

Technical Writer (0.5 FTE, can be shared)

Key Responsibilities:

Platform Development (40%):

Build integration platform capabilities

Create reusable connectors (Salesforce, SAP, APIs)

Self-service tools and templates

Platform automation and DevOps

Customer Service (30%):

Serve stream-aligned teams (customers)

Office hours and consultation

Respond to integration requests

Troubleshooting and support

Platform Operations (20%):

Monitor platform health (99.9% uptime target)

Performance optimization

Security and compliance

Incident response

Continuous Improvement (10%):

Identify platform enhancements

Learn new integration patterns

Industry trends

Team development

Treats platform as product:

Stream teams are customers

Self-service is goal (80% of requests self-served)

Service catalog and SLAs

Customer satisfaction tracked

Success Metrics:

Platform availability: 99.9%+

Integration delivery time: 3-5 days (standard)

Self-service rate: 70%+

Customer satisfaction: 4.5/5

Compensation: €95-120K + 15% bonus

## Your Culture Integration

Your Values → How Transformation Embodies Them:

### Flexibility

How transformation delivers:

✅ Stream-aligned teams can pivot quickly to changing business needs

✅ Product Owners can re-prioritize based on market conditions

✅ Architecture provides guardrails, not rigid gates

✅ Platform teams enable teams to move fast

Example: BU1 suddenly needs to respond to competitor - BU1 Technology Team can shift priorities immediately without going through bureaucracy

### Entrepreneurship

How transformation delivers:

✅ Product Owners are "mini-CEOs" of their domain

✅ Teams own outcomes, not just outputs

✅ Teams can make decisions without constant approval

✅ Encouraged to experiment and learn

Example: Customer & Sales PO identifies opportunity for new customer self-service capability, builds business case, gets approval, team delivers - all within the team's authority

### Agility

How transformation delivers:

✅ Small, cross-functional teams

✅ Continuous delivery (deploy weekly or more)

✅ Short feedback loops

✅ Respond to change over following a plan

Example: Claims regulation changes - Claims Technology Team can respond and deploy updates within 2 weeks instead of 3-month project cycle

### Lean

How transformation delivers:

✅ Eliminate handoffs between BPM and IT

✅ Reduce waste (work that doesn't deliver value)

✅ Focus teams on value stream

✅ Platforms eliminate duplication of effort

Example: Before - 5 handoffs from request to delivery. After - Product Owner receives request, prioritizes, team delivers. 5 steps → 3 steps.

### Robustness

How transformation delivers:

✅ Architecture practice ensures sound technical decisions

✅ Security embedded from start (Security Architect)

✅ Platforms provide reliable, tested patterns

✅ Data quality and governance

✅ Risk managed through ARB and portfolio management

Example: Architecture Review Board catches team about to make risky vendor choice, suggests better alternative, avoids €500K mistake and future pain

## Key Decisions You Need to Make

Decision 1: CTO/Unified Leadership

Options:

A: Promote Head of IT Applications to CTO

B: Hire external CTO

C: Maintain current structure (not recommended)

Recommendation: Option A (promote internally)

Knows your business and culture

Credibility with team

Lower cost and faster

Get external architecture expertise via EA hire

Timeline: Decide by end of Month 1

Decision 2: Stream-Aligned Team Model

Options:

A: BU-Aligned (BU1 team, BU2 team, BU3 team + functional teams)

B: Functional-Aligned (Customer, Operations, Finance teams serving all BUs)

C: Hybrid (mix of both)

To Decide:

Do your BUs have very different systems and processes? → Option A

Do BUs mostly share systems? → Option B

Some unique, some shared? → Option C

Action: Map your systems to BUs (Month 1-2), then decide

Timeline: Decide by Month 2

Decision 3: IT Systems Integration

Options:

A: Keep separate (coordinate via governance)

B: IT Systems reports to CTO (unified IT)

C: Split infrastructure - app infrastructure to CTO, network/hardware stays separate

Recommendation: Option A Year 1, evaluate Option B Year 2

Start separate, strong coordination

Evaluate after 12-18 months

Based on how well coordination works

Timeline: Decide Year 1 approach now, revisit Month 12

Decision 4: BPM Transition

Options:

A: Merge BPM completely into IT Applications (recommended)

B: Keep BPM separate but aligned

C: Distribute BPM people (some to portfolio, some to teams, eliminate BPM org)

Recommendation: Option A

Creates unified Business Solutions organization

Eliminates silos

BPM expertise valued and embedded

Timeline: Announce Month 1, execute Month 2-3

Decision 5: Support Model

Options:

A: Support stays with stream teams (DevOps "you build it, you run it")

B: Centralized Application Support team (Platform Engineering)

C: Hybrid (Tier 1-2 centralized, Tier 3 with teams)

Recommendation: Option C (hybrid)

Frees development capacity

Maintains team ownership

Dedicated support quality

Timeline: Decide Month 3, implement Month 4-6

## Your First 30 Days - Customized

### Week 1: Leadership Alignment & Structure

Day 1-2: CEO and Leadership

[ ] Meet with CEO (2 hours)

  - Present transformation vision

  - Discuss CTO/unified leadership structure

  - Get approval for BPM + IT Applications merge

  - Budget discussion (€2.8M Year 1)

  - Request explicit sponsorship

[ ] Meet with Head of IT Systems (1 hour)

  - Explain transformation (IT Applications focus)

  - Discuss coordination mechanisms

  - Address concerns about being "left out"

  - Partnership model

[ ] Meet with BPM Manager (1.5 hours)

  - Explain BPM evolution (not elimination)

  - Discuss their future role (Head of Portfolio & Demand Mgmt)

  - Address team concerns

  - Get their support as transformation champion

Day 3-4: Structure Definition

[ ] Draft new organization structure

  - CTO/Head of Business Solutions

  - Head of Portfolio & Demand Management

  - Head of EA

  - Head of Data & AI (existing)

  - Head of Platform Engineering

  - Stream-aligned teams (design)

[ ] Map current people to future structure

  - BPM intake team → Portfolio Analysts

  - BPM PMs → Project Manager pool

  - BPM BAs → some to teams, some to BA CoE

  - Development teams → stream teams (TBD which)

[ ] Identify pilot teams (2-3)

  - Criteria: Clear boundaries, motivated lead, business sponsor

  - Candidates: One BU team + one functional team

Day 5: Communication Preparation

[ ] Prepare announcement materials

  - New structure

  - Rationale (why we're doing this)

  - Timeline

  - What's in it for people

  - FAQ

[ ] Schedule Week 2 announcements

  - IT All-hands (IT Applications + BPM)

  - Separate session with IT Systems (explain coordination)

  - Business stakeholder briefing

### Week 2: Launch & Hiring

Day 6-7: Announcements

[ ] IT Applications + BPM All-Hands (90 min)

  - Announce merge and new structure

  - BPM becomes Portfolio & Demand Management

  - Stream-aligned team model

  - Timeline and approach

  - Q&A

[ ] IT Systems Briefing (45 min)

  - Explain what's happening in IT Applications

  - How this affects coordination

  - Governance structures

  - Partnership emphasis

[ ] Business Leaders Briefing (60 min)

  - 3 BU heads + supporting department heads

  - Transformation vision

  - Product Owner concept

  - What they need to do (provide POs)

Day 8-9: Immediate Actions

[ ] Post Enterprise Architect job

  - Executive recruiter engaged

  - Job description finalized

  - Posted internally and externally

  - Target: Hire within 45 days

[ ] Form Transformation Steering Committee

  - CEO (sponsor)

  - You (CTO/Head of Business Solutions)

  - Head of IT Systems

  - Head of Data

  - BPM Manager (becoming Portfolio head)

  - CFO

  - 2 BU heads (rotating)

  - First meeting: Week 3

[ ] Launch current state assessment

  - Systems inventory (who owns what)

  - Integration mapping

  - Skills inventory (survey IT Apps + BPM staff)

  - Vendor inventory

  - Timeline: Complete by end Month 1

Day 10: Communication Infrastructure

[ ] Set up transformation channels

  - Intranet transformation hub

  - Slack/Teams channel: #transformation

  - Weekly email update

  - Monthly all-hands schedule

[ ] Populate transformation hub

  - Vision and strategy

  - New organization structure

  - FAQ

  - Timeline and roadmap

  - How to provide feedback

### Week 3: Deep Dive & Planning

Day 11-15: Activities

[ ] Business stakeholder interviews (2-3 per day)

  - BU1, BU2, BU3 heads (60 min each)

  - Sales, Finance, HR, Claims leads (45 min each)

  - Questions: Pain points, needs, priorities, data wishes

  - Identify Product Owner candidates

[ ] BPM transition planning

  - Meet with each BPM team member

  - Discuss their future role

  - Address concerns

  - Career development

[ ] Map systems to business domains

  - Which systems serve BU1, BU2, BU3?

  - Which are shared?

  - Which are functional (CRM, Finance, HR)?

  - This informs stream team design

[ ] EA hiring progress

  - Review candidates from recruiter

  - Schedule interviews

  - Shortlist

[ ] Platform vendor research

  - Integration platform (may already have something)

  - Data platform (what does Head of Data recommend?)

  - Schedule demos for Month 2

Weekend (after Week 3):

[ ] Read "Team Topologies" (at least first half)

[ ] Draft pilot team designs

[ ] Prepare Week 4 activities

### Week 4: Finalization & Month 2 Setup

Day 16-18: Pilot Team Design

[ ] Design 2 pilot stream-aligned teams

  - Pilot 1: [BU or functional domain]

    - Product Owner: [Candidate identified]

    - Business Analyst: [From BPM or current]

    - Developers: [Names from current teams]

    - Testers: [Names]

    - Solution Architect: [TBD - to hire]

  - Pilot 2: [Different BU or functional domain]

    - Similar structure

[ ] Create pilot team charters

  - Use template from Appendix B

  - Scope, goals, success criteria

  - Timeline: 6 months pilot

[ ] Meet with pilot Product Owner candidates

  - Explain role

  - Offer opportunity

  - Get commitment (or find alternatives)

Day 19-20: Approval & Communication

[ ] Steering Committee Meeting #1 (2 hours)

  - Review Month 1 progress

  - Approve pilot team design

  - Approve Month 2-3 plan

  - Budget confirmation

  - Assign responsibilities

[ ] Month 1 communication

  - What we accomplished

  - Current state assessment findings

  - Pilot teams announced

  - EA hiring status

  - What's coming in Month 2

Day 21-22: Month 2 Preparation

[ ] Schedule Month 2 activities

  - Platform demos (6-8 over 2 weeks)

  - ARB kickoff (once EA hired)

  - Pilot team kickoffs (end of Month 2)

  - BPM transition activities

[ ] Finalize hiring plan

  - EA: Interviews scheduled

  - Solution Architects: Post jobs Month 2

  - Data Architect: Post job Month 2

  - Product Owners: Sourcing from business

[ ] BPM transition execution plan

  - Detailed timeline

  - Communication to BPM team

  - New role announcements

  - Change management support

End of Month 1 Reflection:

[ ] What went well?

[ ] What was harder than expected?

[ ] Adjustments for Month 2?

[ ] Quick wins identified?

[ ] Team morale check?

## Success Metrics - Customized for Your Organization

### Year 1 Success Criteria (Month 12)

Organizational:

✅ BPM and IT Applications merged into unified Business Solutions

✅ 4-6 stream-aligned teams operational

✅ Architecture practice established (EA + 2-3 SAs + Data Arch)

✅ Portfolio Management function working effectively

✅ IT Systems coordination smooth

Delivery:

✅ Lead time reduced 30%+ (from request to production)

✅ Deployment frequency increased (weekly or better)

✅ 50% capacity on new features (vs. 30% baseline estimate)

✅ Integration platform operational (10+ integrations)

✅ Data platform operational (5+ sources)

Business:

✅ Business stakeholder satisfaction: 3.5-4/5 (up from 2.5-3 baseline)

✅ BU heads satisfied with their Product Owners

✅ 200+ change request backlog managed (down to 80-100 active)

✅ Quick wins delivered: €500K+ value

People:

✅ Team satisfaction: 4/5+

✅ Key talent retained (attrition <10%)

✅ BPM team successfully transitioned

✅ New roles filled (internal promotions + external hires)

### Year 2 Success Criteria (Month 24)

Organizational:

✅ All teams stream-aligned (6-7 teams)

✅ Full architecture team (EA + 3-4 SAs + Data + Security)

✅ AI capability operational (2-3 data scientists, ML engineers)

✅ Vendor management function mature

Delivery:

✅ Lead time reduced 50%

✅ 65% capacity on new features

✅ Support <20% of development capacity

✅ Self-service platforms widely adopted

Business:

✅ Business stakeholder satisfaction: 4+/5

✅ 3-5 AI models in production

✅ Measurable business value: €8-10M over 2 years

✅ Data quality 95%+ for tier 1 data

People:

✅ New operating model the "new normal"

✅ Internal mobility (people growing into new roles)

✅ Training and development active

✅ Culture shift visible (entrepreneurship, agility, data-driven)

## What Makes Your Transformation Unique

Compared to base blueprint, your transformation has these unique aspects:

### 1. BPM Integration

You have existing intake, prioritization, and PM capability

Advantage: Don't need to build from scratch

Challenge: Change management (BPM team needs to evolve mindset)

Key: BPM becomes Portfolio Management (elevated, strategic)

### 2. Multiple Business Units

3 BUs create complexity (competing priorities)

Advantage: Forces clear prioritization and governance

Challenge: Resource conflicts between BUs

Key: Strong Portfolio Management and Executive Committee

### 3. IT Systems Separate

Infrastructure/security stays separate from applications

Advantage: Focused transformation scope

Challenge: Coordination and alignment critical

Key: Strong governance (IT Leadership Team, ARB, SLAs)

### 4. Data Leadership Already Exists

Head of Data already building team

Advantage: Data foundation can start immediately

Challenge: Ensure alignment with overall transformation

Key: Head of Data in steering committee, Data Architect hired early

### 5. Claims Complexity

Claims is complex, regulated, critical domain

Advantage: Clear candidate for dedicated stream team

Challenge: May need more resources (2 BAs, more testers)

Key: Claims Technology Team with proper staffing

## Final Recommendations Specific to You

1. Start with BPM Integration (Month 1)

This is your foundation

Get BPM team on board early

Their expertise is valuable

Frame as evolution, not elimination

2. Pilot with One BU Team + One Functional Team (Month 3-6)

BU Pilot: Choose one BU (maybe smallest or most eager)

Functional Pilot: Customer & Sales OR Claims (high visibility, clear value)

Prove model with both types

Learn and adjust before scaling

3. Don't Underestimate IT Systems Coordination (Ongoing)

This is a risk

Invest in governance structures

Regular IT Leadership meetings

Joint planning and projects

Consider: Year 2, should IT Systems report to CTO?

4. Leverage Existing Integration Team (Month 2-4)

You already have integration capability

Evolve to platform mindset

Add self-service

This can be a quick win

5. Product Owners from Business (Month 3-9)

Hire POs from your BUs and departments

Look for: Business Operations Managers, Process Leads

Not IT people becoming POs

Critical for credibility

6. Use Your Values as North Star (Always)

When in doubt, ask: "Does this support flexibility, entrepreneurship, agility, lean, robustness?"

If yes → do it

If no → reconsider

Your values are your differentiator

## You're Ready to Start

You now have:

✅ Customized organization structure

✅ Clear transition from current to future state

✅ BPM integration plan

✅ Adjusted budget (lower due to existing capabilities)

✅ Stream-aligned team options for your BU structure

✅ IT Systems coordination approach

✅ Governance model

✅ 30-day action plan customized to your context

✅ Success metrics

✅ Risk mitigations

Next Action: Day 1, this week: Block 2 hours, review this plan, schedule meeting with CEO for next week: "IT Transformation - Strategic Discussion"

You've got this. Your transformation starts now. 🚀

# Customized IT Transformation Blueprint for Your Logistics Organization (our Business Units)

## Your Specific Context

### Business Structure

Shipping BU: Ocean freight, vessel operations

Ports BU: Terminal operations (container terminals + car terminals)

Cargo BU: Door-to-door logistics, end-to-end supply chain

### Critical Systems Landscape

Current State:

Shipping BU

├── Legacy Shipping/Ports System (shared with Ports) → TO BE REPLACED

├── EDI integrations (customer booking, status updates)

├── Customs logic (embedded in legacy)

└── Billing System (own dev) → Future SaaS candidate

Ports BU

├── Legacy Shipping/Ports System (shared with Shipping) → TO BE REPLACED

├── Separate Car Terminal System

├── EDI integrations (terminal operations, customs)

└── Customs logic (embedded in legacy)

Cargo BU

├── TMS (Transport Management System) → REPLACEMENT IN PROGRESS

├── Separate systems from Shipping/Ports

└── Own integrations

Cross-BU / Shared

├── CRM (own dev) → Future SaaS candidate

├── Billing System (own dev) → Future SaaS candidate

├── HRIS SAP → BEING IMPLEMENTED

├── Seafarer HR System (own dev) → Future SaaS candidate

├── Databricks (data platform) → Already have!

├── Power BI (analytics) → Already have!

└── EDI Hub (many integrations)

Integration Layer

└── Extensive EDI integrations (customers, carriers, customs, ports)

Future State (already planned):

New Shipping System (separate from Ports)

New Ports System (separate from Shipping)

New Cargo TMS (in progress)

Potentially: CRM, Billing, Seafarer HR → SaaS

## Immediate Strategic Insights

### Good News - You Have Strong Foundation

Already Have (Major advantages):

✅ Databricks + Power BI: Data platform exists! (€200-400K saved)

✅ BPM team: 5 people doing intake/prioritization (exists)

✅ Head of Data: Building data capability (exists)

✅ Integration team: Must exist given EDI volume (confirmed)

✅ HRIS implementation underway: SAP experience with SaaS

This Saves You: €600K-1M vs. base blueprint

### Major Opportunities

1. Legacy System Replacement is Perfect Timing

Shipping and Ports splitting anyway

Use this as transformation catalyst

New systems = Clean architecture from day one

New Product Owner model aligns with new systems

2. SaaS Migration Wave Coming

CRM, Billing, Seafarer HR all candidates

Architecture and vendor management critical

Build vs. Buy decisions need EA oversight

3. Data Platform Already Exists

Databricks is excellent choice

Accelerate data and AI roadmap

Can start AI use cases earlier (Year 1 vs. Year 2)

4. EDI Integration Complexity

Hundreds of integrations likely

Integration platform ROI is huge

Quick wins through integration standardization

## Your Customized Organization Structure

### Current State (Assumed)

CEO

│

├── Head of IT Applications (~80 people)

│   ├── Operations Manager

│   │   ├── Shipping/Ports System Team

│   │   ├── Car Terminal System Team

│   │   ├── Cargo TMS Team

│   │   ├── CRM/Billing Team

│   │   ├── HR Systems Team

│   │   ├── Integration/EDI Team (est. 6-8 people)

│   │   └── Support Team (est. 15-20 people)

│   └── Head of Data (building team, est. 3-5 people)

│

├── BPM Department (~5 people)

│   ├── Intake & Prioritization (2)

│   ├── Business Analysts (2)

│   └── Project Manager (1)

│

└── Head of IT Systems

├── Infrastructure

├── Networks

└── Security

### Future State (Target - Month 18-24)

CEO

│

├── CTO (promoted Head of IT Applications)

│   │

│   ├── Head of Business Solutions & Delivery

│   │   │

│   │   ├── Portfolio & Demand Management (from BPM)

│   │   │   ├── Portfolio Analysts (2)

│   │   │   ├── Project Managers (2-3)

│   │   │   └── Business Analysis CoE Lead

│   │   │

│   │   ├── SHIPPING BUSINESS SOLUTIONS TEAM

│   │   │   ├── Product Owner (from Shipping BU) ⭐

│   │   │   ├── Business Analyst (1-2)

│   │   │   ├── Developers (8-10) - vessel ops, bookings, etc.

│   │   │   ├── Testers (2-3)

│   │   │   ├── Solution Architect (40% allocation)

│   │   │   └── Systems: New Shipping System, Shipping EDI, Customs

│   │   │

│   │   ├── PORTS & TERMINALS SOLUTIONS TEAM

│   │   │   ├── Product Owner (from Ports BU) ⭐

│   │   │   ├── Business Analyst (1-2)

│   │   │   ├── Developers (8-10) - container + car terminals

│   │   │   ├── Testers (2-3)

│   │   │   ├── Solution Architect (40% allocation)

│   │   │   └── Systems: New Ports System, Car Terminal, Ports EDI, Customs

│   │   │

│   │   ├── CARGO & LOGISTICS SOLUTIONS TEAM

│   │   │   ├── Product Owner (from Cargo BU) ⭐

│   │   │   ├── Business Analyst (1-2)

│   │   │   ├── Developers (6-8) - TMS, logistics

│   │   │   ├── Testers (2)

│   │   │   ├── Solution Architect (30% allocation)

│   │   │   └── Systems: TMS, Cargo integrations

│   │   │

│   │   ├── CUSTOMER & COMMERCIAL SOLUTIONS TEAM

│   │   │   ├── Product Owner (from Sales/Commercial) ⭐

│   │   │   ├── Business Analyst (1)

│   │   │   ├── Developers (4-6) - CRM, customer portals

│   │   │   ├── Testers (1-2)

│   │   │   ├── Solution Architect (20% allocation)

│   │   │   └── Systems: CRM, Customer Portal, Billing integrations

│   │   │

│   │   ├── FINANCE & BILLING SOLUTIONS TEAM

│   │   │   ├── Product Owner (from Finance) ⭐

│   │   │   ├── Business Analyst (1)

│   │   │   ├── Developers (4-5) - billing, finance

│   │   │   ├── Testers (1)

│   │   │   ├── Solution Architect (20% allocation)

│   │   │   └── Systems: Billing System, Finance integrations

│   │   │

│   │   └── HR & EMPLOYEE SOLUTIONS TEAM

│   │       ├── Product Owner (from HR) ⭐

│   │       ├── Business Analyst (1)

│   │       ├── Developers (3-4) - HRIS, Seafarer system

│   │       ├── Testers (1)

│   │       ├── Solution Architect (20% allocation)

│   │       └── Systems: SAP HRIS, Seafarer HR System

│   │

│   ├── Head of Enterprise Architecture

│   │   ├── Enterprise Architect (1) ⭐ NEW - CRITICAL

│   │   ├── Maritime/Logistics Architect (1) ⭐ NEW - Domain expert

│   │   ├── Solution Architects (3-4) ⭐ NEW

│   │   ├── Integration Architect (1) ⭐ NEW - Given EDI volume

│   │   └── Security Architect (1) NEW

│   │

│   ├── Head of Data & AI (existing, elevated)

│   │   ├── Data Architect (1) ⭐ NEW

│   │   ├── Data Engineers (4-6) - Databricks, pipelines

│   │   ├── Data Analysts (2-3) - Business intelligence

│   │   ├── Data Scientists (2-3) - AI/ML (Year 2)

│   │   ├── ML Engineers (2) - MLOps (Year 2)

│   │   └── Platform: Databricks, Power BI (existing!)

│   │

│   └── Head of Platform Engineering

│       │

│       ├── EDI & INTEGRATION PLATFORM TEAM ⭐ CRITICAL

│       │   ├── Team Lead

│       │   ├── Integration Engineers (6-8) - existing team evolved

│       │   ├── EDI Specialists (2-3) - logistics domain

│       │   ├── Integration Architect (matrixed from EA)

│       │   └── Platform: Integration Platform (MuleSoft/Boomi) + EDI Hub

│       │

│       ├── DEVOPS & INFRASTRUCTURE TEAM

│       │   ├── Team Lead

│       │   ├── DevOps Engineers (3-4)

│       │   ├── Cloud Engineers (2-3)

│       │   └── Tools: CI/CD, Cloud (Azure/AWS), Monitoring

│       │

│       └── APPLICATION SUPPORT TEAM

│           ├── Team Lead

│           ├── Support Engineers (10-12) - Tier 1-2

│           ├── EDI Support Specialists (2-3)

│           └── Coordination with stream teams for Tier 3

│

└── Head of IT Systems (stays separate - reports to CEO)

├── Infrastructure & Cloud

├── Networks (critical for ports/terminals)

├── Security & Compliance (customs, data privacy)

└── Operations Support

Total Headcount: ~95-105 people (from current 80 + 15-25 new hires over 2 years)

## Your Stream-Aligned Teams - Detailed Design

### Team 1: SHIPPING BUSINESS SOLUTIONS TEAM

Product Owner: From Shipping BU Operations or Commercial

Ideal candidate: Shipping Operations Manager or Head of Vessel Operations

Domain expert in vessel scheduling, booking, freight rates

Business outcome: Shipping revenue, vessel utilization, customer satisfaction

Team Composition: 13-16 people

Product Owner (1) - from Shipping

Business Analysts (2) - shipping operations expertise

Developers (8-10) - backend, integration, web

Testers (2-3) - quality critical for shipping operations

Solution Architect (40% = ~0.4 FTE shared)

Domain & Systems:

Primary: New Shipping System (replacing legacy)

  - Vessel scheduling and operations

  - Freight booking and pricing

  - Bill of Lading

  - Freight tracking

Secondary: Shipping EDI integrations (customers, agents, carriers)

Related: Customs logic for shipping

Integrations: CRM, Billing, Cargo (cross-selling)

Business Outcomes (KPIs this team influences):

Shipping revenue

Vessel utilization %

On-time departure/arrival %

Customer booking conversion rate

Freight rate optimization

Operational cost per TEU

Key Challenges:

Legacy system replacement is major initiative

Maritime domain complexity

Heavy EDI integration requirements

Customs compliance critical

24/7 operations (vessels don't stop)

Why This Team Makes Sense:

✅ Clear business domain (Shipping BU)

✅ Distinct customer base (shippers, freight forwarders)

✅ Own P&L and business metrics

✅ Natural Product Owner from Shipping leadership

✅ Technology will be distinct (new Shipping System)

### Team 2: PORTS & TERMINALS SOLUTIONS TEAM

Product Owner: From Ports BU Operations

Ideal candidate: Terminal Operations Manager or Port Operations Director

Domain expert in terminal operations, vessel berthing, cargo handling

Business outcome: Terminal throughput, equipment utilization, dwell time

Team Composition: 13-16 people

Product Owner (1) - from Ports

Business Analysts (2) - terminal operations, car terminal expertise

Developers (8-10) - TOS (Terminal Operating System), IoT/equipment

Testers (2-3)

Solution Architect (40% = ~0.4 FTE shared)

Domain & Systems:

Primary: New Ports/Terminal System (replacing legacy)

  - Vessel berthing and operations

  - Container/cargo tracking in terminal

  - Equipment scheduling (cranes, reach stackers)

  - Yard management

  - Gate operations

Secondary: Car Terminal System (separate system)

Related: Ports EDI (shipping lines, customs, rail/truck operators)

Related: Customs logic for ports

IoT: Equipment sensors, automation systems

Business Outcomes (KPIs this team influences):

Container throughput (TEUs)

Car throughput (units)

Berth utilization %

Equipment utilization %

Dwell time (containers in terminal)

Gate turn time (trucks)

Terminal revenue per TEU

Key Challenges:

Legacy system replacement

Two different terminal types (container + car)

Real-time operations and IoT integration

24/7 operations

Safety and compliance critical

Equipment automation

Why This Team Makes Sense:

✅ Clear business domain (Ports BU)

✅ Distinct operations (terminal vs. vessel operations)

✅ Own P&L

✅ Natural Product Owner from Ports operations

✅ Technology will be distinct (new Ports System)

Note: Depending on size/complexity, could split into:

Container Terminals Team (larger)

Car Terminals Team (smaller, might be 6-8 people)

### Team 3: CARGO & LOGISTICS SOLUTIONS TEAM

Product Owner: From Cargo BU Operations

Ideal candidate: Cargo Operations Manager or Head of Logistics

Domain expert in door-to-door logistics, multimodal transport

Business outcome: Cargo revenue, on-time delivery, margin per shipment

Team Composition: 10-12 people

Product Owner (1) - from Cargo

Business Analysts (1-2)

Developers (6-8) - TMS, logistics, tracking

Testers (2)

Solution Architect (30% = ~0.3 FTE shared)

Domain & Systems:

Primary: TMS (Transport Management System) - REPLACEMENT IN PROGRESS ⭐

  - Shipment planning and optimization

  - Carrier selection

  - Tracking and visibility

  - Proof of delivery

Secondary: Cargo-specific integrations

Related: Customer portal for cargo tracking

Integrations: Carriers, warehouses, customs brokers

Business Outcomes (KPIs this team influences):

Cargo revenue

Shipment margin %

On-time delivery %

Customer satisfaction (NPS)

Cost per shipment

Asset utilization (trucks, containers if owned)

Key Challenges:

TMS replacement already in progress ⚠️

  - Need to align with transformation

  - May already have project structure

  - Transition to Product Owner model mid-project

Door-to-door complexity (multimodal: truck, rail, ocean, air)

Real-time tracking and visibility expectations

Integration with many external carriers

Why This Team Makes Sense:

✅ Clear business domain (Cargo BU)

✅ Completely separate systems from Shipping/Ports

✅ Different customer base (cargo shippers vs. freight shippers)

✅ Own P&L

✅ Natural Product Owner from Cargo leadership

Special Note: TMS replacement project needs integration into transformation

Likely has existing project team and PM

Transition: PM → Product Owner or PM continues but reports to PO

Use as pilot for Product Owner model

### Team 4: CUSTOMER & COMMERCIAL SOLUTIONS TEAM

Product Owner: From Sales/Commercial Department

Ideal candidate: Head of Commercial Excellence or Customer Experience Manager

Domain expert in customer journey, sales process, customer service

Business outcome: Customer acquisition, retention, satisfaction, sales conversion

Team Composition: 7-10 people

Product Owner (1) - from Sales/Commercial

Business Analyst (1)

Developers (4-6) - CRM, portals, web

Testers (1-2)

Solution Architect (20% = ~0.2 FTE shared)

Domain & Systems:

Primary: CRM System (own dev) → Future SaaS candidate ⭐

  - Customer master data

  - Opportunities and pipeline

  - Customer interactions

  - Account management

Secondary: Customer Portals

  - Booking portal (shipping/cargo)

  - Tracking and visibility

  - Documentation (invoices, B/L)

  - Self-service

Related: Customer data integration to all BUs

Business Outcomes (KPIs this team influences):

Customer acquisition (new customers)

Customer retention rate

Customer lifetime value

Sales pipeline conversion

Customer satisfaction (NPS, CSAT)

Self-service adoption %

Key Challenges:

CRM replacement decision: Build vs. Buy (likely Buy - Salesforce, Dynamics)

Serves all three BUs (Shipping, Ports, Cargo)

  - Different customer types

  - Different sales processes

  - Need to balance priorities

Customer data quality critical

Why This Team Makes Sense:

✅ Clear domain: Customer-facing technology

✅ Cross-BU but unified (all BUs need CRM)

✅ Natural Product Owner from Commercial/Sales

✅ Aligns with customer experience as strategic priority

Governance Note:

PO coordinates with all 3 BUs for requirements

Quarterly review with Shipping, Ports, Cargo heads

Prioritize based on customer impact and revenue

### Team 5: FINANCE & BILLING SOLUTIONS TEAM

Product Owner: From Finance Department

Ideal candidate: Finance Operations Manager or Head of Billing/Revenue

Domain expert in billing, revenue recognition, financial reporting

Business outcome: Billing accuracy, DSO (Days Sales Outstanding), revenue recognition

Team Composition: 6-8 people

Product Owner (1) - from Finance

Business Analyst (1)

Developers (4-5) - billing, finance, integration

Testers (1)

Solution Architect (20% = ~0.2 FTE shared)

Domain & Systems:

Primary: Billing System (own dev) → Future SaaS candidate ⭐

  - Invoice generation (shipping, ports, cargo)

  - Pricing and tariffs

  - Revenue recognition

  - Credit management

Secondary: Finance reporting and integrations

Related: Integration to ERP/Finance systems

Data: Financial data to Databricks for reporting

Business Outcomes (KPIs this team influences):

Billing accuracy (% invoices without errors)

Days Sales Outstanding (DSO - how fast customers pay)

Revenue leakage (unbilled services)

Time to invoice (speed)

Finance close cycle time

Key Challenges:

Billing for 3 different BUs (different tariff structures)

Complex pricing (freight rates, terminal tariffs, cargo pricing)

Revenue recognition rules (IFRS 15)

Billing system replacement: Build vs. Buy decision

Integration with finance/accounting systems

Why This Team Makes Sense:

✅ Clear domain: Billing and revenue

✅ Cross-BU but unified (all BUs bill through same system)

✅ Natural Product Owner from Finance

✅ Clear business metrics (DSO, accuracy, leakage)

Note: Depending on size, could merge with Customer & Commercial (both commercial functions), but billing complexity likely warrants separate team.

### Team 6: HR & EMPLOYEE SOLUTIONS TEAM

Product Owner: From HR Department

Ideal candidate: Head of HR Operations or HR Systems Manager

Domain expert in HR processes, employee lifecycle, seafarer management

Business outcome: Employee satisfaction, HR efficiency, compliance

Team Composition: 6-8 people

Product Owner (1) - from HR

Business Analyst (1)

Developers (3-4) - HRIS, seafarer system, integrations

Testers (1)

Solution Architect (20% = ~0.2 FTE shared)

Domain & Systems:

Primary: SAP HRIS → BEING IMPLEMENTED ⭐

  - Employee master data

  - Payroll

  - Time & attendance

  - Performance management

  - Recruiting

Secondary: Seafarer HR System (own dev) → Future SaaS candidate ⭐

  - Crew management

  - Certifications and licenses

  - Voyage assignments

  - Seafarer payroll (different from shore)

  - Maritime compliance (STCW, MLC)

Related: Employee self-service portal

Business Outcomes (KPIs this team influences):

Employee satisfaction / engagement

HR process efficiency (time to hire, time to onboard)

Compliance (seafarer certifications, MLC compliance)

Payroll accuracy

Crew availability and planning

Key Challenges:

SAP HRIS implementation in progress ⚠️

  - Large SAP project likely has own governance

  - Need to integrate into Product Owner model

Seafarer HR is complex and unique (maritime compliance)

Two very different user bases: shore employees vs. seafarers

Seafarer system replacement decision (niche market, specialized SaaS exists)

Why This Team Makes Sense:

✅ Clear domain: Employee technology

✅ Natural Product Owner from HR

✅ Combination of SaaS (SAP) and custom (Seafarer) is manageable

✅ HR systems serve all BUs

Special Note on SAP HRIS:

Likely already has SAP Program Manager and implementation partner

Transition approach:

  - Current SAP PM continues for implementation

  - Product Owner takes over post-go-live (ongoing ownership)

  - Or: SAP PM becomes Product Owner (if from HR and suitable)

## Platform Teams - Your Context

### EDI & INTEGRATION PLATFORM TEAM ⭐ MOST CRITICAL

Why This is Your Highest ROI Platform:

Logistics = integration-heavy industry

EDI everywhere: EDIFACT messages (IFTMIN, IFTSTA, IFCSUM, etc.)

Customer integrations: 100s of customers, each with EDI requirements

Carrier integrations: Shipping lines, trucking companies, rail, airlines

Port/customs integrations: Port community systems, customs authorities

B2B integration critical for operations

Current State (Assumed):

Integration/EDI team exists (6-8 people estimate)

Point-to-point integrations (hundreds of them)

Mix of: Custom code, EDI software, manual processes

High maintenance burden

Each new integration takes weeks/months

Future State - Integration Platform Team:

Team Composition: 12-15 people

Team Lead (1) - from current integration team

Integration Engineers (6-8) - existing team evolved + new hires

EDI Specialists (2-3) - logistics domain experts (EDIFACT, customs messages)

Integration Architect (matrixed 80% from EA team)

Technical Writer (0.5 FTE - documentation critical)

Platform Stack:

Integration Platform: MuleSoft, Boomi, Azure Logic Apps, or Dell Boomi

  - Recommendation for logistics: MuleSoft or Boomi (strong EDI capabilities)

EDI Hub/Gateway: Existing or new (many platforms have EDI support)

API Management: Layer for modern APIs

Monitoring: Real-time integration monitoring and alerting

Responsibilities:

Platform Development (40%):

Build integration platform capabilities

Create reusable connectors:

  - CRM connector (Salesforce, Dynamics)

  - ERP/SAP connector

  - Shipping/TOS systems connectors

  - EDI message templates (IFTMIN, IFTSTA, IFCSUM, IFTMAN, etc.)

Self-service tools for stream teams

Platform automation and DevOps

EDI Services (30%):

EDI message mapping and transformation

Customer/partner EDI onboarding

EDI compliance and standards

Customs messaging (varies by country)

Test harnesses for EDI

Integration Support (20%):

Serve stream-aligned teams

Office hours and consultation

Complex integration assistance

Troubleshooting and issue resolution

Operations (10%):

Monitor integration health (99.9% uptime)

Performance optimization

Incident response

SLA management

Service Catalog (What stream teams can request):

Self-Service (Goal: 60% of integrations):

Standard EDI message (customer, carrier) - using templates

Standard API integration - using existing connectors

Data sync between known systems

Estimated time: 2-3 days by team themselves

Platform Team Assistance (30% of integrations):

New EDI partner with custom requirements

Complex API integration

New connector development

Estimated time: 5-10 days

Custom Development (10% of integrations):

Highly complex, unique integration

New protocol or standard

Legacy system with no API

Estimated time: 2-4 weeks

Success Metrics:

Platform availability: 99.9%+

Integration delivery time: Median <5 days (from weeks currently)

Self-service rate: 60%+

Customer EDI onboarding time: <2 weeks (from 4-8 weeks)

Customer satisfaction: 4.5/5+

Quick Wins (First 6 months):

Migrate 10-15 existing integrations to platform

Create 5-8 reusable connectors

Self-service portal for standard EDI messages

Monitoring dashboard (visibility for all)

Result: 50% faster integration delivery

ROI:

Current: ~200 integrations, average 3 weeks to build, €3K effort each = €600K/year

Future: Platform reduces effort 60% = €360K saving

Plus: Faster time-to-market, better reliability, easier maintenance

### DATA PLATFORM TEAM

Great News: You already have Databricks and Power BI! 🎉

Current State:

Databricks deployed

Power BI deployed

Head of Data building team (3-5 people currently)

Likely: Some data sources connected, some dashboards

Future State - Mature Data Platform Team:

Team Composition: 10-14 people (Year 2)

Head of Data & AI (existing - elevated role)

Data Architect (NEW - Month 3-4)

Data Engineers (4-6) - pipelines, data quality, Databricks

Data Analysts (2-3) - business intelligence, Power BI

Data Scientists (2-3) - ML/AI (Year 2)

ML Engineers (2) - MLOps (Year 2)

Platform Stack (Already Have!):

Data Platform: Databricks ✅

Visualization: Power BI ✅

Add: Data catalog (Collibra, Alation, or Azure Purview)

Add: Data quality monitoring

Add: ML platform (Databricks ML or Azure ML)

Responsibilities:

Data Engineering (40%):

Build data pipelines from all source systems

Data quality monitoring and cleansing

Data transformation and modeling

Real-time and batch pipelines

Analytics & BI (30%):

Self-service analytics enablement

Power BI dashboard development

Business intelligence support

Data literacy and training

Data Governance (15%):

Data catalog maintenance

Data quality oversight

Data access and security

Master data management

AI/ML (15%, growing to 40% in Year 2):

ML model development

MLOps and model deployment

AI use case identification

Model monitoring and improvement

Priority Data Sources (Month 4-12):

High Priority (First 6 months):

New Shipping System → Databricks (vessel ops, bookings, revenue)

New Ports System → Databricks (terminal ops, throughput)

TMS (Cargo) → Databricks (shipments, logistics)

Billing System → Databricks (revenue, invoicing)

CRM → Databricks (customers, sales pipeline)

Medium Priority (Month 6-12): 6. SAP HRIS → Databricks (employees, payroll) 7. Car Terminal System → Databricks 8. EDI/Integration logs → Databricks (operational intelligence)

Lower Priority (Year 2): 9. Seafarer HR System 10. External data (market data, weather, port congestion)

Analytics Use Cases (Prioritized):

Year 1 - Foundation:

Executive dashboard (revenue, volume, KPIs across BUs)

Operational dashboards (vessel tracking, terminal throughput, shipment status)

Financial reporting (revenue, billing, collections)

Customer analytics (top customers, customer health, churn risk)

Year 2 - Advanced Analytics & AI:

Predictive demand forecasting (freight demand by route)

Dynamic pricing optimization (freight rates based on demand, capacity)

Equipment predictive maintenance (terminal equipment, vessels)

Route optimization (cargo logistics)

Customer churn prediction

Container/cargo dwell time prediction

Vessel ETA prediction (weather, port congestion)

AI Use Cases - Logistics-Specific (Year 2):

High ROI Use Cases:

Dynamic Freight Pricing (Shipping)

  - Predict optimal freight rates based on demand, route, season, competition

  - Impact: +2-5% revenue through better pricing

Demand Forecasting (All BUs)

  - Predict freight volume by route and time

  - Capacity planning and optimization

  - Impact: Better asset utilization (+5-10%)

Equipment Predictive Maintenance (Ports)

  - Predict crane, reach stacker failures before they happen

  - Reduce downtime and maintenance costs

  - Impact: 20-30% reduction in unplanned downtime

Dwell Time Prediction (Ports)

  - Predict how long containers will stay in terminal

  - Optimize yard planning

  - Impact: Better yard utilization, reduced congestion

Route & Load Optimization (Cargo)

  - AI-powered route planning for door-to-door logistics

  - Load optimization (trucks, containers)

  - Impact: 10-15% cost reduction per shipment

Customer Churn Prediction (Commercial)

  - Identify customers at risk of leaving

  - Proactive retention

  - Impact: Reduce churn by 20-30%

Success Metrics:

Data quality: 95%+ for tier 1 data (shipping, ports, cargo, finance)

Self-service adoption: 60%+ of analytics requests self-served

Time to insight: <1 day for standard queries

AI models in production: 3-5 by end of Year 2

Business value from AI: €2-5M/year

### DEVOPS & INFRASTRUCTURE TEAM

Part of Platform Engineering

Team Composition: 6-8 people

Team Lead (1)

DevOps Engineers (3-4)

Cloud Engineers (2-3)

Responsibilities:

CI/CD pipelines for all stream teams

Cloud infrastructure (Azure or AWS)

Monitoring and observability

Infrastructure as code

Container orchestration (Kubernetes if needed)

Security tooling and automation

Service Catalog:

New environment provisioning (dev, test, prod)

CI/CD pipeline setup

Monitoring and alerting setup

Performance testing support

Infrastructure consultation

### APPLICATION SUPPORT TEAM

Part of Platform Engineering

Team Composition: 12-15 people

Team Lead (1)

### APPLICATION SUPPORT TEAM (continued)

Part of Platform Engineering

Team Composition: 12-15 people

Team Lead (1)

Support Engineers (10-12) - Tier 1-2 support

  - Shipping/Ports specialist (2-3)

  - Cargo specialist (2)

  - CRM/Billing specialist (2)

  - HRIS specialist (1-2)

  - General support (3-4)

EDI Support Specialists (2-3) - Critical given EDI volume

Responsibilities:

Tier 1 Support (50%):

User inquiries and how-to questions

Password resets and access issues

Standard troubleshooting

Incident logging and categorization

SLA: 4 hours response, 1 day resolution

Tier 2 Support (35%):

Complex troubleshooting

Data issues and corrections

Configuration problems

EDI message failures (many will be here)

System performance issues

SLA: 1 day response, 3 days resolution

Knowledge Management (10%):

Documentation and knowledge base

Training materials

User guides

FAQ maintenance

Continuous Improvement (5%):

Identify recurring issues

Recommend improvements to stream teams

Process optimization

Tier 3 Escalation to Stream Teams:

Code defects

Architecture/design issues

Complex business logic problems

New feature requests disguised as issues

Stream teams: Rotational on-call, handle escalations

Support Model:

24/7 coverage needed (shipping/ports don't stop)

Follow-the-sun model or on-call rotation

Specialized by domain (shipping operations support is different from HR support)

Heavy EDI support (message failures, partner issues)

Success Metrics:

First Contact Resolution: 60%+

SLA compliance: 95%+

Customer satisfaction (CSAT): 4/5+

Developer time on support: <20% (vs. 40%+ currently)

Escalation rate to Tier 3: <15%

Handoff to Support (From Stream Teams):

Each stream team creates runbooks

Support team trained on each system

Regular sync meetings (weekly)

Support shadows team for new releases

## Major Projects Integration with Transformation

You have 3 major projects already in flight or planned. These need special handling:

### 1. Legacy Shipping/Ports System Replacement ⭐⭐⭐ CRITICAL

Current Plan: Split into two systems

New Shipping System

New Ports System

Transformation Alignment:

This is Your Transformation CATALYST - Perfect timing!

Approach:

Option A: Run as Traditional Projects, Transition to Product Owner Model After Go-Live

Hire/assign Project Managers for system implementations

Large SaaS implementations need PM rigor

After go-live: PM hands off to Product Owner for ongoing ownership

Pro: Lower risk for critical implementations

Con: Delays full Product Owner model adoption

Option B: Product Owner Model from Day 1

Assign Product Owners immediately

POs own vendor selection, implementation, ongoing

PM supports but PO makes decisions

Pro: Product Owner fully invested from start

Con: PO learning curve during critical project

Recommendation: Hybrid - Option A with Product Owner Involvement

Shipping System Replacement:

Project Governance (During Implementation):

├── Steering Committee

│   ├── Shipping BU Head (sponsor)

│   ├── CTO

│   └── CFO

├── Project Manager (dedicated, 18-24 months)

├── Product Owner (from Shipping BU) ⭐ INVOLVED FROM START

│   ├── Business requirements owner

│   ├── UAT and acceptance

│   ├── Change management for Shipping users

├── Solution Architect (40%)

├── Implementation Partner (vendor + SI)

└── Project Team

├── Shipping SMEs (business)

├── Developers (integration, customization)

└── Testers

Post Go-Live (Month 18+):

├── Product Owner (full ownership)

├── Shipping Business Solutions Team (ongoing)

└── PM moves to next project

Ports System Replacement: Same structure

Timeline Alignment:

Transformation Month 1: Product Owners identified

Transformation Month 2-3: Product Owners engaged in vendor selection

Transformation Month 4-9: System selection and contracting

Transformation Month 10-24: Implementation (PM leads, PO heavily involved)

Transformation Month 24+: Go-live, transition to Product Owner ownership

Benefits of This Approach:

✅ Product Owner owns requirements from day 1 (better outcome)

✅ PM manages project complexity (vendor, timeline, risk)

✅ Smooth transition post go-live (PO already knows system)

✅ Architecture team ensures sound technical decisions

✅ PO can learn role during implementation (lower stakes than BAU)

Architecture Review Critical:

New systems = greenfield architecture decisions

EA must review and approve vendor selection

Integration architecture critical (EDI, data, other systems)

API-first, cloud-native, modern architecture

Avoid vendor lock-in

Key Decisions (Months 3-6):

Build vs. Buy? (Almost certainly Buy - SaaS TOS/Shipping system)

Which vendor? (CargoWise? Navis N4? Other specialized maritime software?)

Cloud deployment? (Yes - Azure or AWS)

Integration strategy? (via Integration Platform)

Data migration approach?

### 2. Cargo TMS Replacement ⭐⭐ IN PROGRESS

Current Status: Project started (assumed)

Challenge: Project in flight, need to integrate into transformation

Assessment Needed (Month 1):

What stage is project? (vendor selection? implementation? testing?)

Who's leading? (PM? Business lead?)

What governance exists?

Timeline to go-live?

Transformation Integration (Depends on stage):

If Early Stage (vendor selection, contracting):

Assign Cargo Product Owner immediately

PO takes ownership of project going forward

PM supports or transitions to PO model

Same approach as Shipping/Ports

If Mid-Stage (implementation underway):

Don't disrupt! Let project continue with current structure

Identify Product Owner for post-go-live

PO shadows project, learns system

Transition at go-live

If Late Stage (UAT, near go-live):

Let project complete as-is

Product Owner takes over immediately after go-live

Quick transition to Product Owner model

Post Go-Live:

Cargo Business Solutions Team owns TMS

Continuous improvement and enhancement

Integration with other systems via Integration Platform

Special Considerations:

TMS is Cargo's core system - business critical

Cargo BU needs to be first or early pilot for Product Owner model

Use TMS project experience to shape transformation approach

### 3. SAP HRIS Implementation ⭐ IN PROGRESS

Current Status: Being implemented (SAP SuccessFactors or S/4HANA HCM?)

SAP Project Characteristics:

Large, complex, 12-18 month implementation

Implementation partner (Deloitte, Accenture, others?)

Significant change management

Likely has robust governance already

Transformation Integration:

During Implementation:

SAP Program Manager continues (don't disrupt)

Identify HR Product Owner for post-go-live

Product Owner role:

  - Involved in business requirements

  - UAT and user acceptance

  - Change management and training

  - Prepare for ongoing ownership

Post Go-Live:

Product Owner takes full ownership

HR & Employee Solutions Team owns SAP HRIS

Ongoing: Enhancements, integrations, optimization

SAP expertise may stay (contractor or hire) for technical support

Why This Works:

SAP implementations require specialized rigor - don't change that

Product Owner model perfect for post-go-live (continuous improvement)

HR Product Owner also owns Seafarer HR System (different system, same domain)

## Your Transformation Roadmap - Customized

### Month 1: Foundation & Launch

Week 1-2: Leadership & Structure

Day 1-3: CEO and Executive Alignment

[ ] Meet with CEO (2 hours)

  - Present transformation vision

  - Promote Head of IT Applications to CTO

  - BPM + IT Applications merge approved

  - Budget: €2.5-3M Year 1

  - CEO sponsorship confirmed

[ ] Meet with 3 BU Heads (1 hour each)

  - Shipping BU Head

  - Ports BU Head

  - Cargo BU Head

  - Explain Product Owner concept

  - Request: Each BU provides Product Owner candidate

  - Discuss legacy system replacements as opportunity

[ ] Meet with CFO (1 hour)

  - Budget discussion and approval process

  - ROI and business case

  - Financial metrics and reporting

Day 4-5: Internal IT Alignment

[ ] Meet with BPM Manager (1.5 hours)

  - BPM evolution to Portfolio & Demand Management

  - Their future role: Head of Portfolio & Demand Management

  - Team transition plan

  - Get their support and enthusiasm

[ ] Meet with Head of Data (1 hour)

  - Elevation of role in transformation

  - Data platform acceleration

  - AI roadmap discussion

  - Their team growth plan

[ ] Meet with Operations Manager (1.5 hours)

  - Evolution to Head of Business Solutions & Delivery

  - Stream-aligned team model

  - Their role in transformation

  - Support and partnership

[ ] Meet with Integration/EDI Team Lead (1 hour)

  - Integration Platform vision

  - Their team evolution (current 6-8 to future 12-15)

  - EDI expertise is highly valued

  - Platform team opportunity

[ ] Meet with Head of IT Systems (1 hour)

  - Transformation scope (IT Applications focus)

  - Coordination and partnership model

  - Governance structures

  - Address any concerns

Week 3: Announcements & Assessment

Day 11: IT All-Hands (IT Applications + BPM, 90 min)

[ ] Transformation announcement

  - Vision: Business partnership, agility, data-driven

  - Why: Legacy system replacements, SaaS wave, AI opportunities

  - Structure: BPM merge, stream teams, platform teams

  - Timeline: 24 months, phased approach

  - Opportunities: New roles, growth, modern tech

  - Q&A (be open and transparent)

Day 12: Business Stakeholder Briefing (60 min)

[ ] Attendees: 3 BU Heads, Sales, Finance, HR leads

[ ] Content:

  - Transformation overview

  - Product Owner concept and expectations

  - "You'll have dedicated IT partners"

  - What we need from you (provide Product Owners)

  - Timeline and benefits

Day 13-15: Current State Assessment Launch

[ ] Systems inventory

  - Who owns what system?

  - Which systems serve which BU?

  - Integration dependencies

  - Technical debt assessment

[ ] Skills inventory survey

  - All IT Applications + BPM staff (85 people)

  - Current skills, desired skills, career interests

  - Domain expertise (shipping, ports, cargo, EDI)

[ ] Integration/EDI mapping

  - Document all current integrations

  - EDI partners and message types

  - Integration patterns and technology

  - Pain points and issues

[ ] Vendor inventory

  - All current vendors and licenses

  - Costs and contract terms

  - Redundancies and consolidation opportunities

Week 4: Hiring & Planning

Day 16-18: Critical Hires Launch

[ ] Enterprise Architect - TOP PRIORITY ⭐

  - Job description finalized

  - Executive recruiter engaged

  - Requirements: Maritime/logistics industry experience preferred

  - Posted internally and externally

  - Target hire: 30-45 days

  - Salary: €130-160K

[ ] Maritime/Logistics Architect - UNIQUE TO YOUR INDUSTRY ⭐

  - Domain expertise critical

  - Understands shipping, terminals, cargo logistics

  - Experience with maritime systems (TOS, shipping systems)

  - Can be Solution Architect level or Enterprise Architect level

  - Target hire: Month 2-3

  - Salary: €95-130K

[ ] Solution Architect positions (2-3)

  - Post jobs Month 2

  - Embedded with stream teams

[ ] Integration Architect

  - EDI and integration platform expertise

  - Critical given integration volume

  - Can promote from current integration team or hire external

Day 19-20: Pilot Team Selection

[ ] Identify 2 pilot stream-aligned teams

Recommendation:

  - Pilot 1: Cargo Business Solutions Team

    - Why: TMS replacement in progress, natural transition point

    - Product Owner from Cargo BU

    - Clear business domain

    - Separate systems from Shipping/Ports

  - Pilot 2: Customer & Commercial Solutions Team

    - Why: CRM replacement candidate, high visibility

    - Product Owner from Sales/Commercial

    - Cross-BU but clear domain

    - Strategic priority (customer experience)

[ ] Alternative pilots:

  - Finance & Billing (if ready)

  - HR & Employee (if HRIS implementation stage allows)

Day 21-22: Month 1 Wrap & Month 2 Setup

[ ] Transformation Steering Committee Meeting #1

  - Members: CEO, CTO (you), 3 BU Heads, CFO, Head of IT Systems, BPM Manager, Head of Data

  - Review Month 1 progress

  - Approve pilot teams

  - Approve hiring plan

  - Approve Month 2-3 roadmap

  - Budget confirmed

[ ] Communication

  - Month 1 transformation update (email + intranet)

  - What we accomplished

  - Assessment findings (high level)

  - Pilots announced

  - What's coming in Month 2

### Month 2-3: Architecture Foundation & Pilot Design

Architecture Practice Launch

Month 2:

[ ] Enterprise Architect hired and onboards (Week 5-6)

  - Intensive onboarding: Meet all teams, BUs, stakeholders

  - System landscape review

  - Current state architecture assessment

  - Legacy system replacement strategy

  - Integration architecture (critical)

[ ] Form Architecture Review Board (Week 7)

  - Enterprise Architect (chair)

  - Maritime/Logistics Architect (if hired, otherwise senior dev)

  - Integration Architect (from integration team or hire)

  - Head of Data (Data Architect search begins)

  - Head of IT Systems or Infrastructure Architect

  - 2 senior developers (rotating)

  - Meets: Bi-weekly, starting Week 7

[ ] Initial architecture work (Week 6-8)

  - Architecture principles defined

    - API-first

    - Cloud-first (Azure or AWS)

    - Buy before build (especially for maritime systems)

    - Integration via platform (no more point-to-point)

    - Data centralized (Databricks)

    - Security by design

    - Maritime standards (UN/EDIFACT, SMDG, etc.)

  - Architecture assessment

    - Legacy system analysis (technical debt, integration complexity)

    - Integration patterns (current state - likely point-to-point mess)

    - Data architecture (current - siloed, inconsistent)

    - Security posture

    - Cloud readiness

Month 3:

[ ] Platform vendor evaluation (Week 9-12)

Integration Platform (CRITICAL):

  - Shortlist: MuleSoft, Boomi, Azure Logic Apps

  - For logistics, recommend: MuleSoft or Boomi

    - Strong EDI capabilities

    - Pre-built connectors for logistics systems

    - Cloud-native

    - Proven in maritime/logistics

  - Evaluation criteria:

    - EDI support (UN/EDIFACT, X12, customs messages)

    - Maritime system connectors (CargoWise, Navis, etc.)

    - Cloud deployment

    - Self-service capabilities

    - Cost (license + implementation + ongoing)

    - Vendor stability and support

  - POC: Real use case

    - Example: Customer EDI integration (IFTMIN booking message)

    - Test: Message transformation, routing, error handling

    - Measure: Time to implement, ease of use

  - Decision: End of Month 3

  - Procurement: Begin Month 4

Data Catalog (Month 3):

  - Already have Databricks, add catalog

  - Options: Azure Purview (if Azure), Collibra, Alation

  - Decision: Month 3

BPM Transition (Month 2-3):

[ ] Org structure change effective (Week 5)

  - BPM Department dissolves (as separate org)

  - BPM Manager → Head of Portfolio & Demand Management

  - Reports to: CTO (you) or Head of Business Solutions (Operations Manager evolved)

[ ] BPM team member transitions (Week 5-8)

  - Intake/Prioritization staff (2) → Portfolio Analysts

  - Business Analysts (2) → Options:

    - Join BA Center of Excellence

    - Embed with pilot stream teams

    - Transition to Product Owner (if suitable and interested)

  - Project Manager (1) → Project Manager pool (Portfolio Management)

[ ] Process evolution (Week 6-12)

  - Current BPM intake process continues BUT

  - Add categorization: Domain-specific vs. Cross-domain

  - Domain-specific → Route to future Product Owner (or current team for now)

  - Cross-domain → Portfolio Management handles

  - Begin capacity tracking by team

Pilot Team Design (Month 2-3):

Pilot 1: Cargo Business Solutions Team (Week 6-12)

[ ] Product Owner identification

  - Target: Cargo Operations Manager or Head of Logistics

  - Meet and offer role

  - If accept: Begin Product Owner training

  - If decline: Find alternative (Cargo Director, Process Manager)

[ ] Team composition design

  - Current: People working on TMS project + Cargo systems

  - Future team:

    - Product Owner (1) - from Cargo

    - Business Analyst (1) - from BPM or current

    - Developers (6-8) - from current Cargo teams

    - Testers (2) - from current

    - Solution Architect (30% = 0.3 FTE) - to be hired, Month 4

[ ] Define scope and boundaries

  - In scope: TMS, Cargo integrations, Cargo customer portal

  - Out of scope: Shipping systems, Ports systems, shared CRM

  - Integrations: Via Integration Platform (when ready)

[ ] Team charter draft

  - Mission, vision, scope

  - Success metrics (Cargo BU KPIs)

  - Ways of working

  - Decision rights

Pilot 2: Customer & Commercial Solutions Team (Week 8-12)

[ ] Product Owner identification

  - Target: Head of Commercial Excellence or Customer Experience Manager

  - Cross-BU role (serves all 3 BUs)

  - Meet and offer role

[ ] Team composition design

  - Product Owner (1) - from Sales/Commercial

  - Business Analyst (1)

  - Developers (4-6) - CRM, customer portal

  - Testers (1-2)

  - Solution Architect (20%)

[ ] Define scope

  - In scope: CRM, customer portals, customer data

  - Serves: All 3 BUs (prioritization needed)

  - Major initiative: CRM replacement evaluation

Legacy System Replacement Projects (Month 2-3):

Shipping & Ports System Replacement:

[ ] Product Owners identified (Month 2-3)

  - Shipping Product Owner: From Shipping BU operations

  - Ports Product Owner: From Ports BU operations

  - These are likely different people than pilot POs

[ ] Project structure designed (Month 3)

  - Project Managers assigned (2 - one for Shipping, one for Ports)

  - Steering committees formed

  - Product Owners involved from vendor selection onward

[ ] Vendor evaluation planning (Month 3-6)

  - RFP preparation begins

  - Architecture Review Board oversight

  - Requirements gathering (Product Owners lead)

Cargo TMS (Month 2-3):

[ ] Assessment of current project status

[ ] Product Owner transition plan

[ ] Integration into transformation governance

SAP HRIS (Month 2-3):

[ ] Assessment of implementation status

[ ] HR Product Owner identified (for post-go-live)

[ ] Integration with transformation where appropriate

End of Month 3 Deliverables:

✅ EA hired and productive

✅ ARB operational (meeting bi-weekly)

✅ Architecture principles defined

✅ Integration Platform selected

✅ BPM integrated into IT Applications

✅ 2 pilot teams designed and POs identified

✅ Legacy system replacement projects structured with PO involvement

✅ Solution Architect hiring in progress

### Month 4-6: Pilot Launch & Platform Deployment

Pilot Teams Go Live (Month 4):

Week 13-14: Pilot Team Kickoffs

[ ] Cargo Business Solutions Team kickoff

  - Team charter finalized and signed

  - Backlog initial prioritization (Product Owner)

  - Sprint 1 planning

  - Tools setup (Jira/Azure DevOps, Slack/Teams channel)

  - Ways of working established

[ ] Customer & Commercial Team kickoff

  - Similar structure

[ ] Support for pilots

  - Weekly check-ins with each pilot (CTO or Head of Business Solutions)

  - Architecture support (EA embedded)

  - Remove blockers aggressively

  - Portfolio Management support

Week 15-24: Pilots Delivering

[ ] Sprints running (2-week sprints typical)

[ ] Product Owners learning and adapting

[ ] Teams delivering working software

[ ] Metrics tracked (lead time, velocity, satisfaction)

[ ] Challenges identified and addressed

[ ] Quick wins celebrated

Integration Platform Deployment (Month 4-6):

[ ] Platform procurement and contracting (Month 4)

[ ] Platform infrastructure setup (Month 4-5)

  - Cloud environment (Azure or AWS)

  - Development, test, production instances

  - Monitoring and alerting

[ ] Integration Platform Team formation (Month 4-5)

  - Current integration team transitions

  - Team Lead (promote from current team)

  - Integration Engineers (existing 6-8)

  - Hire: Integration Architect (if not already)

  - Hire: 2-3 additional Integration Engineers (Month 5-6)

  - Hire: EDI Specialists (2, Month 5-6)

[ ] Platform development (Month 5-6)

  - First connectors: CRM, Billing, TMS

  - EDI message templates: IFTMIN (booking), IFTSTA (status), IFCSUM (consignment summary)

  - Self-service portal (basic)

  - Documentation and training

[ ] First integrations migrated (Month 6)

  - Pilot: 3-5 integrations moved to platform

  - Customer EDI: 2-3 customers

  - Internal: CRM to Billing, TMS to CRM

  - Measure: Time, quality, stability

  - Learn and improve

Data Platform Acceleration (Month 4-6):

[ ] Data Architect hired (Month 4-5)

[ ] Data Engineers hired (2-3, Month 4-6)

  - Total team: 6-8 people (including existing)

[ ] Data sources prioritized (Month 4)

  - Priority: New systems first (TMS Cargo if live, or next priority)

  - If legacy still in use: Shipping/Ports legacy system

  - CRM, Billing

  - Plan for future: New Shipping, New Ports

[ ] Data pipelines built (Month 5-6)

  - First 3-5 data sources to Databricks

  - Data quality monitoring

  - Data catalog initial population

[ ] Analytics use cases (Month 6)

  - Executive dashboard (revenue, volume by BU)

  - Operational dashboards (1-2 initial)

  - Self-service analytics pilot

Architecture Team Building (Month 4-6):

[ ] Solution Architects hired (2, Month 4-6)

  - Embedded with teams (pilot teams initially)

  - Support legacy system replacement projects

[ ] Maritime/Logistics Architect hired (Month 4-5) if not Month 3

  - Domain expertise for shipping, ports, cargo

  - Supports all teams with maritime context

[ ] Security Architect hiring begins (Month 6)

  - Hire Month 7-9

Portfolio Management Maturing (Month 4-6):

[ ] Capacity model created (Month 4-5)

  - Track capacity by team

  - Forecast future capacity needs

[ ] IT Portfolio Review Board operational (Month 5)

  - Bi-weekly meetings

  - Cross-domain prioritization

  - Resource conflict resolution

[ ] Change request backlog management (Month 5-6)

  - Categorize all 200+ requests

  - Route domain-specific to pilot Product Owners

  - Portfolio handles cross-domain

  - Communicate status to all requestors

Support Transition Planning (Month 5-6):

[ ] Current support team assessment

  - Who does what?

  - Pain points and issues?

  - Handoff process with development teams?

[ ] Future support model designed

  - Tier 1-2: Application Support Team (Platform Engineering)

  - Tier 3: Stream teams

  - 24/7 coverage model (follow-the-sun or on-call)

  - EDI support specialization

[ ] Pilot support transition (Month 6)

  - One pilot team (Cargo) transitions support to new model

  - Learn and adjust

  - Roll out to other teams Month 7+

Legacy System Replacement Progress (Month 4-6):

[ ] Shipping System: Vendor selection in progress or complete

[ ] Ports System: Vendor selection in progress or complete

[ ] Implementation planning

[ ] Product Owners actively involved

End of Month 6 Deliverables:

✅ 2 pilot teams operational and delivering

✅ Integration Platform deployed (initial)

✅ Data Platform team built, first pipelines delivering

✅ Architecture team forming (EA + 2-3 SAs + Data Arch + Maritime Arch)

✅ Portfolio Management operational

✅ Quick wins delivered (integration examples, data dashboards, pilot team velocity)

✅ Support model piloted

✅ Transformation 25% complete

### Month 7-12: Expansion & Scale

Stream Team Expansion (Month 7-9):

[ ] Convert 3-4 more teams to stream-aligned model

Wave 2 Teams:

  - Shipping Business Solutions Team (Month 7)

    - Product Owner from Shipping BU

    - Team: 13-16 people

    - Focus: New Shipping System implementation + BAU

  - Ports & Terminals Solutions Team (Month 7-8)

    - Product Owner from Ports BU

    - Team: 13-16 people

    - Focus: New Ports System implementation + BAU

  - Finance & Billing Solutions Team (Month 8-9)

    - Product Owner from Finance

    - Team: 6-8 people

    - Focus: Billing system, evaluate SaaS options

  - HR & Employee Solutions Team (Month 9) (if HRIS project allows)

    - Product Owner from HR

    - Team: 6-8 people

    - Focus: SAP HRIS post-go-live prep + Seafarer system

[ ] Total by Month 9: 6 stream teams operational

Platform Teams Mature (Month 7-12):

Integration Platform Team (Month 7-12):

[ ] Team at full strength (12-15 people by Month 9)

[ ] 10-15 integrations on platform by Month 9

[ ] 20+ integrations by Month 12

[ ] Self-service capabilities expanding

[ ] EDI onboarding streamlined (<2 weeks for new customer)

[ ] Platform availability >99%

Data Platform Team (Month 7-12):

[ ] Team: 8-10 people by Month 9

[ ] Data sources: 7-10 by Month 12

  - New Shipping System (if live)

  - New Ports System (if live)

  - TMS Cargo

  - CRM, Billing, SAP HRIS

  - Legacy Shipping/Ports (until retired)

[ ] Data quality: 90%+ for tier 1 data

[ ] Self-service analytics: 50+ users by Month 12

[ ] AI readiness assessment complete

DevOps & Infrastructure Team (Month 7-12):

[ ] Team: 6-8 people

[ ] CI/CD for all stream teams

[ ] Cloud infrastructure (all new systems cloud-based)

[ ] Monitoring comprehensive

Application Support Team (Month 7-12):

[ ] Team: 12-15 people

[ ] Support for all 6 stream teams

[ ] 24/7 coverage operational

[ ] EDI support specialized

[ ] Developer support time: <20%

Architecture Practice Mature (Month 7-12):

[ ] Full team by Month 10:

  - Enterprise Architect (1)

  - Maritime/Logistics Architect (1)

  - Solution Architects (3-4)

  - Integration Architect (1)

  - Data Architect (1)

  - Security Architect (1) - hired Month 9

[ ] Architecture Review Board meeting weekly (increased frequency)

[ ] Technology radar published

[ ] Reference architectures documented

[ ] ADRs (Architecture Decision Records) for all major decisions

Portfolio Management Full Power (Month 7-12):

[ ] All change requests categorized and routed

[ ] Capacity planning accurate

[ ] Resource conflicts minimal (good planning)

[ ] Quarterly portfolio reviews with Executive Committee

[ ] Business value tracking

Data & AI Planning (Month 10-12):

[ ] AI use case prioritization

  - Top 3-5 use cases identified

  - Business cases developed

  - Data readiness assessed

[ ] ML platform selection (Month 11-12)

  - Databricks ML (already have Databricks)

  - Or: Azure ML, AWS SageMaker

[ ] Data Scientist hiring plan (for Year 2)

Legacy System Replacements (Month 7-12):

[ ] Shipping System: Implementation underway (months 12-24 estimated)

[ ] Ports System: Implementation underway (months 12-24 estimated)

[ ] Architecture oversight continuous

[ ] Product Owners fully engaged

Year 1 Metrics (Month 12):

Organizational:

  - 6 stream-aligned teams operational ✅

  - 3 platform teams operational ✅

  - Architecture practice established (7-8 people) ✅

Delivery:

  - Lead time reduced: 30%+ ✅

  - Integration delivery: 50% faster ✅

  - Data pipelines: 7-10 sources ✅

Business:

  - Business stakeholder satisfaction: 3.5-4/5 ✅

  - Integration platform ROI: €200-300K savings ✅

  - Quick wins: €500-800K value ✅

People:

  - Team satisfaction: 4/5 ✅

  - Attrition: <10% ✅

  - Training delivered: 40 hours/person ✅

End of Year 1:

✅ Transformation 50% complete

✅ New operating model working

✅ Platforms operational and delivering value

✅ Architecture practice mature

✅ Business partnership model emerging

✅ Ready for Year 2: AI, optimization, continuous improvement

### Month 13-18: AI Capability & Optimization

All Teams Stream-Aligned (Month 13-15):

[ ] If not already: Convert remaining teams

[ ] All 6-7 teams fully operational

[ ] Product Owners mature and effective

[ ] Teams autonomous and delivering

AI/ML Capability Building (Month 13-18):

Team Building:

[ ] Data Scientists hired (2-3, Month 13-15)

### Month 13-18: AI Capability & Optimization (continued)

AI/ML Capability Building (continued):

Team Building:

[ ] Data Scientists hired (2-3, Month 13-15)

  - Maritime/logistics domain knowledge preferred

  - ML experience (predictive models, optimization)

  - Python, ML frameworks (scikit-learn, TensorFlow, PyTorch)

[ ] ML Engineers hired (2, Month 14-16)

  - MLOps expertise

  - Model deployment and monitoring

  - Databricks ML or Azure ML experience

[ ] Data & AI team now: 12-16 people

  - Head of Data & AI

  - Data Architect

  - Data Engineers (4-6)

  - Data Analysts (2-3)

  - Data Scientists (2-3) ⭐ NEW

  - ML Engineers (2) ⭐ NEW

ML Platform Deployment (Month 13-15):

[ ] Platform selection finalized (Month 13)

  - Recommendation: Databricks ML (you already have Databricks)

  - Alternative: Azure ML (if Azure cloud)

[ ] Platform setup (Month 14)

  - ML workspace configuration

  - Model registry

  - Experiment tracking

  - Feature store

[ ] MLOps infrastructure (Month 15)

  - CI/CD for ML models

  - Model deployment pipelines

  - Model monitoring and alerting

  - A/B testing framework

First AI Use Cases (Month 15-18):

Use Case 1: Dynamic Freight Pricing (Shipping) - Month 15-18

Business Problem: Manual freight rate setting, missing optimization opportunities

ML Approach: Price optimization model

  - Features: Route, season, demand, capacity, competition, fuel costs, historical rates

  - Target: Optimal freight rate (maximize revenue while maintaining competitiveness)

  - Model: Gradient boosting (XGBoost, LightGBM)

Data Required:

  - Historical bookings and rates (2+ years)

  - Vessel capacity and utilization

  - Market rates (competitive intelligence)

  - Route profitability

Expected Impact: +2-5% revenue through better pricing

Timeline:

  - Month 15: Data preparation, exploratory analysis

  - Month 16: Model development and training

  - Month 17: Pilot with 2-3 routes

  - Month 18: Production deployment, monitoring

Product Owner: Shipping Business Solutions Team PO

Use Case 2: Equipment Predictive Maintenance (Ports) - Month 15-18

Business Problem: Unplanned equipment downtime costs €X per hour, impacts throughput

ML Approach: Predictive maintenance model

  - Features: Equipment sensor data (IoT), maintenance history, usage patterns, age

  - Target: Probability of failure in next 7/14/30 days

  - Model: Time-series classification, anomaly detection

Data Required:

  - Equipment maintenance history

  - Sensor data (vibration, temperature, usage hours)

  - Failure incidents

Expected Impact: 20-30% reduction in unplanned downtime

Timeline: Similar to Use Case 1

Product Owner: Ports & Terminals Solutions Team PO

Use Case 3: Container Dwell Time Prediction (Ports) - Month 16-18

Business Problem: Yard planning difficult without knowing container dwell time

ML Approach: Regression model

  - Features: Container type, cargo type, customer, destination, customs status, season

  - Target: Predicted dwell time (days in terminal)

  - Model: Random forest or gradient boosting

Expected Impact: Better yard utilization, reduced congestion

Timeline:

  - Month 16: Data prep and model development

  - Month 17-18: Pilot and production

Product Owner: Ports & Terminals Solutions Team PO

Architecture & Security Optimization (Month 13-18):

Security Architecture (Month 13-16):

[ ] Security Architect now in role (hired Month 9)

[ ] Security assessment complete (Month 13-14)

  - Application security

  - Data security (especially customs data, commercial data)

  - Integration security (EDI, APIs)

  - Cloud security

  - Identity and access management

[ ] Security roadmap (Month 14)

  - Critical vulnerabilities remediation

  - Security standards and policies

  - Secure development practices

  - Security monitoring and SIEM

[ ] Security implementation (Month 15-18)

  - Zero-trust architecture

  - API security (OAuth, API keys)

  - Data encryption (at rest, in transit)

  - GDPR compliance (personal data)

  - Maritime security standards (ISPS Code if applicable)

Architecture Optimization (Month 13-18):

[ ] Reference architectures comprehensive

  - Microservices architecture (for new systems)

  - Integration architecture (via platform)

  - Data architecture (Databricks-centric)

  - Cloud architecture (Azure or AWS patterns)

  - Maritime-specific patterns (EDI, vessel tracking, terminal operations)

[ ] Technical debt reduction initiatives

  - Legacy system retirement tracking

  - Code quality improvements

  - Documentation catch-up

  - Test automation

[ ] Architecture guilds and communities

  - Monthly architecture community of practice

  - Knowledge sharing across teams

  - Innovation time (20% for exploration)

Vendor Management & Optimization (Month 13-18):

If Not Already: Head of Vendor Management hired (Month 13-14)

Vendor Portfolio Optimization:

[ ] SaaS consolidation (Month 14-16)

  - Identify duplicate tools

  - Eliminate redundancies

  - Negotiate better rates

  - Target: €100-200K savings

[ ] Strategic vendor relationships (Month 15-18)

  - Tier 1 vendors: Strategic partnerships

    - Integration platform vendor

    - New Shipping system vendor

    - New Ports system vendor

    - Databricks

    - Microsoft (if SAP, Power BI, Azure)

  - Regular business reviews

  - Roadmap alignment

  - Volume discounts negotiated

CRM & Billing Replacement Decisions (Month 14-18):

CRM Replacement (Month 14-16):

[ ] Build vs. Buy analysis (Month 14)

  - Current: Own development CRM

  - Options: Salesforce, Microsoft Dynamics 365, SugarCRM

  - Recommendation: Buy (SaaS) - almost certainly

[ ] Vendor evaluation (Month 15)

  - Requirements from Customer & Commercial PO

  - Architecture Review Board oversight

  - Demos and POCs

  - Cost analysis

[ ] Decision & planning (Month 16)

  - Vendor selected

  - Implementation plan (Month 18-24)

  - Integration strategy (via Integration Platform)

  - Data migration strategy

Billing System (Month 16-18):

[ ] Build vs. Buy analysis (Month 16)

  - Current: Own development

  - Complex: 3 BUs, different tariff structures

  - Options:

    - SaaS: Zuora, BillingPlatform, custom built on Salesforce

    - Keep and modernize current system

  - Likely decision: Depends on complexity, may need custom or heavily configured SaaS

[ ] If SaaS: Vendor evaluation Month 17-18

[ ] Implementation: Year 3 likely (complex migration)

Seafarer HR System (Month 16-18):

[ ] Build vs. Buy analysis (Month 16)

  - Current: Own development

  - Niche: Maritime crew management

  - SaaS options exist: Mespas, Danaos, Tero Marine

[ ] Vendor evaluation (Month 17-18)

  - Maritime crew management features

  - Certifications tracking (STCW)

  - Voyage assignments

  - Seafarer payroll

  - Integration with SAP HRIS

[ ] Decision: Month 18

  - Implementation: Year 2-3

Legacy System Retirement Progress (Month 13-18):

[ ] Shipping System: Implementation ongoing (Month 12-24)

[ ] Ports System: Implementation ongoing (Month 12-24)

[ ] Target go-live: Month 20-24 (Year 2)

[ ] Legacy system retirement: Month 24-30

End of Month 18 Deliverables:

✅ All stream-aligned teams operational (6-7 teams)

✅ AI capability operational (2-3 Data Scientists, 2 ML Engineers)

✅ ML platform deployed (Databricks ML)

✅ 2-3 AI models in development/pilot

✅ Architecture mature (security, reference architectures)

✅ Vendor portfolio optimized

✅ CRM replacement decision made

✅ Legacy system replacements progressing well

✅ Transformation 75% complete

### Month 19-24: Maturity & Continuous Improvement

AI Models in Production (Month 19-24):

[ ] Dynamic Freight Pricing model live (Month 19)

  - Shipping team using in daily operations

  - Business impact measured

  - Continuous monitoring and improvement

[ ] Equipment Predictive Maintenance live (Month 20)

  - Ports team scheduling maintenance proactively

  - Downtime reduction measured

[ ] Container Dwell Time Prediction live (Month 21)

  - Yard planning optimized

  - Throughput improved

[ ] 2-3 additional models in development

  - Demand Forecasting (all BUs): Predict freight volume by route/lane

  - Customer Churn Prediction: Identify at-risk customers

  - Route Optimization (Cargo): AI-powered logistics planning

  - Vessel ETA Prediction: Better arrival time predictions (weather, port congestion)

Business Value from AI (Month 22-24):

[ ] Measured impact: €2-5M/year

  - Freight pricing optimization: +€1-2M revenue

  - Predictive maintenance: €500K-1M cost savings

  - Other use cases: €500K-2M combined

[ ] AI roadmap for Year 3

  - 5-10 models in production target

  - Scaling ML operations

  - More sophisticated use cases

New System Go-Lives (Month 20-24):

Shipping System Go-Live (Month 20-22, estimated):

[ ] Implementation complete

[ ] UAT and user training

[ ] Data migration from legacy

[ ] Cutover and go-live

[ ] Post-go-live stabilization

[ ] Product Owner takes full ownership

[ ] Shipping Business Solutions Team ongoing enhancements

Ports System Go-Live (Month 22-24, estimated):

[ ] Similar timeline to Shipping

[ ] Ports Business Solutions Team ownership

Legacy System Retirement (Month 24-26):

[ ] Once both new systems stable

[ ] Legacy system decommissioned

[ ] Technical debt eliminated

[ ] Major milestone! 🎉

Platform Teams at Scale (Month 19-24):

Integration Platform Team:

[ ] 30+ integrations on platform

[ ] Self-service rate: 70%+

[ ] New customer EDI onboarding: <1 week (from 4-6 weeks)

[ ] Platform availability: 99.95%

[ ] Team innovations: AI-powered integration monitoring, auto-healing

Data Platform Team:

[ ] 12-15 data sources in Databricks

[ ] Data quality: 95%+ tier 1 data

[ ] Self-service analytics: 100+ active users

[ ] Data catalog comprehensive

[ ] Data literacy program: 200+ employees trained

[ ] Real-time data pipelines operational

DevOps Team:

[ ] All teams deploying daily or more

[ ] Deployment automation complete

[ ] Infrastructure as code (100%)

[ ] Observability comprehensive

[ ] Chaos engineering (resilience testing)

Application Support Team:

[ ] Supporting all systems efficiently

[ ] Developer support time: 15% (target achieved)

[ ] CSAT: 4.2/5

[ ] Knowledge base comprehensive

[ ] Continuous improvement: 30% ticket reduction year-over-year

Organization Fine-Tuning (Month 19-24):

[ ] Team boundaries adjusted based on 18 months experience

  - Any teams too big or too small?

  - Any domains better combined or split?

  - Optimize based on learning

[ ] Product Owner effectiveness

  - All POs mature and confident

  - Business partners trust and value POs

  - POs making good decisions autonomously

[ ] Career development active

  - Internal promotions (developers → architects, BAs → POs)

  - Clear career paths

  - Succession planning

IT Systems Coordination Review (Month 20):

[ ] Evaluate: Should IT Systems report to CTO?

  - How well has coordination worked?

  - Benefits of unification?

  - Risks?

[ ] Decision options:

  - A: Continue separate (if working well)

  - B: IT Systems reports to CTO (unified IT)

  - C: Hybrid (some functions move, some stay separate)

[ ] Recommendation: Assess in Month 20, decide by Month 24

Culture Transformation Visible (Month 19-24):

[ ] Values embodied:

  - ✅ Flexibility: Teams pivot quickly to business needs

  - ✅ Entrepreneurship: POs empowered, teams innovative

  - ✅ Agility: Continuous delivery, rapid response

  - ✅ Lean: Waste eliminated, focus on value

  - ✅ Robustness: Architecture ensures quality and security

[ ] Data-driven decision making normal

  - Metrics visible to all

  - Decisions backed by data

  - Experiments and learning

[ ] Continuous improvement embedded

  - Retrospectives driving change

  - Innovation time used well

  - Learning culture

Business Outcomes Demonstrated (Month 24):

Organizational:

✅ 6-7 stream-aligned teams operational

✅ 3 platform teams mature

✅ Architecture practice comprehensive (8-10 people)

✅ Data & AI team delivering value (12-16 people)

✅ Portfolio Management effective

✅ ~100 people total (from 80 + ~20 net new)

Delivery:

✅ Lead time reduced 50% (from 6-8 weeks to 3-4 weeks)

✅ Deployment frequency: Daily (from monthly)

✅ 65% capacity on new features (from ~30%)

✅ Integration delivery: 70% faster

✅ Support: <15% developer time (from 40%)

Business Value:

✅ Business stakeholder satisfaction: 4+/5 (from ~2.5/5)

✅ Integration platform savings: €600K/year

✅ Vendor optimization savings: €200K/year

✅ AI value delivered: €2-5M/year

✅ Faster time-to-market: Revenue opportunities captured sooner

✅ Total 3-year value: €15-20M

People:

✅ Team satisfaction: 4.2/5

✅ Attrition: <8%

✅ Internal mobility: 15+ people in new roles

✅ Training: 50+ hours/person/year

✅ Culture: Entrepreneurial, agile, data-driven

Technology:

✅ New Shipping System live (replacing legacy)

✅ New Ports System live (replacing legacy)

✅ New Cargo TMS operational

✅ Integration platform: 30+ integrations

✅ Data platform: 12-15 sources, comprehensive analytics

✅ AI: 3-5 models in production

✅ Cloud-first architecture

✅ Technical debt significantly reduced

End of Month 24:

✅ Transformation complete (90%)

✅ New operating model the "new normal"

✅ Business outcomes achieved

✅ Sustainable and continuously improving

## Your Customized Budget

### Year 1 Budget (Your Organization)

New Headcount (€1.4-2.2M):

| Role | Count | Cost Each | Total | When |
| --- | --- | --- | --- | --- |
| CTO (if external) | 0-1 | €0-150K | €0-150K | Month 1 (or promote internally = €0) |
| Enterprise Architect | 1 | €130-160K | €130-160K | Month 2 ⭐ |
| Maritime/Logistics Architect | 1 | €95-130K | €95-130K | Month 3 ⭐ |
| Solution Architects | 2-3 | €95-125K | €190-375K | Month 4-6 |
| Integration Architect | 1 | €95-125K | €95-125K | Month 4-5 |
| Data Architect | 1 | €100-130K | €100-130K | Month 4-5 |
| Product Owners | 4-5 | €85-110K | €340-550K | Month 3-6 (from business ideally = partial cost) |
| Business Analysts | 2-3 | €70-90K | €140-270K | Month 3-6 (some from BPM = partial) |
| Data Engineers | 2-3 | €75-95K | €150-285K | Month 4-6 |
| Integration Engineers | 2-4 | €75-95K | €150-380K | Month 5-6 |
| EDI Specialists | 2 | €75-95K | €150-190K | Month 5-6 |
| Platform Engineers | 1-2 | €85-110K | €85-220K | Month 6-9 |

Total New Headcount Year 1: €1,625-2,965K

Adjustments:

CTO: Promote internally (€0) vs. hire external (+€150K)

Product Owners: 3-4 from business (business pays salary initially) = -€255-440K

Business Analysts: 2 from BPM transition (already budgeted) = -€140-180K

Adjusted Year 1 Headcount: €1,230-2,345K (using mid-point: ~€1.8M)

Platforms & Tools (€350-700K):

| Platform/Tool | Year 1 | Notes |
| --- | --- | --- |
| Integration Platform | €80-200K | MuleSoft or Boomi; logistics pricing |
| Databricks | €0 | ✅ Already have! |
| Power BI | €0 | ✅ Already have! |
| Data Catalog | €30-100K | Azure Purview, Collibra, or Alation |
| API Management | €20-60K | Azure APIM or AWS API Gateway |
| Monitoring/Observability | €30-80K | Datadog, New Relic, or Azure Monitor |
| DevOps Tools | €20-50K | GitHub, Azure DevOps (may have) |
| EDI Gateway (if new) | €40-100K | May have existing or included in integration platform |
| ML Platform | €0-30K | Databricks ML (included) or Azure ML |
| Security Tools | €30-80K | SIEM, vulnerability scanning, etc. |
| Collaboration/PM | €20-40K | Jira, Confluence (may have) |
| Training Platforms | €10-30K | LinkedIn Learning, Pluralsight |
| Other | €50-100K | Miscellaneous tools |

Total Platforms Year 1: €330-870K (mid-point: ~€600K)

Note: You already have Databricks + Power BI = €200-400K savings vs. base blueprint

Training & Development (€200-400K):

External training (maritime systems, cloud, AI): €80-150K

Certifications (architecture, cloud, data): €40-80K

Conferences (logistics tech, cloud, data): €40-80K

Online learning: €15-30K

Product Owner training (6 POs): €30-60K

Internal training and workshops: €20-50K

Consulting & Advisory (€150-350K):

Architecture advisory (maritime/logistics expertise): €60-150K

Change management consulting: €40-100K

Integration platform implementation support: €30-80K

Executive coaching (for new POs, CTO): €20-50K

Note: Maritime/logistics domain consulting may be needed for architecture decisions specific to your industry

Project Management for Legacy Replacements (€100-200K):

2 Project Managers for Shipping/Ports system replacements

Either contractors or internal (included in headcount above if internal)

If contractors: €100-200K

Contingency (€150-300K):

10-15% of total budget

YEAR 1 TOTAL: €2.1-4.4M
Mid-Point/Recommended: €2.8-3.2M

Compare to base blueprint: €3.0-4.5M
Your savings: €500K-1.2M (Databricks, Power BI, existing BPM team, existing integration team)

### Year 2 Budget (€2.2-4.0M)

Additional Headcount (€900K-1.8M):

Security Architect (Month 9, partial year): €50-65K

Solution Architects (1-2 more): €95-250K

Business Analysts (2-3): €140-270K

Data Scientists (2-3): €170-345K ⭐

ML Engineers (2): €170-230K ⭐

Integration Engineers (2-3 more): €150-285K

Product Owners (1-2 more for remaining teams): €85-220K

Support Engineers (2-3): €120-195K

Platforms (€600K-1.2M):

Full year operations + expansion

ML platform full deployment

Additional integrations and capabilities

Training (€200-400K):

Ongoing development

AI/ML training

Maritime/logistics domain training

Consulting (€50-150K):

Reduced from Year 1

Specific expertise as needed

Contingency (€150-300K)

YEAR 2 TOTAL: €2.1-4.0M
Mid-Point: €2.9M

### 3-Year Total Investment

Total 3-Year: €8-12M
Mid-Point: €10M

Compare to base blueprint: €11-15M
Your savings: €2-5M (due to existing capabilities: Databricks, Power BI, BPM team, integration team)

### 3-Year ROI - Logistics Specific

Value Delivered (Conservative Estimates):

Year 1 (€3.5-4.5M):

Integration platform savings: €300K (faster delivery, reduced effort)

Vendor optimization: €150K (SaaS consolidation)

Improved delivery speed: €2M (business value enabled)

EDI onboarding faster: €500K (customer satisfaction, revenue protection)

Databricks analytics: €500K (better decisions)

Total Year 1: €3.5-4.5M

Year 2 (€8-10M):

All Year 1 benefits continue and grow: €5-6M

AI models (pricing, predictive maintenance): €2-3M

New systems efficiency: €1-2M (Shipping, Ports systems better than legacy)

Data-driven improvements: €1M

Total Year 2: €9-12M

Year 3 (€13-16M/year ongoing):

All Year 2 benefits scaled: €10-12M

Additional AI models: €2-3M

Continuous improvement: €1M

Total Year 3+: €13-16M/year

3-Year Cumulative Value: €25-32M

3-Year Investment: €10M (mid-point)

3-Year ROI: 150-220%
Payback Period: 16-20 months

## Quick Wins - Logistics Specific

Month 2-4: Vendor Consolidation

Identify duplicate logistics software (TMS, tracking, EDI tools)

Target: €100-150K annual savings

Communication: "SaaS consolidation saves €120K/year"

Month 4-6: Integration Platform Early Win

Migrate 3-5 customer EDI integrations to platform

Show: 60% faster onboarding time

Customer satisfaction improved

Communication: "Integration platform delivers customer EDI in days, not weeks"

Month 5-7: Databricks Dashboard Quick Win

Executive dashboard: Revenue, volume, KPIs by BU (Shipping, Ports, Cargo)

Operational dashboard: Vessel tracking OR terminal throughput

Communication: "Data platform delivers insights in hours, not weeks"

Month 6-9: Support Model Improvement

Application Support team reduces developer interruptions

Developers free up 20% capacity

Value: ~€300-400K capacity returned to development

Communication: "New support model frees developers to build new capabilities"

Month 8-12: Architecture Prevents Costly Mistake

EA catches team about to make poor vendor choice or architecture decision

Calculate avoided cost (€300-500K)

Communication: "Architecture review saved €400K on avoided mistake"

Total Quick Wins (First Year): €800K-1.2M value delivered/saved

## Risks Specific to Your Context

### Risk 1: Legacy System Replacement Delays

Probability: Medium-High
Impact: High

Why This is a Risk:

Shipping and Ports systems are business-critical

Implementations are complex (18-24 months)

Vendor dependencies

Data migration complexity

User adoption challenges

Mitigation:

Strong project governance (PM + PO + Steering Committee)

Architecture Review Board oversight

Experienced implementation partner

Phased go-live approach

Extensive UAT and training

Fallback plans if issues arise

Contingency:

If delayed: Adjust transformation timeline

Legacy system kept operational longer

Interim improvements to legacy if needed

Clear communication to business about delays

### Risk 2: EDI Integration Complexity Underestimated

Probability: Medium
Impact: Medium-High

Why This is a Risk:

You likely have 100+ EDI partners

Each with unique requirements

Message variants and customizations

Customs regulations vary by country

High reliability required (customer-facing)

Mitigation:

Integration Architect dedicated to EDI

EDI Specialists on integration platform team (2-3 people)

Thorough assessment of current EDI landscape (Month 2-3)

Integration platform with strong EDI capabilities (MuleSoft, Boomi)

Phased migration (don't migrate all at once)

Test harnesses for EDI

Customer communication and coordination

### Risk 3: Maritime Domain Expertise Shortage

Probability: Medium
Impact: Medium

Why This is a Risk:

Maritime/logistics is specialized domain

Not all architects or developers have shipping/ports knowledge

Business jargon and processes unique

Regulatory requirements (IMO, SOLAS, ISPS, customs)

Mitigation:

Maritime/Logistics Architect role - critical hire with domain expertise

Preference for hiring people with maritime/logistics background when possible

Domain training for all IT staff (shipping operations 101, terminal operations 101)

Product Owners from business (domain experts)

Business Analysts with domain knowledge

Partnerships with maritime technology vendors (knowledge transfer)

### Risk 4: Three BUs with Competing Priorities

Probability: High
Impact: Medium-High

Why This is a Risk:

Shipping, Ports, Cargo have different business models and priorities

Shared resources (Integration Platform, Data Platform, some applications)

Each BU wants their initiatives prioritized

Political complexity

Mitigation:

Strong Portfolio Management function

IT Portfolio Review Board with clear prioritization criteria

Executive Portfolio Committee (CEO, 3 BU Heads, CTO, CFO) decides major conflicts

Transparent decision-making with clear rationale

Some dedicated resources per BU (stream-aligned teams)

Quarterly alignment sessions with all BU heads

### Risk 5: 24/7 Operations Complexity

Probability: Medium
Impact: Medium

Why This is a Risk:

Shipping and Ports operate 24/7 (vessels don't stop for system maintenance)

Deployments must be carefully planned

Support must be available around the clock

Downtime extremely costly

Mitigation:

Blue-green deployments (zero-downtime releases)

Careful change management windows

24/7 Application Support team (follow-the-sun or on-call)

Comprehensive monitoring and alerting

Incident response procedures

High availability architecture (cloud, redundancy)

### Risk 6: Data Quality in Legacy Systems

Probability: High
Impact: Medium-High

Why This is a Risk:

Legacy Shipping/Ports system likely has data quality issues

Years of workarounds and manual data entry

Inconsistent data across systems

Data migration to new systems will surface issues

AI models require high-quality data

Mitigation:

Data quality assessment early (Month 3-4)

Data cleansing initiatives before migration

Data Architect focused on data quality

Data quality monitoring in Databricks

Master Data Management approach

Don't promise AI until data ready (be realistic about timeline)

## Your Transformation Success Factors

What Will Make This Succeed:

Legacy System Replacement as Catalyst

  - Perfect timing to introduce Product Owner model

  - New systems = clean start with good architecture

  - Business invested in success

Product Owners from Business Units

  - Shipping PO from Shipping operations

  - Ports PO from Ports operations

  - Cargo PO from Cargo operations

  - Domain expertise and business credibility

Integration Platform ROI

  - High volume of integrations = high ROI

  - EDI complexity = platform value clear

  - Quick wins possible

Databricks Already Exists

  - Data platform head start (6-12 months ahead)

  - Can start AI earlier than typical transformation

  - Cost savings vs. building from scratch

BPM Team Transition

  - Existing intake and prioritization capability

  - Just needs evolution, not creation

  - People skilled in business analysis

Maritime Domain Focus

  - Maritime/Logistics Architect brings domain expertise

  - EDI Specialists understand shipping/logistics patterns

  - POs from business bring operational knowledge

Internal Promotion

  - Promoting Head of IT Applications to CTO

  - Credibility with team and business

  - Knows the company and culture

  - Cultural fit with values (entrepreneurship, flexibility)

## Your First Email to CEO

Subject: IT Transformation Proposal - Strategic Discussion Requested

Dear [CEO Name],

I'd like to discuss a strategic IT transformation that will position us to support our business growth and digital future.

Context: As we replace our legacy Shipping and Ports systems and implement new capabilities (TMS, SAP HRIS), we have a unique opportunity to fundamentally transform how IT delivers value to our three business units.

The Opportunity:

Faster delivery of technology capabilities (50% reduction in time-to-market)

Dedicated IT partners for Shipping, Ports, and Cargo (Product Owner model)

Modern integration platform (streamline our 100+ EDI integrations)

AI-powered insights and automation (dynamic pricing, predictive maintenance, demand forecasting)

€10M+ business value over 3 years

The Approach:

24-month phased transformation

Pilot teams first, scale gradually

Merge BPM and IT Applications into unified organization

Architecture and data foundations

€2.8M investment Year 1, ROI 150%+ over 3 years

Next Step: I'd appreciate 90 minutes to walk through the detailed plan, business case, and how this aligns with our strategic priorities for Shipping, Ports, and Cargo.

What I Need from You:

Your sponsorship and support

Approval to proceed with Year 1 budget (€2.8M)

Support for organizational changes (BPM merge, Product Owner model)

Your voice in communicating this to the organization

This transformation will enable us to move faster, deliver more value, and compete effectively in an increasingly digital logistics industry.

Can we schedule time next week to discuss?

Best regards,
[Your Name]

## Success Story: Customer EDI Onboarding - From 6 Weeks to 3 Days

Team: EDI & Integration Platform Team
Date: Month 8
Category: Quick Win

### The Challenge

Onboarding new customers for EDI integration was taking 6-8 weeks, causing:

Delayed customer go-live and revenue

Customer frustration and competitive disadvantage

High manual effort (60+ hours per customer)

Error-prone manual EDI mapping

### The Solution

Integration Platform Team created:

Reusable EDIFACT message templates (IFTMIN, IFTSTA, IFCSUM)

Self-service EDI onboarding portal

Automated testing and validation

Standard connector for Shipping system

Customer onboarding process:

Customer registers in portal (30 min)

System generates EDI configuration (automated)

Customer tests with sample messages (2 hours)

Integration Platform team reviews and approves (4 hours)

Go-live (next business day)

### The Results

Business Impact:

Customer onboarding time: 6 weeks → 3 days (95% reduction)

Customer satisfaction: Significantly improved

Competitive advantage: Fastest EDI onboarding in industry

Revenue impact: Earlier customer go-live = earlier revenue

Operational Impact:

Manual effort: 60 hours → 6 hours per customer (90% reduction)

Error rate: 30% → 5% (better quality)

Team capacity freed for other integrations

Metrics:

Customers onboarded: 12 in 3 months (vs. 4 previously)

Cost savings: €150K/year (reduced manual effort)

Customer NPS improved: +15 points

### What We Learned

Standardization is key (templates enable self-service)

Self-service empowers customers and frees team capacity

Automated testing catches issues early

Good documentation essential for self-service success

### Replicability

Other platform teams can apply:

Create reusable templates/connectors for common patterns

Build self-service portals with clear guidance

Automate testing and validation

Invest in documentation

Pattern now used for: Carrier integrations, Port Community Systems, Customs EDI

## Success Story Example 2: Dynamic Freight Pricing AI Model

Team: Data & AI Team + Shipping Business Solutions Team
Date: Month 18
Category: AI Innovation

### The Challenge

Freight pricing was manual and reactive:

Pricing based on gut feel and historical rates

Missed optimization opportunities (leaving money on table)

Slow to respond to market changes

No systematic approach to demand/capacity pricing

Impact: Estimated €2-3M annual revenue opportunity missed

### The Solution

Data Scientists built dynamic pricing ML model:

Features (20+ variables):

Route characteristics (lane, distance, port pair)

Demand indicators (booking velocity, seasonal patterns)

Capacity (vessel utilization, available TEUs)

Competition (market rates from rate platforms)

Fuel costs and bunker prices

Customer segment and history

Port congestion indicators

Model: Gradient Boosting (LightGBM)

Trained on 3 years historical bookings (500K+ data points)

Predicts optimal rate to maximize revenue while maintaining competitiveness

Recommendations updated daily

Implementation:

Integrated into Shipping system

Pricing team sees recommended rates

Override capability maintained (human in the loop)

A/B testing: 20% of routes use AI, 80% manual (Month 17)

Full rollout after validation (Month 18)

### The Results

Business Impact:

Revenue increase: +3.2% on AI-priced routes

Utilization improved: +2% (better demand capture)

Annualized revenue impact: €2.1M

Pricing team efficiency: 40% time saved (automated pricing decisions)

Model Performance:

Accuracy: 92% (predicted vs. actual booking rate)

Adoption: Pricing team uses recommendations 85% of time

Override rate: 15% (mostly for strategic accounts)

Market Response:

Customer booking conversion improved 8%

Competitive win rate improved 12%

### What We Learned

Domain expertise critical (Shipping PO and pricing team input essential)

Start with pilot routes, prove value, then scale

Human-in-the-loop builds trust and handles edge cases

Model needs continuous retraining (market conditions change)

Data quality was biggest challenge (18 months to prepare data)

## Next Steps

Expand to all routes (Month 19-20)

Add more sophisticated features (weather, geopolitics, trade flows)

Real-time pricing adjustments (currently daily)

Similar model for Ports tariff optimization

ROI: €2.1M annual revenue vs. €180K development cost = 1,067% ROI

## Final Checklist - Ready to Start?

Before You Begin (Pre-Month 1):

Strategic Readiness:

[ ] You've read and internalized this entire plan

[ ] CEO supportive and willing to sponsor

[ ] CFO willing to allocate budget (€2.8M Year 1)

[ ] 3 BU Heads willing to provide Product Owners

[ ] You're committed to 24-month transformation journey

Organizational Readiness:

[ ] Head of IT Applications ready to step into CTO role

[ ] BPM Manager willing to evolve to Portfolio Management head

[ ] Operations Manager willing to evolve role

[ ] Head of Data ready for elevated role

[ ] Integration team ready to become platform team

Personal Readiness:

[ ] You have executive recruiter relationship (for EA hire)

[ ] You have 10-15 hours/week for transformation leadership

[ ] You're ready for resistance and challenges

[ ] You have support system (mentor, peer CTO, consultant)

Knowledge Readiness:

[ ] Read "The Phoenix Project" (or will this month)

[ ] Read "Team Topologies" Part 1 (or will in Month 1-2)

[ ] Understand Product Owner concept

[ ] Understand stream-aligned teams concept

If you checked 80%+ of these boxes, you're ready to start!

## Your Transformation Starts Now

You have everything you need:

✅ Complete blueprint customized for logistics industry

✅ Shipping, Ports, Cargo business unit structure

✅ Maritime/logistics specific roles and architecture

✅ EDI and integration platform focus (your highest ROI)

✅ Databricks/Power BI leverage (12-month head start)

✅ Legacy system replacement integration

✅ 24-month detailed roadmap

✅ First 30 days action plan

✅ Budget (€10M over 3 years, 150-220% ROI)

✅ Risks identified and mitigated

✅ Success metrics defined

✅ Communication templates

✅ Job descriptions

✅ Everything you need to execute

Your next action: This week, Day 1:

Block 2 hours on your calendar

Review this plan one more time

Make notes on what to customize further

Schedule meeting with CEO for next week: "Strategic IT Transformation Discussion"

Then: Follow the 30-day action plan, day by day.

## You've Got This! 🚀

This transformation will:

Modernize your IT organization for the digital logistics era

Enable Shipping, Ports, and Cargo BUs to move faster

Deliver AI-powered insights and automation

Position you competitively in logistics technology

Transform IT from cost center to strategic partner

In 24 months, you'll look back and see:

New Shipping and Ports systems operational

AI models driving business value (€3-5M/year)

Integration platform powering 30+ integrations seamlessly

Product Owners as trusted business partners

Teams empowered, engaged, and delivering

Data-driven culture across the organization

Your values (flexibility, entrepreneurship, agility, lean, robustness) embodied in how IT works

You're about to lead one of the most important transformations in your company's digital journey.

Now go make it happen. The logistics industry is waiting for your innovation. ⚓🚢📦

You have the blueprint. Trust the process. Adapt where needed. Execute with discipline.

Good luck! You're ready. 🎯

# Additional topics explained/added

## Question 1: Stream-Aligned Team Structure - Domain Boundaries

This is the most complex question because getting team boundaries right is foundational. Let me analyze each area:

### Current State Analysis - Your Systems Landscape

Based on what you've described, you have:

Shipping Domain:

- Legacy Shipping Tool A (from merger, part of business)

- Legacy Shipping Tool B + Port functionalities (majority of business)

- Future: Single new Shipping System (consolidating both)

Ports Domain:

- Cars operations

- Cargo - Containers

- Cargo - Trailers

- Terminal equipment/maintenance/workshops tool

Cross-Cutting:

- Customs (touches Shipping AND Ports)

- Sales/Commercial (separate in 3 business units)

- Fleet Management (vessel fleet tool)

- Claims tool

### Recommended Stream-Aligned Team Structure

#### Option A: Recommended Structure (7-8 Teams)

STREAM-ALIGNED TEAMS (Domain-Based)

1. SHIPPING SOLUTIONS TEAM (12-15 people)

├─ Product Owner: Head of Shipping Operations (50%)

├─ Business Analysts: 2 (Shipping domain specialists)

├─ Developers: 8-10

├─ QA: 1-2

│

├─ Scope:

│   ├─ Current: Legacy Shipping Tool A + B

│   ├─ Future: New unified Shipping System

│   ├─ Integrations: EDI booking, tracking, documentation

│   └─ INCLUDES: Fleet Management Tool ⭐

│

└─ Rationale:

• Fleet management is SHIPPING domain knowledge

• Same users (shipping operations teams)

• Natural fit with booking/vessel operations

• Small tool, doesn't warrant separate team

2. PORTS - CARS TEAM (10-12 people)

├─ Product Owner: Head of Cars Operations (50%)

├─ Business Analysts: 1-2 (Cars + port ops specialists)

├─ Developers: 6-8

├─ QA: 1-2

│

├─ Scope:

│   ├─ Cars port operations system

│   ├─ Cars terminal management

│   ├─ Cars inventory and tracking

│   ├─ INCLUDES: Terminal Equipment/Workshop Tool (for cars terminals) ⭐

│   └─ Customs (cars-specific) - see customs discussion below

│

└─ Rationale:

• Cars is distinct domain (different operations, customers, processes)

• Enough complexity to warrant dedicated team

• Cars business has own COO/leadership

3. PORTS - CONTAINERS & TRAILERS TEAM (10-12 people)

├─ Product Owner: Head of Container/Trailer Operations (50%)

├─ Business Analysts: 1-2 (Container/trailer specialists)

├─ Developers: 6-8

├─ QA: 1-2

│

├─ Scope:

│   ├─ Container terminal operations

│   ├─ Trailer operations

│   ├─ Container/trailer tracking

│   ├─ INCLUDES: Terminal Equipment/Workshop Tool (for container terminals) ⭐

│   └─ Customs (container/trailer-specific) - see customs discussion below

│

└─ Rationale:

• Containers and trailers have similar operations (cargo handling vs. cars)

• Combined: Enough work for full team

• Natural grouping

4. CUSTOMS & COMPLIANCE SOLUTIONS TEAM ⭐ (8-10 people)

├─ Product Owner: Head of Customs/Compliance (50%)

│   OR Senior Customs Manager if no head-level person

├─ Business Analysts: 1-2 (Customs/compliance specialists)

├─ Developers: 5-7

├─ QA: 1

│

├─ Scope:

│   ├─ Customs declarations (AES, AMS, ENS, ICS2, etc.)

│   ├─ Compliance systems (sanctions screening, licensing)

│   ├─ Regulatory reporting

│   ├─ Integrations: Customs authorities, port communities

│   ├─ SERVES: Shipping team + Ports teams (shared service)

│

└─ Rationale for SEPARATE team:

• Highly specialized domain knowledge (customs regulations complex)

• Significant development volume (regulatory changes constant)

• Cross-cutting (touches shipping AND ports)

• Dedicated focus needed (compliance risk too high for divided attention)

• Career path for customs specialists (rare skills, need to retain)

5. CUSTOMER & COMMERCIAL SOLUTIONS TEAM (10-12 people)

├─ Product Owner: Chief Commercial Officer or Head of Sales (50%)

│   OR rotate among 3 BU COOs quarterly (if no single CCO)

├─ Business Analysts: 2 (Commercial/sales specialists)

├─ Developers: 6-8

├─ QA: 1-2

│

├─ Scope:

│   ├─ CRM (Salesforce or equivalent)

│   ├─ Sales processes and tools

│   ├─ Customer portal

│   ├─ Quotations and pricing

│   ├─ Contract management

│   ├─ INCLUDES: Claims Tool ⭐

│   ├─ SERVES: All 3 business units (Cars, Containers/Trailers, Shipping)

│

└─ Rationale for COMBINED team:

• Sales processes have commonalities across BUs (quote, contract, close)

• CRM is shared platform (Salesforce serves all BUs)

• Customer-facing capabilities benefit from consistency

• Separating by BU creates silos and duplicate work

• Claims tool is small, fits naturally here (commercial/customer-facing)

• PO challenge: See detailed solution below ⭐

6. CARGO & TRANSPORT MANAGEMENT TEAM (10-12 people)

├─ Product Owner: Head of Cargo Operations (50%)

├─ Business Analysts: 1-2 (TMS specialists)

├─ Developers: 6-8

├─ QA: 1-2

│

├─ Scope:

│   ├─ TMS (Transportation Management System)

│   ├─ Haulage operations

│   ├─ Inland transport

│   ├─ Multimodal operations

│   └─ Track & trace

│

└─ Rationale:

• Distinct domain (inland vs. port operations)

• Enough complexity for dedicated team

7. BILLING & FINANCE SOLUTIONS TEAM (8-10 people)

├─ Product Owner: CFO or Finance Director (50%)

├─ Business Analysts: 1-2 (Finance/billing specialists)

├─ Developers: 5-7

├─ QA: 1

│

├─ Scope:

│   ├─ Invoicing and billing systems

│   ├─ Financial integrations (ERP)

│   ├─ Revenue recognition

│   ├─ Financial reporting

│   └─ Credit management

│

└─ Rationale:

• Financial systems critical and complex

• Dedicated focus needed

8. HR & WORKFORCE SOLUTIONS TEAM (6-8 people)

├─ Product Owner: CHRO or HR Director (50%)

├─ Business Analysts: 1

├─ Developers: 4-5

├─ QA: 1

│

├─ Scope:

│   ├─ HRIS (SAP HR or equivalent)

│   ├─ Payroll systems

│   ├─ Workforce management

│   ├─ Time & attendance

│   └─ Employee portal

│

└─ Rationale:

• HR systems serve entire organization

• Smaller team (less development volume than operational systems)

TOTAL: 8 Stream-Aligned Teams, 68-83 people

### Deep Dive: Customs - Separate Team or Embedded?

Decision: SEPARATE Customs Team (Recommended) ⭐

Rationale for Separate Team:

✅ Highly Specialized Domain:

- Customs regulations are complex, change frequently, vary by country

- Requires deep expertise (customs brokers, compliance specialists)

- Mistakes = Major consequences (fines, shipment holds, license revocation)

- Career path: Customs IT specialists are rare, need dedicated focus to retain talent

✅ Significant Development Volume:

- Regulatory changes: ICS2, Brexit, US CBP rules, EU Customs Code updates (constant)

- New country requirements (expanding to new markets = new customs declarations)

- Integration complexity (customs authorities, port community systems, different protocols)

- My estimate: 8-10 people needed full-time just for customs/compliance

✅ Cross-Cutting Nature:

- Touches Shipping (export declarations, bills of lading)

- Touches Ports - Cars (vehicle imports/exports, VIN reporting)

- Touches Ports - Containers/Trailers (container security, cargo manifests)

- Better as shared service than duplicated across 3 teams

✅ Risk Management:

- Compliance failures = business-critical risk

- Dedicated team = Clear accountability, focused expertise

- Embedded in multiple teams = Diluted focus, coordination challenges

Alternative (NOT Recommended): Embedded Model:

Customs embedded in each team:

├─ Shipping Team: 2-3 developers for shipping customs

├─ Ports Cars Team: 2-3 developers for cars customs

├─ Ports Containers Team: 2-3 developers for container customs

└─ Problems:

├─ Duplicate work (same customs authority integrations built 3 times)

├─ Inconsistent quality (customs expertise diluted)

├─ Coordination overhead (who owns customs platform?)

└─ Career path unclear (customs specialists isolated in different teams)

If you're hesitant about separate Customs team, compromise approach:

Option B: Start Embedded, Extract Later:

- Month 1-6: Customs developers embedded in Shipping and Ports teams

- Month 6: Review customs development volume and complexity

- Month 7-12: If significant (which I expect), extract to separate Customs team

- Transition: Move customs developers from 3 teams into dedicated Customs team

My strong recommendation: Start with separate Customs team (saves reorganization pain later)

### Deep Dive: Sales/Commercial - Separate Team or Embedded?

Decision: COMBINED Customer & Commercial Team (Recommended) ⭐

Rationale for Combined Team:

✅ Shared Systems:

- CRM (Salesforce) serves ALL business units

- Customer portal is unified (customers see all services)

- Pricing/quoting has common logic (even if rates differ by BU)

- Contract management platform is shared

✅ Process Commonalities:

- Sales process stages: Lead → Opportunity → Quote → Contract → Customer (similar across BUs)

- Commercial analytics and reporting: Common KPIs (revenue, margin, customer acquisition)

- Customer service: Better if consistent experience across all BUs

✅ Avoid Silos:

- If 3 separate commercial teams (one per BU):

  - Duplicate CRM customizations (Cars sales team builds feature, Containers team builds same feature independently)

  - Inconsistent customer experience (customer buying cars AND containers gets two different portals)

  - Coordination overhead (changes to shared CRM require 3 teams to coordinate)

✅ Right-Sized:

- Combined: 10-12 people (full productive team)

- Separate: 3 teams of 3-4 people each (too small, unproductive)

Challenge: Product Owner for Combined Commercial Team:

The challenge you identified is real: 3 BUs have separate COOs, who owns Commercial PO?

Solution 1: Chief Commercial Officer as PO (Ideal):

IF you have CCO (or equivalent):

├─ CCO is natural PO (owns commercial strategy across all BUs)

├─ CCO prioritizes work based on overall commercial impact

├─ BU COOs provide input (requirements, priorities for their BU)

└─ Works well: Single decision-maker, clear accountability

Solution 2: Rotating PO Among 3 BU COOs (If No CCO):

IF no CCO:

├─ Rotate PO role quarterly among 3 BU COOs

├─ Q1: Cars COO is PO

├─ Q2: Containers/Trailers COO is PO

├─ Q3: Shipping COO is PO

├─ Q4: Cars COO is PO (cycle repeats)

│

Process:

├─ Each COO (when PO): Prioritizes entire backlog (not just their BU)

├─ Coordination: Monthly meeting with all 3 COOs (alignment on priorities)

├─ Benefit: Each BU gets focused attention 3 months/year

└─ Challenge: Context switching every quarter (manageable with good BA support)

Solution 3: Dedicated Commercial Product Manager (Alternative):

Hire dedicated Commercial Product Manager (full-time):

├─ Reports to: CEO or COO (above BU level)

├─ Role: Full-time PO for Customer & Commercial Solutions Team

├─ Works with: All 3 BU COOs (gathers requirements, aligns priorities)

├─ Benefit: Continuity, dedicated focus, no part-time challenge

├─ Cost: 1 FTE (€100-120K) but saves 3 COOs time

└─ Recommended IF: Commercial systems have high development volume

My Recommendation:

- Start with Solution 2 (Rotating PO) → Low cost, tests if model works

- After 6-9 months, evaluate:

  - If working well: Continue rotating PO ✅

  - If too much coordination overhead: Move to Solution 3 (dedicated Commercial PM)

### Deep Dive: Small Tools - Where to Place?

Fleet Management Tool:

- Recommendation: Shipping Solutions Team ✅

- Rationale: Fleet = vessels, vessels = shipping operations, same users, natural fit

- Size: Small tool, doesn't justify separate team

Terminal Equipment/Maintenance/Workshop Tool:

- Recommendation: Split by terminal type ✅

  - Cars terminals: Cars Team handles

  - Container/trailer terminals: Containers & Trailers Team handles

- Rationale: Terminal equipment is port-specific, different equipment for cars vs. containers

- If tool is unified (same platform for all terminals):

  - Alternative: One team owns platform (e.g., Ports - Containers Team)

  - Other teams (Cars) consume platform, submit requests

  - Avoids duplicate development

Claims Tool:

- Recommendation: Customer & Commercial Solutions Team ✅

- Rationale: Claims = customer-facing, commercial process (dispute resolution, refunds)

- Size: Small tool, fits naturally with customer service capabilities

### Handling Legacy Systems During Transition

Current: 2 Legacy Shipping Tools

Transition Strategy:

Phase 1: Current State (Month 1-12):

Shipping Solutions Team manages:

├─ Legacy Shipping Tool A (merger legacy)

│   ├─ Maintenance only (no new features)

│   ├─ 2-3 developers maintaining

│

├─ Legacy Shipping Tool B + Port functionalities

│   ├─ Maintenance + limited enhancements

│   ├─ 4-5 developers maintaining

│

└─ New Shipping System implementation

├─ Business Analyst: Requirements for new system

├─ 3-5 developers: Configuration, customization, integration

└─ Parallel run: Old and new systems coexist

Phase 2: Migration (Month 13-24):

Shipping Solutions Team:

├─ Migrate users from Legacy Tool A → New System

├─ Migrate users from Legacy Tool B → New System

├─ Developers: Data migration, user training, cutover

└─ Sunset legacy tools (decommission after migration complete)

Phase 3: Steady State (Month 25+):

Shipping Solutions Team:

├─ Single new Shipping System only

├─ Full team focus on enhancements and optimization

├─ No more legacy maintenance (freed capacity)

└─ 8-10 developers fully productive on single platform

During Transition (Month 1-24):

- Team Size: Temporarily larger (15-18 people) to handle:

  - Legacy maintenance (4-5)

  - New system implementation (6-8)

  - Migration work (3-4)

- After Transition (Month 25+):

  - Team Size: Normal (12-15 people)

  - Freed capacity: 3-5 developers redeployed or headcount reduced

### Summary: Recommended Stream-Aligned Teams

Final Structure (8 Teams, 68-83 people):

| # | Team Name | Size | Product Owner | Key Systems |
| --- | --- | --- | --- | --- |
| 1 | Shipping Solutions | 12-15 | Head of Shipping Ops (50%) | Shipping systems + Fleet Management |
| 2 | Ports - Cars | 10-12 | Head of Cars Ops (50%) | Cars port systems + Terminal Equipment (cars) |
| 3 | Ports - Containers & Trailers | 10-12 | Head of Container Ops (50%) | Container/trailer systems + Terminal Equipment (containers) |
| 4 | Customs & Compliance ⭐ | 8-10 | Head of Customs (50%) | Customs declarations, compliance |
| 5 | Customer & Commercial ⭐ | 10-12 | CCO (50%) or Rotating BU COOs | CRM, Sales, Customer Portal, Claims |
| 6 | Cargo & Transport | 10-12 | Head of Cargo Ops (50%) | TMS, haulage, inland transport |
| 7 | Billing & Finance | 8-10 | CFO (50%) | Invoicing, billing, ERP integration |
| 8 | HR & Workforce | 6-8 | CHRO (50%) | HRIS, payroll, workforce management |

Total: 68-83 people in stream-aligned teams

### Decision Matrix: When to Create Separate Team vs. Embed

Use this framework for future decisions:

SEPARATE TEAM if:

✅ Distinct domain (different business operations, customers, processes)

✅ Significant work volume (8+ people needed full-time)

✅ Specialized expertise required (rare skills, deep domain knowledge)

✅ High risk/compliance needs (dedicated focus required)

✅ Cross-cutting across multiple other teams (shared service model better)

EMBED IN EXISTING TEAM if:

✅ Small tool (1-2 developers sufficient)

✅ Closely related domain (same users, same business context)

✅ Limited ongoing work (mostly maintenance, few new features)

✅ Can leverage existing team expertise (no specialized knowledge needed)

EXAMPLES:

• Customs: SEPARATE (specialized, high volume, cross-cutting, high risk) ✅

• Fleet Management: EMBED in Shipping (small, same users, related domain) ✅

• Claims: EMBED in Commercial (small, customer-facing, fits naturally) ✅

• Terminal Equipment: SPLIT between Cars and Containers teams (domain-specific) ✅

## Question 2: Vendor and Partner Management - Organization Chart Placement

Answer: Vendor & Partner Management is Separate from IT Applications

### Recommended Structure

CEO

│

├─ CTO (promoted from Head of IT Applications)

│   │

│   ├─ Head of Business Solutions & Delivery (your focus)

│   │   └─ [Stream teams, BAs, Portfolio Management]

│   │

│   ├─ Head of Enterprise Architecture

│   ├─ Head of Data & AI

│   ├─ Head of Platform Engineering

│   │   └─ [Integration Platform, DevOps, Application Support]

│   │

│   └─ Head of Vendor & Partner Management ⭐ NEW

│       ├─ Vendor Managers (3-5)

│       ├─ Contract Managers (1-2)

│       └─ Partner Relationship Managers (1-2)

│

└─ Head of IT Systems (Infrastructure, separate from Applications)

└─ [Networks, servers, security infrastructure]

### Why Vendor & Partner Management Reports to CTO

Rationale:

✅ Cross-Cutting Function:

- Vendor Management serves ALL IT departments:

  - Business Solutions (application vendors: Shipping system, TMS, CRM)

  - Platform Engineering (integration vendors: MuleSoft, monitoring tools)

  - Data & AI (data platform vendors: Snowflake, Databricks)

  - IT Systems (infrastructure vendors: AWS, Microsoft)

- Reporting to CTO = Neutral, serves entire IT organization

✅ Strategic Function:

- Vendor relationships are strategic (multi-year contracts, significant spend)

- CTO-level oversight ensures alignment with overall IT strategy

- Too important to be buried deep in organization chart

✅ Commercial/Contract Focus:

- Vendor Management is primarily commercial (negotiations, contracts, SLAs)

- Different skill set than technical delivery (Business Solutions)

- Natural separation: Technical teams build, Vendor Management manages vendors

### Vendor & Partner Management Team Structure

Team Size: 6-9 people (for your organization)

Roles:

#### Head of Vendor & Partner Management (1 person)

- Reports To: CTO

- Salary: €90-110K

- Responsibilities:

  - Overall vendor strategy and governance

  - Executive vendor relationships (C-level contacts)

  - Contract negotiations (major renewals)

  - Vendor portfolio optimization (rationalize vendors, reduce costs)

  - Risk management (vendor dependencies, exit strategies)

#### Vendor Managers (3-5 people, domain-specialized)

- Salary: €70-90K each

- Specialization:

1. Application Vendor Manager (1-2 people):

- Scope:

  - Shipping system vendor

  - Ports system vendor

  - TMS vendor

  - CRM vendor (Salesforce)

  - Other business applications

- Responsibilities:

  - Day-to-day relationship management

  - SLA monitoring and enforcement

  - Quarterly Business Reviews with vendors

  - Escalations from Application Support team

  - Roadmap discussions (vendor's product direction vs. our needs)

  - License optimization

2. Platform & Infrastructure Vendor Manager (1 person):

- Scope:

  - Integration platform vendor (MuleSoft/Boomi)

  - Cloud vendors (AWS/Azure)

  - Database vendors

  - Monitoring tools (Datadog, New Relic)

  - DevOps tools

- Responsibilities:

  - Platform vendor relationships

  - Infrastructure vendor relationships

  - SLA governance

  - Cost optimization (cloud spend, licensing)

3. Data & Analytics Vendor Manager (1 person):

- Scope:

  - Data platform vendors (Snowflake, Databricks)

  - BI tools (Power BI, Tableau)

  - Data integration tools

  - Analytics vendors

- Responsibilities:

  - Data platform vendor management

  - License optimization (data platform costs can be high)

  - SLA management

4. Strategic Partner Manager (1 person, optional but recommended for logistics):

- Scope:

  - Maritime technology partners (CargoWise, Navis, etc.)

  - Port community system integrations

  - Carrier EDI partnerships

  - Customs authority relationships

- Responsibilities:

  - Strategic partnership development

  - Industry consortium participation

  - Partner ecosystem management

  - Co-innovation initiatives

#### Contract Managers (1-2 people)

- Salary: €60-75K each

- Responsibilities:

  - Contract administration and tracking

  - Renewal management (ensure renewals happen on time)

  - Contract compliance (are we using what we're paying for?)

  - License audits

  - Procurement coordination

  - Contract repository management

### Vendor Management Operating Model

Quarterly Cycle:

VENDOR MANAGEMENT ACTIVITIES

MONTHLY:

├─ Vendor SLA Reviews (each Vendor Manager)

│   ├─ Review vendor performance data (from Application Support)

│   ├─ Track SLA compliance

│   └─ Escalate issues to vendor if needed

│

├─ Contract Renewals (Contract Managers)

│   ├─ Identify contracts renewing in next 90 days

│   ├─ Initiate renewal negotiations

│   └─ Coordinate with finance (budget approval)

│

└─ Vendor Spend Review (Head of Vendor Mgmt)

├─ Review vendor spend month-to-date

├─ Identify cost optimization opportunities

└─ Report to CTO and CFO

QUARTERLY:

├─ Quarterly Business Reviews (Vendor Managers)

│   ├─ Meet with each major vendor (account team)

│   ├─ Review: Service quality, SLA compliance, roadmap, issues

│   ├─ Plan next quarter priorities

│   └─ Document action items

│

├─ Vendor Portfolio Review (Head of Vendor Mgmt)

│   ├─ Review entire vendor portfolio

│   ├─ Identify: Redundant vendors, consolidation opportunities

│   ├─ Evaluate: New vendors to consider

│   └─ Present to CTO (strategic vendor decisions)

│

└─ License Optimization (Contract Managers + Vendor Managers)

├─ Audit: Are we using all licenses we're paying for?

├─ Identify: Unused licenses, over-provisioned services

└─ Action: Reduce spend, reallocate licenses

ANNUALLY:

├─ Major Contract Negotiations (Head + Vendor Managers)

│   ├─ Renew or renegotiate major contracts

│   ├─ Involve: CFO, CTO, relevant IT heads

│   └─ Goal: Optimize pricing, improve SLAs, align roadmaps

│

├─ Vendor Risk Assessment (Head of Vendor Mgmt)

│   ├─ Evaluate: Financial stability, security posture, viability

│   ├─ Identify: High-risk vendors (too dependent, vendor struggling)

│   └─ Plan: Exit strategies, backup vendors

│

└─ Vendor Strategy (Head of Vendor Mgmt + CTO)

├─ Multi-year vendor roadmap

├─ Build vs. buy decisions

├─ Vendor ecosystem strategy

└─ Present to executive team

### Relationship: Vendor Management ↔ Application Support

Clear Boundary (from earlier discussion):

APPLICATION SUPPORT:

├─ Opens vendor support cases (day-to-day)

├─ Monitors vendor case progress

├─ Tracks vendor SLA compliance (operational)

├─ Escalates to Vendor Management when:

│   ├─ Vendor SLA breach

│   ├─ Recurring vendor issues

│   ├─ Vendor unresponsive

│   └─ Major vendor incident (P1)

VENDOR MANAGEMENT:

├─ Receives escalations from Application Support

├─ Engages vendor executive (account manager, VP)

├─ Enforces SLAs (contract penalties if needed)

├─ Manages strategic vendor relationships

├─ Contract negotiations and renewals

└─ Vendor selection and evaluation

COLLABORATION:

├─ Monthly meeting: Application Support Manager + Vendor Managers

│   └─ Review vendor performance, escalations, issues

├─ Quarterly: Support provides data for Vendor QBRs

│   └─ Vendor Manager uses Support data in vendor meetings

└─ Annual: Support provides input for contract renewals

└─ "We need better SLA," "We need dedicated support team," etc.

### Vendor Management in Organization Chart

Full Organization Chart with Vendor Management:

CEO

│

├─ CTO (Head of IT Applications, promoted)

│   │

│   ├─ Head of Business Solutions & Delivery

│   │   ├─ Portfolio & Demand Management (from BPM)

│   │   ├─ 8 Stream-Aligned Teams (60-75 developers)

│   │   └─ BA Center of Excellence (6-7 BAs)

│   │

│   ├─ Head of Enterprise Architecture

│   │   ├─ Enterprise Architect (1)

│   │   ├─ Maritime/Logistics Architect (1)

│   │   ├─ Solution Architects (3-4)

│   │   ├─ Data Architect (1)

│   │   └─ Security Architect (1)

│   │

│   ├─ Head of Data & AI

│   │   ├─ Data Engineers (4-6)

│   │   ├─ Data Scientists (2-3)

│   │   ├─ ML Engineers (2)

│   │   └─ Data Analysts (2-3)

│   │

│   ├─ Head of Platform Engineering

│   │   ├─ Application Support Organization (18-22) ⭐

│   │   │   ├─ Service Desk Manager → Agents (4-6)

│   │   │   └─ Application Support Manager → Engineers (10-12)

│   │   │

│   │   ├─ Integration Platform Team (12-15)

│   │   └─ DevOps & Infrastructure Team (6-8)

│   │

│   └─ Head of Vendor & Partner Management ⭐ (6-9 people)

│       ├─ Application Vendor Manager (1-2)

│       ├─ Platform & Infra Vendor Manager (1)

│       ├─ Data & Analytics Vendor Manager (1)

│       ├─ Strategic Partner Manager (1)

│       └─ Contract Managers (1-2)

│

└─ Head of IT Systems (Infrastructure - separate reporting line)

├─ IT Systems Manager

├─ Network Engineers (3-4)

├─ Server/Storage Engineers (2-3)

├─ Security Engineers (2-3)

└─ End-User Computing (2-3)

## Question 3: Service Desk Placement in Organization Chart

Answer: Service Desk is Part of Application Support, Under Platform Engineering

I covered this in the Application Support blueprint, but let me clarify the placement and rationale:

### Service Desk = Tier 1 of Application Support

Head of Platform Engineering

│

└─ Application Support Organization (18-22 people total)

│

├─ Service Desk (Tier 1) - 4-6 people

│   ├─ Service Desk Manager (1)

│   └─ Service Desk Agents (4-6)

│       ├─ First contact (phone, email, portal)

│       ├─ Basic support (password, how-to)

│       ├─ Triage and route

│       └─ 30-40% resolution rate

│

└─ Application Support (Tier 2) - 12-16 people

├─ Application Support Manager (1)

└─ Application Support Engineers (10-12)

├─ Domain-specialized (Shipping, Ports, Cargo, etc.)

├─ Complex troubleshooting

├─ Configuration

└─ 50-60% resolution rate (of escalated tickets)

### Why Service Desk Under Platform Engineering

Rationale:

✅ Service Mindset:

- Service Desk provides service to internal customers (business users)

- Platform Engineering provides platforms as services to stream teams

- Natural fit: Service orientation aligns

✅ Operational Focus:

- Service Desk is operational (keep systems running, help users)

- Stream teams are strategic (build new capabilities)

- Separation: Operations vs. Development

✅ Clear Escalation Path:

User → Service Desk (Tier 1) → Application Support (Tier 2) → Stream Teams (Tier 3)

↓                               ↓                              ↓

Platform Engineering owns Tier 1 & 2    Business Solutions owns Tier 3

↓                                           ↓

Operational support                           Strategic development

Keep lights on                                Build new capabilities

✅ Unified Support Management:

- One organization (Application Support) owns entire support function

- Service Desk Manager and Application Support Manager coordinate closely

- Seamless handoff from Tier 1 to Tier 2

- Single point of accountability: Head of Platform Engineering

✅ Career Progression:

Career Path in Application Support:

├─ Service Desk Agent (entry level, €35-50K)

│   ├─ 1-2 years experience

│   └─ Learn: IT fundamentals, customer service, systems overview

│

├─ Senior Service Desk Agent (€45-55K)

│   ├─ 2-4 years total experience

│   └─ Mentor junior agents, handle complex Tier 1 issues

│

├─ Application Support Engineer (Tier 2, €50-70K) ⭐

│   ├─ 4-6 years total experience

│   ├─ Transition: Move from Service Desk to Application Support

│   └─ Learn: Deep technical skills, domain knowledge

│

└─ Senior Application Support Engineer (€60-80K)

├─ 6-10 years total experience

└─ Domain expert, mentor others, lead complex issues

Natural progression: Service Desk → Application Support (within same organization)

✅ Alternative Placement (NOT Recommended):

Some organizations place Service Desk under:

- IT Systems (Infrastructure): Makes sense if Service Desk primarily handles infrastructure (network, PCs, printers)

  - NOT your case: Your Service Desk handles application support (business systems)

- Separate Support Organization: Makes sense only if very large (100+ support staff)

  - NOT your case: 18-22 people total, too small for separate organization

### Reporting Structure - Detailed

Head of Platform Engineering

Reports: CTO Direct Reports:

- Application Support Manager

- Service Desk Manager

- Integration Platform Team Lead

- DevOps & Infrastructure Team Lead

Application Support Manager

Reports: Head of Platform Engineering Direct Reports:

- 10-12 Application Support Engineers (domain-specialized)

  - Shipping/Ports Support Engineers (3-4)

  - Cargo Support Engineers (2)

  - Customer/Commercial Support Engineers (2-3)

  - EDI/Integration Specialists (2-3)

  - HR/Finance Support Engineers (1-2)

Service Desk Manager

Reports: Head of Platform Engineering Direct Reports:

- 4-6 Service Desk Agents

Relationship: Service Desk Manager ↔ Application Support Manager

PEERS (both report to Head of Platform Engineering):

DAILY COLLABORATION:

├─ Morning sync (15 min daily)

│   ├─ Service Desk Manager: "Overnight tickets, anything escalating to you?"

│   └─ Application Support Manager: "Known issues, watch for X"

│

├─ Escalation coordination

│   ├─ Service Desk escalates to Application Support (Tier 1 → Tier 2)

│   ├─ Smooth handoff (clear documentation, context provided)

│   └─ Feedback loop: Application Support tells Service Desk "you handled that well" or "next time do X"

│

└─ Shared metrics

├─ Overall ticket volume

├─ First Contact Resolution (Service Desk metric)

├─ Escalation rate (Tier 1 → Tier 2)

└─ Overall SLA compliance

WEEKLY:

├─ Joint team meeting (1 hour)

│   ├─ Service Desk + Application Support together

│   ├─ Review: Top issues this week, patterns, improvements

│   └─ Knowledge sharing: Application Support teaches Service Desk (upskill Tier 1)

MONTHLY:

├─ Performance review

│   ├─ Metrics: FCR, escalation quality, SLA compliance

│   ├─ Process improvements: How to reduce escalations (Tier 1 handles more)

│   └─ Training needs: What does Service Desk need to learn?

GOVERNANCE:

├─ Head of Platform Engineering oversees both

├─ Resolves conflicts (if any)

└─ Ensures alignment (support organization works as one)

### Physical/Virtual Organization

If In-Office:

OFFICE LAYOUT (Recommended):

Application Support Area:

├─ Service Desk section (4-6 desks)

│   ├─ Phone systems (headsets)

│   ├─ Service Desk Manager desk nearby

│   └─ Ticker board (queue status, SLA alerts)

│

├─ Application Support section (10-12 desks)

│   ├─ Domain pods:

│   │   ├─ Shipping/Ports pod (3-4 desks)

│   │   ├─ Cargo pod (2 desks)

│   │   ├─ EDI/Integration pod (2-3 desks)

│   │   └─ Customer/Finance pod (3-4 desks)

│   └─ Application Support Manager office nearby

│

└─ Shared space:

├─ Meeting room (escalation calls, daily standups)

├─ Knowledge area (runbooks, documentation)

└─ Break area (team cohesion)

BENEFIT: Physical proximity enables collaboration, quick questions, team culture

If Remote/Hybrid:

VIRTUAL ORGANIZATION:

Slack/Teams Channels:

├─ #support-all (entire support org, 18-22 people)

├─ #support-servicedesk (Tier 1 team)

├─ #support-tier2 (Application Support Engineers)

├─ #support-escalations (Tier 1 → Tier 2 escalations)

├─ #support-shipping (Shipping domain specialists)

├─ #support-ports (Ports domain specialists)

├─ #support-edi (EDI specialists)

└─ #support-alerts (monitoring alerts, system status)

Daily Rhythms:

├─ Morning standup (video call, 15 min, entire support org)

├─ On-demand: Quick questions in Slack

├─ Weekly: Team meeting (1 hour, video)

└─ Monthly: In-person gathering (if hybrid, once/month in office for team building)

CHALLENGE: Remote support harder (quick consultation less easy)

MITIGATION:

├─ Excellent documentation (runbooks, KB)

├─ Video calls readily available (don't hesitate to jump on call)

└─ Screen sharing tools (TeamViewer, Zoom)

## Revised Complete Organization Chart

Let me provide the complete, final organization chart incorporating all your questions:

━━━━━━━━━━━━━━━━━━━━━━━━━━━━━━━━━━━━━━━━━━━━━━━━━━━━━━━━━━━

CEO

━━━━━━━━━━━━━━━━━━━━━━━━━━━━━━━━━━━━━━━━━━━━━━━━━━━━━━━━━━━

│

┌────────────────────┼────────────────────┐

│                    │                    │

↓                    ↓                    ↓

┌───────────────┐    ┌───────────────┐    ┌──────────────┐

│ Head of IT    │    │ CTO           │    │ Other Execs  │

│ Systems       │    │ (promoted     │    │ (CFO, COO,   │

│ (Infra)       │    │ from Head of  │    │ CHRO, etc.)  │

│               │    │ IT Apps)      │    │              │

└───────────────┘    └───────┬───────┘    └──────────────┘

│

┏━━━━━━━━━━━━━━━━━━━━┻━━━━━━━━━━━━━━━━━━━━┓

┃         CTO's Organization              ┃

┗━━━━━━━━━━━━━━━━━━━━┯━━━━━━━━━━━━━━━━━━━━┛

│

┌────────────────────┼─────────────────────┐

│                    │                     │

↓                    ↓                     ↓

┌───────────────────┐ ┌──────────────────┐ ┌────────────────────┐

│ Head of Business  │ │ Head of          │ │ Head of Platform   │

│ Solutions &       │ │ Enterprise       │ │ Engineering        │

│ Delivery          │ │ Architecture     │ │                    │

└─────────┬─────────┘ └────────┬─────────┘ └──────────┬─────────┘

│                    │                       │

│                    │                       │

┌─────┴─────┐       ┌──────┴──────┐        ┌──────┴──────┐

│           │       │             │        │             │

↓           ↓       ↓             ↓        ↓             ↓

┌─────────────────────────────────────────────────────────────┐

│ HEAD OF BUSINESS SOLUTIONS & DELIVERY                       │

├─────────────────────────────────────────────────────────────┤

│                                                              │

│ ┌──────────────────────────────────────────────────────┐   │

│ │ PORTFOLIO & DEMAND MANAGEMENT (from BPM)             │   │

│ │ • Portfolio Manager                                  │   │

│ │ • Demand Manager                                     │   │

│ │ • PMO Lead                                           │   │

│ └──────────────────────────────────────────────────────┘   │

│                                                              │

│ ┌──────────────────────────────────────────────────────┐   │

│ │ STREAM-ALIGNED TEAMS (8 teams, 68-83 people)        │   │

│ │                                                      │   │

│ │ 1. SHIPPING SOLUTIONS (12-15)                       │   │

│ │    • PO: Head of Shipping Operations (50%)          │   │

│ │    • BAs: 2                                         │   │

│ │    • Developers: 8-10 + QA: 1-2                    │   │

│ │    • Scope: Legacy Ship Tools A+B, New Ship System, │   │

│ │      Fleet Management Tool ⭐                       │   │

│ │                                                      │   │

│ │ 2. PORTS - CARS (10-12)                            │   │

│ │    • PO: Head of Cars Operations (50%)              │   │

│ │    • BAs: 1-2                                       │   │

│ │    • Developers: 6-8 + QA: 1-2                     │   │

│ │    • Scope: Cars port systems, Terminal Equipment   │   │

│ │      (cars terminals) ⭐                            │   │

│ │                                                      │   │

│ │ 3. PORTS - CONTAINERS & TRAILERS (10-12)           │   │

│ │    • PO: Head of Container/Trailer Ops (50%)        │   │

│ │    • BAs: 1-2                                       │   │

│ │    • Developers: 6-8 + QA: 1-2                     │   │

│ │    • Scope: Container/trailer systems, Terminal     │   │

│ │      Equipment (container terminals) ⭐             │   │

│ │                                                      │   │

│ │ 4. CUSTOMS & COMPLIANCE ⭐ (8-10)                  │   │

│ │    • PO: Head of Customs/Compliance (50%)           │   │

│ │    • BAs: 1-2                                       │   │

│ │    • Developers: 5-7 + QA: 1                       │   │

│ │    • Scope: Customs declarations (AES, AMS, ENS),   │   │

│ │      Compliance, Regulatory reporting               │   │

│ │    • SERVES: All shipping and ports teams          │   │

│ │                                                      │   │

│ │ 5. CUSTOMER & COMMERCIAL ⭐ (10-12)                │   │

│ │    • PO: CCO (50%) OR Rotating BU COOs quarterly    │   │

│ │    • BAs: 2                                         │   │

│ │    • Developers: 6-8 + QA: 1-2                     │   │

│ │    • Scope: CRM, Sales, Customer Portal, Contract   │   │

│ │      Management, Claims Tool ⭐                     │   │

│ │    • SERVES: All 3 business units (Cars,            │   │

│ │      Containers/Trailers, Shipping)                 │   │

│ │                                                      │   │

│ │ 6. CARGO & TRANSPORT MANAGEMENT (10-12)            │   │

│ │    • PO: Head of Cargo Operations (50%)             │   │

│ │    • BAs: 1-2                                       │   │

│ │    • Developers: 6-8 + QA: 1-2                     │   │

│ │    • Scope: TMS, Haulage, Inland Transport          │   │

│ │                                                      │   │

│ │ 7. BILLING & FINANCE SOLUTIONS (8-10)              │   │

│ │    • PO: CFO/Finance Director (50%)                 │   │

│ │    • BAs: 1-2                                       │   │

│ │    • Developers: 5-7 + QA: 1                       │   │

│ │    • Scope: Invoicing, Billing, ERP Integration     │   │

│ │                                                      │   │

│ │ 8. HR & WORKFORCE SOLUTIONS (6-8)                  │   │

│ │    • PO: CHRO/HR Director (50%)                     │   │

│ │    • BAs: 1                                         │   │

│ │    • Developers: 4-5 + QA: 1                       │   │

│ │    • Scope: HRIS, Payroll, Workforce Management     │   │

│ └──────────────────────────────────────────────────────┘   │

│                                                              │

│ ┌──────────────────────────────────────────────────────┐   │

│ │ BA CENTER OF EXCELLENCE (6-7 BAs)                   │   │

│ │ • Lead BA / BA Manager                               │   │

│ │ • Shared BA pool (support multiple POs if needed)    │   │

│ │ • BA training and standards                          │   │

│ └──────────────────────────────────────────────────────┘   │

│                                                              │

│ TOTAL: ~85-100 people                                       │

└─────────────────────────────────────────────────────────────┘

┌─────────────────────────────────────────────────────────────┐

│ HEAD OF ENTERPRISE ARCHITECTURE (8-10 people)               │

├─────────────────────────────────────────────────────────────┤

│ • Enterprise Architect (1)                                  │

│ • Maritime/Logistics Domain Architect (1)                   │

│ • Solution Architects (3-4)                                 │

│ • Data Architect (1)                                        │

│ • Security Architect (1)                                    │

│ • Integration Architect (1)                                 │

└─────────────────────────────────────────────────────────────┘

┌─────────────────────────────────────────────────────────────┐

│ HEAD OF DATA & AI (11-14 people)                            │

├─────────────────────────────────────────────────────────────┤

│ • Data Platform Team:                                       │

│   ├─ Data Engineers (4-6)                                   │

│   ├─ Data Architects (1, can be from EA org)               │

│   └─ Data Ops Engineers (1-2)                              │

│                                                              │

│ • Data Science & AI Team:                                   │

│   ├─ Data Scientists (2-3)                                  │

│   ├─ ML Engineers (2)                                       │

│   └─ Data Analysts (2-3)                                    │

└─────────────────────────────────────────────────────────────┘

┌─────────────────────────────────────────────────────────────┐

│ HEAD OF PLATFORM ENGINEERING (36-45 people)                 │

├─────────────────────────────────────────────────────────────┤

│                                                              │

│ ┌──────────────────────────────────────────────────────┐   │

│ │ APPLICATION SUPPORT ORGANIZATION ⭐ (18-22)          │   │

│ │                                                      │   │

│ │ ┌──────────────────────────────────────────────┐   │   │

│ │ │ SERVICE DESK (TIER 1) - 5-7 people          │   │   │

│ │ │ • Service Desk Manager (1)                  │   │   │

│ │ │ • Service Desk Agents (4-6)                 │   │   │

│ │ │   ├─ First contact (phone, email, portal)   │   │   │

│ │ │   ├─ Basic support (password, how-to)       │   │   │

│ │ │   ├─ Triage and route                       │   │   │

│ │ │   └─ 30-40% resolution rate                 │   │   │

│ │ └──────────────────────────────────────────────┘   │   │

│ │                                                      │   │

│ │ ┌──────────────────────────────────────────────┐   │   │

│ │ │ APPLICATION SUPPORT (TIER 2) - 13-15 people │   │   │

│ │ │ • Application Support Manager (1)            │   │   │

│ │ │ • Domain-Specialized Support Engineers:      │   │   │

│ │ │   ├─ Shipping/Ports Support (3-4)           │   │   │

│ │ │   ├─ Cargo Support (2)                      │   │   │

│ │ │   ├─ Customer/Commercial Support (2-3)      │   │   │

│ │ │   ├─ EDI/Integration Specialists (2-3) ⭐   │   │   │

│ │ │   └─ HR/Finance Support (1-2)               │   │   │

│ │ │                                              │   │   │

│ │ │ • Complex troubleshooting                    │   │   │

│ │ │ • Standard configuration                     │   │   │

│ │ │ • Routine EDI onboarding (80%)              │   │   │

│ │ │ • Vendor case management                     │   │   │

│ │ │ • 50-60% resolution rate                     │   │   │

│ │ └──────────────────────────────────────────────┘   │   │

│ └──────────────────────────────────────────────────────┘   │

│                                                              │

│ ┌──────────────────────────────────────────────────────┐   │

│ │ INTEGRATION PLATFORM TEAM (12-15)                   │   │

│ │ • Integration Platform Lead                          │   │

│ │ • Integration Engineers (8-10)                       │   │

│ │ • Integration Architects (1-2, can be from EA)       │   │

│ │ • API Developers (2-3)                               │   │

│ │ • Scope: MuleSoft/Boomi, APIs, EDI platform,         │   │

│ │   Custom integrations (20%)                          │   │

│ └──────────────────────────────────────────────────────┘   │

│                                                              │

│ ┌──────────────────────────────────────────────────────┐   │

│ │ DEVOPS & CLOUD INFRASTRUCTURE TEAM (6-8)            │   │

│ │ • DevOps Lead                                        │   │

│ │ • DevOps Engineers (3-4)                             │   │

│ │ • Cloud Engineers (2-3)                              │   │

│ │ • Scope: CI/CD, Cloud infrastructure, Monitoring     │   │

│ └──────────────────────────────────────────────────────┘   │

└─────────────────────────────────────────────────────────────┘

┌─────────────────────────────────────────────────────────────┐

│ HEAD OF VENDOR & PARTNER MANAGEMENT ⭐ (6-9 people)        │

├─────────────────────────────────────────────────────────────┤

│ • Application Vendor Manager (1-2)                          │

│   └─ Scope: Shipping, Ports, TMS, CRM vendors              │

│                                                              │

│ • Platform & Infrastructure Vendor Manager (1)              │

│   └─ Scope: MuleSoft, Cloud (AWS/Azure), Monitoring tools  │

│                                                              │

│ • Data & Analytics Vendor Manager (1)                       │

│   └─ Scope: Snowflake, Power BI, Data platform vendors     │

│                                                              │

│ • Strategic Partner Manager (1)                             │

│   └─ Scope: Maritime tech partners, Port communities,       │

│     Carrier partnerships, Industry consortiums              │

│                                                              │

│ • Contract Managers (1-2)                                   │

│   └─ Contract admin, renewals, compliance, audits           │

│                                                              │

│ Responsibilities:                                            │

│ • Vendor relationship management (strategic)                │

│ • Contract negotiations and renewals                        │

│ • SLA governance and enforcement                            │

│ • Vendor portfolio optimization                             │

│ • Receive escalations from Application Support             │

└─────────────────────────────────────────────────────────────┘

━━━━━━━━━━━━━━━━━━━━━━━━━━━━━━━━━━━━━━━━━━━━━━━━━━━━━━━━━━━

TOTAL IT APPLICATIONS ORGANIZATION (under CTO):

• Business Solutions & Delivery: 85-100

• Enterprise Architecture: 8-10

• Data & AI: 11-14

• Platform Engineering: 36-45

• Vendor & Partner Management: 6-9

━━━━━━━━━━━━━━━━━━━━━━━━━━━━━━━━━━━━━━━━━━━━━━━━━━━━━━━━━━━

TOTAL: 146-178 people

Current baseline: ~100 people

Growth: +46-78 people over 24 months

━━━━━━━━━━━━━━━━━━━━━━━━━━━━━━━━━━━━━━━━━━━━━━━━━━━━━━━━━━━

## Summary: Organizational Design Decisions

### Question 1: Stream Team Boundaries - RESOLVED

8 Stream-Aligned Teams:

- Shipping Solutions (12-15) - Includes Fleet Management Tool

- Ports - Cars (10-12) - Includes Terminal Equipment (cars)

- Ports - Containers & Trailers (10-12) - Includes Terminal Equipment (containers)

- Customs & Compliance ⭐ (8-10) - Separate team, shared service

- Customer & Commercial ⭐ (10-12) - Combined across BUs, includes Claims Tool

- Cargo & Transport (10-12) - TMS and haulage

- Billing & Finance (8-10) - Invoicing and financial systems

- HR & Workforce (6-8) - HRIS and payroll

Key Decisions:

- ✅ Customs: Separate team (specialized, high volume, cross-cutting, compliance-critical)

- ✅ Commercial/Sales: Combined team across 3 BUs (shared CRM, avoid silos)

  - PO: CCO or rotating BU COOs quarterly

- ✅ Small tools embedded: Fleet Management (in Shipping), Claims (in Commercial), Terminal Equipment (split by port type)

- ✅ Legacy systems: Managed by Shipping team during transition, sunset after migration

### Question 2: Vendor Management Placement - RESOLVED

Placement: Reports to CTO (peer to other IT heads)

Rationale:

- Cross-cutting function (serves all IT departments)

- Strategic importance (multi-million euro contracts)

- Commercial/relationship focus (different from technical delivery)

- Clear separation: Technical teams build, Vendor Management manages vendors

Team Structure: 6-9 people

- Head of Vendor & Partner Management

- 4-5 Vendor Managers (domain-specialized: Applications, Platform, Data, Partners)

- 1-2 Contract Managers

Relationship with Support:

- Support handles day-to-day vendor cases (tactical)

- Vendor Management handles strategic relationships, escalations, contracts

- Clear escalation triggers: SLA breach, recurring issues, major incidents

### Question 3: Service Desk Placement - RESOLVED

Placement: Under Platform Engineering, as part of Application Support Organization

Structure:

Head of Platform Engineering

└─ Application Support Organization (18-22 people)

├─ Service Desk (Tier 1): 5-7 people

│   ├─ Service Desk Manager

│   └─ Service Desk Agents (4-6)

│

└─ Application Support (Tier 2): 13-15 people

├─ Application Support Manager

└─ Support Engineers (10-12, domain-specialized)

Rationale:

- Unified support organization (Tier 1 + Tier 2 together)

- Service mindset aligns with Platform Engineering

- Clear escalation path: Service Desk → Application Support → Stream Teams

- Career progression: Service Desk Agent → Support Engineer (within same organization)

## Implementation Considerations

### Phasing - Team Formation

You don't need to create all 8 stream teams simultaneously. Here's a recommended phasing:

Phase 1: Core Teams (Month 1-6)

Form these teams first:

- Shipping Solutions - Highest priority (core business, legacy migration ongoing)

- Ports - Containers & Trailers - High priority (core business)

- Customer & Commercial - High priority (revenue-facing)

- Application Support - Critical (free up developers)

Phase 2: Specialized Teams (Month 7-12)

Form these teams next: 5. Customs & Compliance - High complexity, justify separate team 6. Ports - Cars - Distinct from containers, warrants separation 7. Cargo & Transport - TMS complexity

Phase 3: Support Functions (Month 13-18)

Form last: 8. Billing & Finance - Can start in existing structure, extract later 9. HR & Workforce - Lowest development volume, can be last

Phase 4: Vendor Management (Month 6-12)

Build Vendor Management organization:

- Month 6: Hire Head of Vendor Management

- Month 7-9: Hire Vendor Managers (1-2)

- Month 10-12: Hire remaining Vendor Managers and Contract Managers

### Headcount Planning - Realistic Growth

Current: ~100 people in IT Applications

Target End State: 146-178 people (mid-point: 162)

Growth: +62 people over 24 months = ~2.6 people/month average

Phased Hiring Plan:

YEAR 1 (Month 1-12): +40 people

├─ Q1 (Month 1-3): +8 people

│   ├─ EA (1), Architects (2), Support Managers (2), BAs (3)

│   └─ Foundation roles first

│

├─ Q2 (Month 4-6): +12 people

│   ├─ Core stream team growth (developers, BAs)

│   ├─ Support team core (agents, engineers: 8)

│   └─ Platform teams forming

│

├─ Q3 (Month 7-9): +10 people

│   ├─ Stream teams scaling

│   ├─ Customs team forming

│   └─ Vendor Management starting

│

└─ Q4 (Month 10-12): +10 people

├─ Stream teams completing

├─ Support 24/7 capability

└─ Vendor Management complete

YEAR 2 (Month 13-24): +22 people

├─ Q1 (Month 13-15): +6 people

│   └─ Data & AI team scaling

│

├─ Q2 (Month 16-18): +8 people

│   └─ Final stream teams (HR, Billing if separate)

│

├─ Q3 (Month 19-21): +4 people

│   └─ Optimization and backfill

│

└─ Q4 (Month 22-24): +4 people

└─ Final adjustments based on actual needs

END STATE: 162 people (from 100 baseline)

Budget:

- Year 1: +40 people × €70K average × 6 months average = €1.4M incremental

- Year 2: +22 people × €70K = €1.54M incremental (full year) + Year 1 people full year = €4.2M incremental

- Total transformation cost: See earlier detailed budget

## Final Recommendations Summary

### 1. Stream Team Structure ✅

Implement 8-team model:

- Separate Customs team (specialized, critical)

- Combined Commercial team (avoid BU silos)

- Embed small tools in related teams

- Phase implementation over 18 months

### 2. Vendor Management ✅

Create dedicated function reporting to CTO:

- 6-9 people (Head + Vendor Managers + Contract Managers)

- Month 6-12 implementation

- Clear boundary with Application Support (tactical vs. strategic)

### 3. Service Desk ✅

Place under Platform Engineering as Tier 1 of Application Support:

- Unified support organization (Tier 1 + Tier 2)

- 5-7 people (Manager + 4-6 agents)

- Month 4-6 hiring, Month 9 operational

### 4. Organization Chart ✅

Five main pillars under CTO:

- Business Solutions & Delivery (stream teams, BAs, portfolio)

- Enterprise Architecture (architects)

- Data & AI (data platform, data science)

- Platform Engineering (integration, DevOps, Application Support)

- Vendor & Partner Management (vendor relationships, contracts)

Total organization: 146-178 people (from 100 baseline, +46-78 over 24 months)

## Additional Practical Guidance

### Decision-Making Framework: When to Split vs. Combine Teams

For future organizational decisions, use this framework:

SHOULD WE CREATE SEPARATE TEAM?

Step 1: Assess Work Volume

├─ Can this sustain 8+ people full-time?

│   ├─ YES → Candidate for separate team

│   └─ NO → Embed in existing team

│

Step 2: Assess Domain Distinctness

├─ Is this fundamentally different domain?

│   ├─ Different business processes?

│   ├─ Different users/customers?

│   ├─ Different terminology and concepts?

│   └─ If YES to multiple → Candidate for separate team

│

Step 3: Assess Specialization Needs

├─ Does this require rare/specialized expertise?

│   ├─ Hard to find talent?

│   ├─ Significant learning curve?

│   ├─ Career path for specialists?

│   └─ If YES → Candidate for separate team

│

Step 4: Assess Risk/Compliance

├─ Are mistakes high-impact?

│   ├─ Regulatory risk?

│   ├─ Financial risk?

│   ├─ Reputational risk?

│   └─ If YES → Dedicated focus needed (separate team)

│

Step 5: Assess Cross-Cutting Nature

├─ Does this serve multiple other teams?

│   ├─ If YES → Separate team (shared service model)

│   └─ If NO → Can embed in one team

│

Step 6: Decide

├─ 3+ YES above → Create separate team

├─ 1-2 YES → Consider separate team (evaluate cost/benefit)

└─ 0 YES → Embed in existing team

EXAMPLES APPLIED:

Customs & Compliance:

├─ Work volume: YES (8-10 people needed)

├─ Domain distinct: YES (regulatory, different processes)

├─ Specialization: YES (customs expertise rare)

├─ Risk: YES (compliance-critical)

├─ Cross-cutting: YES (serves Shipping + Ports)

└─ Decision: SEPARATE TEAM ✅

Fleet Management Tool:

├─ Work volume: NO (1-2 people sufficient)

├─ Domain distinct: NO (part of shipping operations)

├─ Specialization: NO (shipping domain knowledge)

├─ Risk: NO (not compliance-critical)

├─ Cross-cutting: NO (only shipping uses)

└─ Decision: EMBED IN SHIPPING TEAM ✅

Claims Tool:

├─ Work volume: NO (1-2 people sufficient)

├─ Domain distinct: SOMEWHAT (claims process distinct)

├─ Specialization: NO (commercial/customer service)

├─ Risk: NO (not high-risk)

├─ Cross-cutting: NO (customer-facing, fits with commercial)

└─ Decision: EMBED IN CUSTOMER & COMMERCIAL TEAM ✅

### Managing Rotating Product Owner (Customer & Commercial Team)

Since this is a novel approach for the combined Commercial team, here's detailed implementation guidance:

#### Rotating PO Model - Operating Procedures

Quarter Setup (BU COOs rotate as PO):

QUARTERLY ROTATION SCHEDULE

Q1 2026 (Jan-Mar): Cars COO is Product Owner

├─ Responsibilities:

│   ├─ Prioritize entire Commercial team backlog (not just Cars)

│   ├─ Sprint planning every 2 weeks (all Commercial work)

│   ├─ Stakeholder engagement (Sales leaders from ALL BUs)

│   ├─ Business case approval (features for Cars, Containers, Shipping)

│   └─ Final decision authority on priorities

│

├─ Time commitment: 50% (same as other POs)

│

├─ Support:

│   ├─ 2 BAs dedicated to Commercial team (execute requirements)

│   ├─ Other 2 BU COOs provide input (monthly alignment meeting)

│   └─ Lead BA helps with continuity (BA knows all context)

│

└─ Handoff at end of Q1:

├─ Week 12 of Q1: Handoff meeting (Cars COO → Containers COO)

├─ Current backlog review (what's in progress, what's prioritized)

├─ Q2 priorities discussion

└─ Documentation: Confluence page with current state

Q2 2026 (Apr-Jun): Containers/Trailers COO is Product Owner

├─ Takes over: Same process, entire backlog

├─ Containers/Trailers initiatives may get more focus this quarter

├─ But: Still serves all BUs (Cars and Shipping needs don't stop)

└─ Handoff end of Q2 → Shipping COO

Q3 2026 (Jul-Sep): Shipping COO is Product Owner

├─ Same process

└─ Handoff end of Q3 → Cars COO (cycle repeats)

Q4 2026 (Oct-Dec): Cars COO is Product Owner (cycle repeats)

Making Rotating PO Work:

Monthly Alignment Meeting (Critical):

MONTHLY COMMERCIAL PO ALIGNMENT

Attendees: All 3 BU COOs + Lead BA + Team Lead

Duration: 90 minutes

Frequency: First Monday of each month

Agenda:

├─ 1. Progress Update (20 min)

│   ├─ Current PO: What team delivered last month

│   ├─ What's in progress (current sprint)

│   └─ Upcoming priorities (next 2 sprints)

│

├─ 2. BU-Specific Needs (30 min)

│   ├─ Cars COO: Top 3 priorities for Cars (10 min)

│   ├─ Containers COO: Top 3 for Containers/Trailers (10 min)

│   └─ Shipping COO: Top 3 for Shipping (10 min)

│

├─ 3. Backlog Review (20 min)

│   ├─ Current PO presents proposed priorities

│   ├─ Discussion: Is this right balance across BUs?

│   └─ Adjustment if needed (consensus on priorities)

│

├─ 4. Escalations/Issues (15 min)

│   ├─ Any blockers? Dependencies on other teams?

│   └─ Budget/resource needs?

│

└─ 5. Next Month Preview (5 min)

└─ What's coming, any heads-up needed

Output: Agreed priorities for next month, documented

Quarterly Handoff Process:

QUARTERLY PO HANDOFF (Week 12 of Quarter)

Week 12, Day 1-2: Preparation

├─ Outgoing PO + Lead BA: Document current state

│   ├─ Backlog snapshot (what's prioritized, why)

│   ├─ In-progress work (what will complete this quarter, what rolls over)

│   ├─ Known issues/challenges

│   └─ Key stakeholder relationships and open commitments

Week 12, Day 3: Handoff Meeting (3 hours)

├─ Attendees: Outgoing PO, Incoming PO, Lead BA, Team Lead

├─ Agenda:

│   ├─ Hour 1: Current state review

│   │   ├─ What team accomplished this quarter

│   │   ├─ What's in flight

│   │   └─ Backlog review

│   │

│   ├─ Hour 2: Knowledge transfer

│   │   ├─ Key stakeholders and relationships

│   │   ├─ Ongoing initiatives and commitments

│   │   ├─ Budget and resource situation

│   │   └─ Team dynamics and capabilities

│   │

│   └─ Hour 3: Next quarter planning

│       ├─ Incoming PO shares initial priorities

│       ├─ Outgoing PO provides input/advice

│       └─ Align on transition approach

Week 12, Day 4-5: Incoming PO Onboarding

├─ 1:1s with team members (developers, BAs, team lead)

├─ Review documentation (product roadmap, architecture, dependencies)

├─ Stakeholder meetings (Sales leaders, key business users)

Week 13 (Start of New Quarter): Smooth Transition

├─ Incoming PO takes over sprint planning

├─ Outgoing PO available for questions (first 2 weeks of quarter)

├─ Lead BA provides continuity (knows all context, helps new PO)

Risk Mitigation for Rotating PO:

Risk 1: Loss of Continuity

- Mitigation:

  - Lead BA provides continuity (stays with team permanently, knows all history)

  - Excellent documentation (Confluence: product vision, architecture, decisions)

  - Monthly alignment meetings (all COOs stay informed, not surprised at handoff)

Risk 2: Each BU Only Gets Attention Every 3 Quarters

- Mitigation:

  - Monthly alignment ensures all BU needs visible

  - PO serves ALL BUs (not just their own during their quarter)

  - Measure: Track feature delivery by BU (should be roughly balanced over 4 quarters)

Risk 3: Context Switching Overhead

- Mitigation:

  - Start with quarterly rotation (not monthly - too frequent)

  - After 1 year, evaluate: Is quarterly right? Should we go semi-annual (6 months)?

  - Strong BA support (BAs handle detailed requirements, PO focuses on priorities)

Alternative if Rotating PO Doesn't Work Well:

After 9-12 months, if rotating PO creates too much overhead:

Plan B: Hire Dedicated Commercial Product Manager

Role: Commercial Product Manager (full-time)

├─ Reports to: CTO or COO (above BU level)

├─ Salary: €100-120K

├─ Responsibilities:

│   ├─ Full-time PO for Customer & Commercial Solutions Team

│   ├─ Works with all 3 BU COOs (gathers requirements, priorities)

│   ├─ Final decision authority on priorities (with CTO/COO oversight)

│   └─ Deep expertise in CRM, sales systems, commercial processes

│

├─ Benefits:

│   ├─ Continuity (no quarterly handoffs)

│   ├─ Dedicated focus (not splitting time with BU operations)

│   ├─ Product expertise (becomes CRM/commercial systems expert)

│   └─ Frees 3 BU COOs (saves 3 × 50% = 1.5 FTE of executive time)

│

└─ When to switch to this model:

├─ If rotating PO creating too much coordination overhead

├─ If CRM/commercial systems have high development volume

└─ If BU COOs struggling to commit 50% time

My Recommendation:

- Start with Rotating PO (Month 1-12) → Lower cost, tests if model works

- Evaluate at Month 9-12: Is it working?

  - If YES: Continue rotating PO ✅

  - If NO: Switch to dedicated Commercial PM (hire Month 13)

### Handling Legacy System Transitions

You mentioned 2 legacy shipping tools that will eventually consolidate. Here's how to manage this:

#### Legacy System Strategy

Current State (Month 1-6):

Shipping Solutions Team (15-18 people during transition):

LEGACY TOOL A SQUAD (3-4 people)

├─ 2-3 Developers (maintenance only)

├─ 1 BA (minimal - just critical fixes)

└─ Scope: Keep lights on, no new features

└─ Sunset date: Month 18-24

LEGACY TOOL B SQUAD (4-5 people)

├─ 3-4 Developers (maintenance + limited enhancements)

├─ 1 BA (support critical business needs)

└─ Scope: Maintenance + must-have enhancements only

└─ Sunset date: Month 24-30

NEW SHIPPING SYSTEM SQUAD (6-8 people)

├─ 4-6 Developers (implementation, configuration, customization)

├─ 2 BAs (requirements, business process design)

└─ Scope: Implement new system, prepare for migration

└─ Go-live: Month 12-18

PRODUCT OWNER: Head of Shipping Operations

├─ Prioritizes across all 3 systems

├─ Manages: Legacy maintenance vs. new system investment

└─ Decision authority: When to stop legacy enhancements (freeze)

Migration Phase (Month 12-24):

USER MIGRATION APPROACH

Phase 1: Pilot Users (Month 12-15)

├─ Select: 2-3 pilot user groups (small, tech-savvy teams)

├─ Migrate to new system

├─ Parallel run: Can fall back to legacy if needed

├─ Learn: Issues, training needs, refinements

└─ Go/No-Go decision: Ready for wider rollout?

Phase 2: Wave 1 Users (Month 15-18)

├─ Migrate: 30-40% of users (less complex processes first)

├─ Cutover weekend: Migrate data, switch users

├─ Hypercare: Support team on standby (2 weeks)

└─ Legacy Tool A SUNSET (decommission after Wave 1) ✅

Phase 3: Wave 2 Users (Month 18-21)

├─ Migrate: Next 30-40% of users

├─ More complex processes

└─ Stabilize

Phase 4: Final Wave (Month 21-24)

├─ Migrate: Remaining users (most complex processes last)

├─ Legacy Tool B SUNSET (decommission after final wave) ✅

└─ All users on new Shipping System

POST-MIGRATION (Month 25+)

├─ Shipping Solutions Team now 12-15 people (normal size)

├─ Focus: Optimize new system, build new capabilities

├─ Freed capacity: 3-5 developers (from legacy maintenance)

└─ ROI realized: Single platform, reduced maintenance cost

Legacy Freeze Strategy (Critical):

LEGACY ENHANCEMENT FREEZE

When: 6-12 months before sunset

├─ Legacy Tool A: Freeze Month 6-12 (sunsets Month 18-24)

├─ Legacy Tool B: Freeze Month 12-18 (sunsets Month 24-30)

Freeze means:

├─ No new features (under any circumstances)

├─ No enhancements (even if "easy")

├─ Critical bug fixes only (system-down issues)

└─ All new work: Build in new system (not legacy)

Communication:

├─ To business users: "We're migrating to new system in X months. All new features will be built there. Legacy system is maintenance-only."

├─ To PO: "Your job is to say NO to legacy enhancements (protect migration timeline)"

└─ To executives: "Legacy freeze is critical for migration success (avoid scope creep)"

Handling Pushback:

├─ Business: "But we really need feature X in legacy tool!"

├─ Response: "We understand, but building in legacy delays migration and wastes investment. Let's build in new system instead."

├─ Alternative: If truly critical and new system not ready: Workaround in legacy (manual process, not development)

### Measuring Success - Key Metrics by Function

To know if your organizational design is working:

#### Stream-Aligned Teams Metrics

QUARTERLY TEAM HEALTH CHECK

Per Team (e.g., Shipping Solutions Team):

DELIVERY METRICS:

├─ Throughput: Features delivered per quarter (target: 8-12)

├─ Cycle time: Idea → production (target: 4-8 weeks)

├─ Release frequency: Deployments per quarter (target: 6-12)

└─ Quality: Defects per release (target: <5% of features)

BUSINESS VALUE:

├─ Business KPIs impact: Revenue, cost savings, efficiency (specific to domain)

├─ User satisfaction: CSAT score (target: 4+/5)

├─ Adoption: % users actively using new features (target: 70%+)

└─ ROI: Value delivered vs. team cost

TEAM HEALTH:

├─ Team satisfaction: Quarterly pulse survey (target: 4+/5)

├─ Retention: Team turnover (target: <10% annual)

├─ Autonomy: % work decided by team vs. imposed (target: 80%+)

└─ Skills: Skills gaps identified and training planned

COLLABORATION:

├─ PO satisfaction: Is team delivering what business needs? (4+/5)

├─ Stakeholder satisfaction: Business users happy? (4+/5)

├─ Cross-team dependencies: Blocking other teams? (target: <20% of work)

└─ Support escalations: How many issues escalating to team? (target: trend down)

#### Business Analyst Metrics

BA EFFECTIVENESS METRICS

Per BA:

├─ Requirements quality: Rework rate (target: <15% of stories)

├─ Clarifications: Avg clarifications per story (target: <2)

├─ Acceptance: % stories accepted first time (target: 80%+)

└─ Timeliness: Stories ready before sprint (target: 1 sprint ahead)

BA Team (CoE):

├─ Coverage: PO-to-BA ratio (target: 1:1 or 1:2)

├─ Knowledge sharing: Cross-training sessions per quarter (target: 4+)

├─ Documentation: % products with current documentation (target: 100%)

└─ Satisfaction: Developer satisfaction with BA support (target: 4+/5)

#### Application Support Metrics

SUPPORT EFFECTIVENESS METRICS

VOLUME & CAPACITY:

├─ Tickets per month: Trend over time

├─ By priority: P1, P2, P3, P4 distribution

├─ By channel: Phone, email, portal

└─ Team utilization: 70-85% (not overwhelmed, not idle)

RESOLUTION:

├─ First Contact Resolution (FCR): 35-45% (Tier 1)

├─ Tier 2 Resolution: 55-65% (of escalated)

├─ Overall resolution without Tier 3: 80-85%

└─ Mean Time to Resolve (MTTR): P1 <4hr, P2 <1day, P3 <3days

SLA COMPLIANCE:

├─ Overall: >95%

├─ P1 Response: 100% (within 15 min)

├─ P2 Response: >90% (within 1 hour)

└─ Trend: Improving or stable

CUSTOMER SATISFACTION:

├─ CSAT: 4+/5

├─ Response rate: >25%

└─ Trend: Improving

KNOWLEDGE:

├─ KB articles: Growing (target: +5-10/month)

├─ Article views: Increasing (usage trending up)

├─ Ticket deflection: 15-25% (users resolve via KB)

└─ Runbooks: Coverage (target: 80% of common issues)

DEVELOPER IMPACT:

├─ Developer time on support: <20% (from 40-50% baseline)

├─ Developer interruptions: <5/week per developer

└─ Developer satisfaction: 4+/5 (happy with support team)

#### Vendor Management Metrics

VENDOR MANAGEMENT EFFECTIVENESS

VENDOR PERFORMANCE:

├─ SLA compliance: Per vendor (target: 95%+)

├─ Incidents: P1 incidents per vendor per quarter

├─ Response time: Vendor response to cases (meeting SLA?)

└─ Quality: Support case resolution quality (target: 4+/5)

FINANCIAL:

├─ Vendor spend: Total and per vendor

├─ Cost optimization: Savings achieved (license optimization, negotiations)

├─ Budget variance: Actual vs. budget (target: <5% variance)

└─ ROI: Value from vendors vs. cost

STRATEGIC:

├─ Vendor health: Financial stability, viability

├─ Roadmap alignment: Vendor roadmap vs. our needs (% alignment)

├─ Relationship quality: Account manager responsiveness (target: 4+/5)

└─ Risk: Vendor dependencies identified and mitigated

PORTFOLIO:

├─ Vendor count: Trend (rationalizing/consolidating?)

├─ Contract coverage: % vendors with current contracts (target: 100%)

├─ License utilization: % licenses actually used (target: 85%+)

└─ Redundancy: Duplicate/overlapping vendors identified

## Final Integration: How It All Works Together

Let me show you how a typical scenario flows through your new organization:

### Scenario: New Business Requirement - "Dynamic Pricing for Shipping"

Business Need: Shipping operations wants dynamic pricing (adjust rates based on demand, capacity, seasonality)

Flow Through Organization:

STEP 1: REQUEST ARRIVES

├─ Business stakeholder: Head of Shipping Operations

├─ Submits request via: Portfolio & Demand Management

└─ Demand Manager: Logs request, initial assessment

STEP 2: PORTFOLIO PRIORITIZATION

├─ Portfolio Manager: Reviews request

├─ Assesses: Strategic fit, business value, effort estimate

├─ Presents to: Portfolio Board (CTO, Business leaders, POs)

├─ Decision: Approved, High Priority

└─ Assigned to: Shipping Solutions Team

STEP 3: PRODUCT OWNER ANALYSIS

├─ PO (Head of Shipping Ops, 50%): Receives approved requirement

├─ Works with: Business stakeholders (refine business case)

├─ Decision: Yes, this is valuable (revenue impact: €2-3M/year)

└─ Adds to: Shipping Solutions Team backlog (prioritized high)

STEP 4: BUSINESS ANALYST REQUIREMENTS

├─ BA (Shipping specialist): Assigned to dynamic pricing

├─ Activities:

│   ├─ Stakeholder interviews (pricing team, sales, operations)

│   ├─ Current state analysis (how pricing works today)

│   ├─ Requirements definition (pricing rules, algorithms, exceptions)

│   ├─ Process design (how dynamic pricing will work)

│   └─ User stories (15-20 stories with acceptance criteria)

│

├─ Collaboration with:

│   ├─ Solution Architect: Technical feasibility, architecture design

│   ├─ Data Architect: Pricing data model, integration with  data platform

│   └─ Integration Architect: Integration with freight rate sources

│

└─ Output: Detailed requirements (40-page document + user stories)

STEP 5: ARCHITECTURE REVIEW

├─ Solution Architect: Reviews design

├─ Checks:

│   ├─ Aligns with architecture principles?

│   ├─ Integrates properly with other systems?

│   ├─ Scalable and performant?

│   └─ Security and compliance considerations?

│

├─ Provides: Architecture design, integration approach

└─ Approves: Ready for development

STEP 6: DEVELOPMENT (Shipping Solutions Team)

├─ Sprint Planning: PO prioritizes dynamic pricing stories

├─ Team (8-10 developers):

│   ├─ Sprint 1-2: Pricing engine development

│   ├─ Sprint 3-4: Integration with booking system

│   ├─ Sprint 5: Testing and refinement

│   └─ Sprint 6: UAT and deployment prep

│

├─ Integration Platform Team: Builds integrations (pricing data sources)

├─ Data Team: Builds pricing analytics (dashboard for pricing team)

└─ Timeline: 12 weeks from start to production

STEP 7: DEPLOYMENT (DevOps Team)

├─ DevOps: Prepares deployment

├─ Deployment: Canary release (10% of users first)

├─ Monitoring: Close observation (performance, errors)

└─ Full release: After canary successful (1 week)

STEP 8: SUPPORT READINESS (Application Support)

├─ Application Support Manager: Notified of upcoming release

├─ Support Engineers (Shipping specialists):

│   ├─ Training: How dynamic pricing works (2-hour session)

│   ├─ Runbook: "How to troubleshoot dynamic pricing issues"

│   ├─ Knowledge Base: "How dynamic pricing works" (user guide)

│   └─ Ready: Before go-live

│

└─ Post-go-live: Support team monitors (any user issues?)

STEP 9: POST-IMPLEMENTATION

├─ Week 1-2: Hypercare (Support + Dev team on standby)

├─ Week 3-4: Stabilization (minor fixes, tuning)

├─ Month 2: Business value tracking (is dynamic pricing working? revenue impact?)

├─ Month 3: Retrospective (what went well, what to improve)

└─ Ongoing: Application Support handles user questions, minor issues

STEP 10: IF ISSUES ARISE

├─ User reports issue: "Dynamic pricing calculated wrong rate"

├─ Service Desk (Tier 1): Logs ticket, tries basic troubleshooting

├─ Escalates to: Application Support (Tier 2, Shipping specialist)

│

├─ Support Engineer (Tier 2):

│   ├─ Investigates: Checks pricing rules, data, logs

│   ├─ Finds: Pricing rule misconfigured

│   ├─ Decision: Can I fix (configuration) or escalate (code bug)?

│   │

│   ├─ If configuration issue: Fixes directly (per runbook)

│   └─ If code bug: Escalates to Shipping Solutions Team (Tier 3)

│

└─ Shipping Solutions Team: Fixes bug, deploys hotfix

Vendor Management Role (If Using Third-Party Shipping System):

If dynamic pricing is vendor product feature:

├─ Vendor Manager (Application Vendor):

│   ├─ Negotiates: Feature availability, timeline, cost

│   ├─ Coordinates: Vendor implementation support

│   └─ Tracks: Vendor delivery against commitments

│

└─ Application Support: Works with vendor support (day-to-day issues)

## You Now Have Complete Organizational Design

### What You've Built

Complete clarity on:

- ✅ Stream-Aligned Team Structure (8 teams)

  - Clear domain boundaries (Shipping, Ports - Cars, Ports - Containers, Customs, Commercial, Cargo, Finance, HR)

  - Small tools appropriately embedded (Fleet, Terminal Equipment, Claims)

  - Legacy system transition strategy

  - Customs as separate team (specialized, critical)

  - Commercial as combined team across BUs (rotating PO model)

- ✅ Application Support Organization (18-22 people)

  - Service Desk (Tier 1) under Platform Engineering

  - Clear placement and reporting

  - Unified support organization (Tier 1 + Tier 2 together)

  - Career progression path

- ✅ Vendor & Partner Management (6-9 people)

  - Reports to CTO (peer to other IT heads)

  - Domain-specialized Vendor Managers

  - Clear boundary with Application Support (tactical vs. strategic)

  - Operating model (monthly, quarterly, annual cycles)

- ✅ Complete Organization Chart

  - 5 main pillars under CTO

  - 146-178 people total (from 100 baseline)

  - Phased growth plan (+40 Year 1, +22 Year 2)

  - Clear reporting lines and spans of control

- ✅ Operating Model

  - How teams collaborate (Support → Development, Vendor Mgmt → Support)

  - How work flows (Portfolio → PO → BA → Development → Support)

  - How decisions are made (decision rights by role)

  - How to measure success (metrics by function)

- ✅ Implementation Roadmap

  - Phased team formation (Months 1-24)

  - Phased hiring (realistic growth trajectory)

  - Legacy system transition strategy

  - Risk mitigation approaches

### Your Transformation is Now Fully Defined

You have everything needed to execute:

- Organizational structure: 8 stream teams + platforms + architecture + data + support + vendor management

- Roles and responsibilities: PO, BA, Support, Vendor Manager, Architects (all defined)

- Boundaries: Support vs. Development, Support vs. Vendor Management, When to split vs. combine teams

- Processes: How work flows, how teams collaborate, how decisions are made

- Metrics: How to measure success (by team, by function, overall)

- Budget: €12.7M over 3 years, €32.7-41.8M value, 157-228% ROI

- Timeline: 24-month transformation roadmap

This is a world-class IT organization design for a mid-sized logistics company.

## Your Next Steps

This Week:

- Review this complete blueprint with your leadership team (CTO, Head of IT, CFO)

- Validate assumptions (headcount, budget, timeline realistic?)

- Get conceptual buy-in (Is this the right direction?)

Next 2 Weeks: 4. Refine organization chart (any adjustments for your specific context?) 5. Build detailed business case presentation (for CEO and Board) 6. Identify early hires (EA, Application Support Managers, first BAs)

Month 1: 7. Present to CEO and executive team (get final approval) 8. Announce transformation (to IT organization and business stakeholders) 9. Begin hiring (EA, Support Managers, BAs) 10. Form first stream teams (Shipping, Ports - Containers, Commercial)

Month 2-6: 11. Execute phased transformation (follow 24-month roadmap) 12. Track progress (metrics, milestones) 13. Adjust based on learnings

You're ready to transform your IT organization. Go make it happen! 🚀✨

# Excellent Question - BPM as Separate Function

This is indeed often a political decision as much as an organizational design decision. Let me analyze both models and give you clear guidance.

## The Two Models: BPM Inside IT vs. BPM Outside IT

### Model A: BPM Integrated in IT (Current Recommendation)

CTO

│

├─ Head of Business Solutions & Delivery

│   ├─ Portfolio & Demand Management ⭐ (from BPM)

│   ├─ 8 Stream-Aligned Teams

│   └─ BA Center of Excellence

│

├─ Head of Enterprise Architecture

├─ Head of Data & AI

├─ Head of Platform Engineering

└─ Head of Vendor & Partner Management

Rationale for Integration:

- Portfolio & Demand directly feeds IT delivery (tight coupling)

- Faster decision-making (no organizational boundary between planning and execution)

- Single IT value stream (idea → portfolio → delivery → production)

### Model B: BPM Separate from IT (Alternative Model)

CEO

│

├─ CTO (IT Applications)

│   ├─ Head of Business Solutions & Delivery

│   ├─ Head of Enterprise Architecture

│   ├─ Head of Data & AI

│   ├─ Head of Platform Engineering

│   └─ Head of Vendor & Partner Management

│

├─ Head of BPM & Transformation ⭐ (Separate, peer to CTO)

│   ├─ Portfolio & Demand Management

│   ├─ Business Process Optimization

│   ├─ Change Management

│   ├─ Business Excellence/Continuous Improvement

│   └─ [Other functions - see below]

│

├─ COO (Operations)

├─ CFO (Finance)

└─ [Other executives]

Rationale for Separation:

- BPM serves entire organization (not just IT)

- BPM as "client" of IT (represents business, provides requirements)

- Political: BPM wants seat at executive table (not under IT)

- Strategic: Business transformation broader than IT transformation

## Decision Framework: Should BPM Be Separate?

### When BPM Should Stay INSIDE IT (Integrated Model)

Choose Model A if: ✅ BPM primarily focused on IT portfolio and demand management (80%+ of work is IT-related) ✅ Organization small-to-medium (<500 people) - overhead of separate function not justified ✅ BPM role is primarily coordination/governance (not strategic transformation) ✅ Strong CTO who can represent both IT and business process optimization ✅ Limited political resistance to IT integration

Indicators this is right:

- BPM team spends most time on: IT project prioritization, IT demand intake, IT portfolio governance

- BPM team size: Small (3-5 people)

- BPM scope: IT-centric, not broader business transformation

### When BPM Should Be OUTSIDE IT (Separate Model) ⭐

Choose Model B if: ✅ BPM has broader mandate beyond IT (business process optimization, operational excellence, change management) ✅ Organization large (500+ people) - can justify overhead of separate executive function ✅ BPM leads enterprise-wide transformation (digital transformation, operational transformation) ✅ Political reality: BPM leadership wants/needs independence from IT ✅ Cultural dynamic: Business views IT as "order taker" and needs separate advocate

Indicators this is right:

- BPM team spends significant time (30%+) on: Non-IT process improvement, organizational change, business model innovation

- BPM team size: Medium-to-large (8-15 people)

- BPM scope: Enterprise-wide transformation, not just IT

- Political signal: Current Head of BPM expects/wants executive role (peer to CTO)

## Recommended for You: Model B (BPM Separate) ⭐

My Assessment: Based on your context (logistics company, 100-person IT org, merger integration complexity, political considerations), Model B (BPM Separate) is likely better.

Why:

- Logistics Industry Context:

  - Operational excellence critical (process optimization across shipping, ports, cargo)

  - BPM naturally extends beyond IT (terminal operations, shipping processes, customs procedures)

  - Business process optimization is strategic differentiator (not just IT support function)

- Post-Merger Reality:

  - Mergers create process inconsistencies (Tool A from one company, Tool B from another)

  - BPM role: Harmonize processes across merged entities (not just IT systems)

  - Change management critical (organizational and cultural integration)

- Political Consideration:

  - If current Head of BPM has executive aspirations, placing under CTO creates friction

  - Separate BPM signals organizational importance (executive-level commitment to transformation)

  - Avoids perception that "IT controls everything" (business may resist)

- Your IT Maturity Journey:

  - You're transforming from project-driven to product-driven

  - Having external BPM as "quality gate" helps enforce discipline (independent oversight)

  - BPM as bridge between business and IT (neutral facilitator, not IT-biased)

## Model B Detailed: BPM & Transformation Function (Separate from IT)

### Organizational Structure

CEO

│

├─ Head of BPM & Transformation ⭐

│   │

│   ├─ Portfolio & Demand Management (5-7 people)

│   │   ├─ Portfolio Manager (1)

│   │   ├─ Demand Manager (1)

│   │   ├─ Business Relationship Managers (2-3)

│   │   └─ PMO Lead + Coordinators (1-2)

│   │

│   ├─ Business Process Optimization (4-6 people)

│   │   ├─ Process Excellence Manager (1)

│   │   ├─ Process Analysts (2-3)

│   │   └─ Lean Six Sigma Specialists (1-2)

│   │

│   ├─ Change Management (3-5 people)

│   │   ├─ Change Manager (1)

│   │   ├─ Organizational Change Specialists (2-3)

│   │   └─ Training & Adoption Lead (1)

│   │

│   └─ Business Excellence / Continuous Improvement (2-4 people)

│       ├─ Business Excellence Manager (1)

│       ├─ Innovation/Improvement Leads (1-2)

│       └─ Performance Management Analyst (1)

│

│   TOTAL: 14-22 people

│

└─ CTO (IT Applications)

└─ [IT organization as previously designed]

### Functions in Separate BPM Organization

#### 1. Portfolio & Demand Management (5-7 people)

Role: Gateway between business and IT, ensures right work gets done

PORTFOLIO & DEMAND MANAGEMENT TEAM

Portfolio Manager (1 person, €80-100K)

├─ Owns: IT portfolio (all IT initiatives across organization)

├─ Responsibilities:

│   ├─ Portfolio governance (what's in portfolio, priorities, budget)

│   ├─ Portfolio Board facilitation (monthly, CTO + Business leaders + POs)

│   ├─ Investment decisions (business case review, approval recommendations)

│   ├─ Portfolio health tracking (on time? on budget? delivering value?)

│   └─ Portfolio optimization (balance: strategic vs. BAU, innovation vs. risk)

│

└─ Does NOT: Manage individual projects/products (that's POs/stream teams)

Demand Manager (1 person, €70-90K)

├─ Owns: IT demand intake and triage

├─ Responsibilities:

│   ├─ Single point of entry for all IT requests (centralized intake)

│   ├─ Demand capture (standardized request forms, initial assessment)

│   ├─ Triage and routing (IT request → right team/PO)

│   ├─ Demand pipeline visibility (what's coming, volume, trends)

│   └─ Capacity planning input (demand vs. IT capacity)

│

└─ Does NOT: Prioritize within product backlog (that's PO's job)

Business Relationship Managers (2-3 people, €60-80K each)

├─ Owns: Relationship between business units and IT

├─ Assignment: One BRM per major business unit

│   ├─ BRM 1: Shipping Business Unit

│   ├─ BRM 2: Ports Business Unit (Cars + Containers/Trailers)

│   └─ BRM 3: Corporate Functions (Finance, HR, Commercial)

│

├─ Responsibilities:

│   ├─ Business unit liaison (understand business needs, priorities, pain points)

│   ├─ Demand aggregation (collect requests from business unit, consolidate)

│   ├─ Stakeholder management (keep business informed of IT delivery)

│   ├─ Satisfaction management (is business happy with IT service?)

│   └─ Strategic planning input (business unit strategy → IT implications)

│

└─ Collaboration:

├─ With Product Owners: Share business insights, help prioritize

├─ With Portfolio Manager: Feed business needs into portfolio decisions

└─ With business leaders: Regular check-ins (monthly/quarterly)

PMO Lead + Coordinators (1-2 people, €60-80K)

├─ Owns: Program/project governance and reporting

├─ Responsibilities:

│   ├─ Portfolio reporting (dashboards, status, executive reporting)

│   ├─ Governance framework (stage gates, decision points, standards)

│   ├─ Risk and issue management (portfolio-level risks)

│   ├─ Benefits tracking (are we delivering promised value?)

│   └─ Process compliance (are teams following agreed processes?)

│

└─ Does NOT: Manage individual projects (that's POs and teams)

Exception: Large cross-cutting programs (multi-team, multi-year)

#### 2. Business Process Optimization (4-6 people)

Role: Improve business processes (operational excellence), not just IT systems

BUSINESS PROCESS OPTIMIZATION TEAM

Process Excellence Manager (1 person, €80-100K)

├─ Owns: Enterprise process optimization strategy

├─ Responsibilities:

│   ├─ Process maturity assessment (where are we today?)

│   ├─ Process improvement roadmap (priorities for optimization)

│   ├─ Process governance (process ownership, standards, documentation)

│   ├─ Lean/Six Sigma methodology (organizational capability building)

│   └─ Coordinate with IT (process changes → IT system implications)

Process Analysts (2-3 people, €60-80K each)

├─ Domain-specialized:

│   ├─ Analyst 1: Shipping & Ports processes

│   ├─ Analyst 2: Cargo & Logistics processes

│   └─ Analyst 3: Support processes (Finance, HR, Commercial)

│

├─ Responsibilities:

│   ├─ Process mapping (current state, document as-is processes)

│   ├─ Process analysis (identify inefficiencies, bottlenecks, waste)

│   ├─ Future state design (design to-be processes)

│   ├─ Process improvement projects (lead Kaizen events, process redesigns)

│   └─ Coordinate with BAs (process design → IT requirements)

│

└─ Typical projects:

├─ "Optimize container booking process" (reduce steps from 15 to 8)

├─ "Streamline customs clearance" (reduce clearance time 30%)

└─ "Harmonize processes post-merger" (standardize Tool A and Tool B processes)

Lean Six Sigma Specialists (1-2 people, €70-90K)

├─ Owns: Advanced process improvement (complex, high-impact projects)

├─ Responsibilities:

│   ├─ Lead Six Sigma projects (DMAIC: Define, Measure, Analyze, Improve, Control)

│   ├─ Statistical analysis (process performance, variation, root causes)

│   ├─ Lean methodology (value stream mapping, waste elimination)

│   └─ Train organization (Green Belt, Yellow Belt certifications)

│

└─ Typical projects:

├─ "Reduce terminal dwell time" (complex, multi-factor optimization)

└─ "Improve on-time performance" (statistical process control, root cause analysis)

Why This Function is Separate from IT:

- Process optimization is business-driven (not IT-driven)

- Changes processes FIRST, then IT systems follow (not IT-first)

- Many process improvements don't require IT (organizational, operational changes)

- Example: "Reduce booking approval steps" may be process redesign (no IT change needed)

Collaboration with IT:

Process Optimization → IT Collaboration:

Process Analyst identifies: "Booking process inefficient (15 manual steps)"

├─ Designs future state: "Reduce to 8 steps, automate 5"

├─ Documents: Process design, business rules, automation requirements

└─ Hands off to: Business Analyst (IT) to translate into IT requirements

Business Analyst (IT) receives: Process design

├─ Works with Process Analyst: Understand business rules, validate requirements

├─ Creates: User stories, acceptance criteria (IT perspective)

└─ Stream team builds: Automation in Shipping system

Result: Business process improved (Process team led), IT enabled improvement (IT delivered)

#### 3. Change Management (3-5 people)

Role: Ensure organizational adoption of changes (process changes, IT system changes, organizational changes)

CHANGE MANAGEMENT TEAM

Change Manager (1 person, €80-100K)

├─ Owns: Enterprise change management strategy

├─ Responsibilities:

│   ├─ Change impact assessment (what's changing? who's affected?)

│   ├─ Change readiness (is organization ready for change?)

│   ├─ Stakeholder management (engage leaders, communicate changes)

│   ├─ Resistance management (identify resistance, address concerns)

│   └─ Change governance (change control board, change approval)

Organizational Change Specialists (2-3 people, €60-80K each)

├─ Assigned to major initiatives:

│   ├─ Specialist 1: New Shipping System rollout

│   ├─ Specialist 2: IT transformation (stream teams, new ways of working)

│   └─ Specialist 3: Operational transformation (post-merger integration)

│

├─ Responsibilities:

│   ├─ Stakeholder engagement (identify stakeholders, engage early and often)

│   ├─ Communication planning (what to communicate, when, how, to whom)

│   ├─ Resistance identification (who's resisting? why? how to address?)

│   ├─ Change champion network (identify and enable change champions)

│   └─ Change metrics (adoption rate, resistance level, satisfaction)

│

└─ Typical activities:

├─ Town halls (communicate change, address questions)

├─ Leadership coaching (help leaders lead change)

├─ Change impact assessments (who's affected, how much)

└─ Post-implementation reviews (did change stick? lessons learned)

Training & Adoption Lead (1 person, €60-80K)

├─ Owns: Training strategy and user adoption

├─ Responsibilities:

│   ├─ Training needs assessment (who needs training? on what?)

│   ├─ Training program design (courses, materials, delivery methods)

│   ├─ Training delivery (coordinate trainers, schedule sessions)

│   ├─ Adoption monitoring (are users using new systems/processes?)

│   └─ Reinforce adoption (coaching, support, reminders)

│

└─ Typical deliverables:

├─ Training curriculum (for new Shipping system: Basic, Advanced, Admin)

├─ Training materials (user guides, videos, quick reference cards)

├─ Train-the-trainer (enable business super users to train peers)

└─ Adoption dashboard (% users trained, % users active, satisfaction)

Why This Function is Separate from IT:

- Change management is organizational and cultural (not technical)

- Resistance to change is people issue (not technology issue)

- Change success requires business ownership (not IT-driven)

- IT delivers systems, Change Management ensures adoption

Example: New Shipping System Rollout:

IT (Stream Team):

├─ Builds new Shipping system

├─ Tests functionality

├─ Deploys to production

└─ Provides technical support

Change Management:

├─ Assesses change impact (500 users affected, major process changes)

├─ Engages stakeholders (shipping managers, operations teams)

├─ Communicates (what's changing, why, when, benefits)

├─ Develops training (100 hours of training material)

├─ Delivers training (train 500 users over 2 months)

├─ Monitors adoption (are users logging in? using features?)

├─ Addresses resistance (coaching resistant users/teams)

└─ Measures success (adoption rate 85%+ after 3 months)

Result: IT delivered working system, Change Management ensured users adopted it

#### 4. Business Excellence / Continuous Improvement (2-4 people)

Role: Drive continuous improvement culture, innovation, performance management

BUSINESS EXCELLENCE TEAM

Business Excellence Manager (1 person, €80-100K)

├─ Owns: Organizational performance and continuous improvement

├─ Responsibilities:

│   ├─ Performance framework (KPIs, metrics, targets across organization)

│   ├─ Continuous improvement culture (promote Kaizen, innovation mindset)

│   ├─ Best practice sharing (identify and disseminate best practices)

│   ├─ Benchmarking (compare our performance to industry peers)

│   └─ Innovation programs (idea management, innovation challenges)

Innovation/Improvement Leads (1-2 people, €60-80K)

├─ Responsibilities:

│   ├─ Idea management (collect improvement ideas from employees)

│   ├─ Innovation projects (pilot new approaches, test ideas)

│   ├─ Best practice identification (find what works, scale it)

│   └─ Continuous improvement events (Kaizen events, improvement workshops)

│

└─ Typical activities:

├─ Innovation challenge: "Best idea to reduce costs" (employees submit ideas)

├─ Pilot project: "Test automated yard management" (small-scale trial)

└─ Best practice scaling: "Terminal A reduced dwell time 20%, roll out to all terminals"

Performance Management Analyst (1 person, €60-80K)

├─ Responsibilities:

│   ├─ KPI definition and tracking (define metrics, collect data, report)

│   ├─ Performance dashboards (executive dashboards, operational dashboards)

│   ├─ Trend analysis (identify performance trends, early warnings)

│   └─ Root cause analysis (performance issues → investigate causes)

Why This Function is Separate from IT:

- Business performance is broader than IT performance

- Continuous improvement applies to all functions (operations, finance, HR, IT)

- Innovation includes non-IT innovations (operational innovations, business model innovations)

### BPM & Transformation - Complete Structure

HEAD OF BPM & TRANSFORMATION

Reports to: CEO

Salary: €120-150K

Team: 14-22 people

Budget: €1.5-2.2M/year

ORGANIZATION:

1. PORTFOLIO & DEMAND MANAGEMENT (5-7)

├─ Portfolio Manager

├─ Demand Manager

├─ Business Relationship Managers (2-3)

└─ PMO Lead + Coordinators (1-2)

Role: Gateway between business and IT

2. BUSINESS PROCESS OPTIMIZATION (4-6)

├─ Process Excellence Manager

├─ Process Analysts (2-3)

└─ Lean Six Sigma Specialists (1-2)

Role: Improve business processes

3. CHANGE MANAGEMENT (3-5)

├─ Change Manager

├─ Organizational Change Specialists (2-3)

└─ Training & Adoption Lead

Role: Ensure change adoption

4. BUSINESS EXCELLENCE (2-4)

├─ Business Excellence Manager

├─ Innovation/Improvement Leads (1-2)

└─ Performance Management Analyst

Role: Drive continuous improvement culture

SCOPE: Enterprise-wide (all business units, all functions including IT)

## Operating Model: BPM ↔ IT Collaboration

### How BPM and IT Work Together

Critical Success Factor: Despite organizational separation, BPM and IT must collaborate seamlessly. Here's how:

#### Weekly Coordination (Operational):

WEEKLY BPM-IT SYNC

Attendees: Head of BPM, CTO, Head of Business Solutions, Portfolio Manager

Duration: 30 minutes

Agenda:

├─ 1. Demand pipeline (10 min)

│   ├─ New requests this week

│   ├─ Priorities shifting?

│   └─ Capacity concerns?

│

├─ 2. Portfolio health (10 min)

│   ├─ Initiatives at risk

│   ├─ Escalations needed

│   └─ Dependencies blocking progress

│

└─ 3. Strategic alignment (10 min)

├─ Business priorities changing?

├─ IT capability gaps?

└─ Next month preview

#### Monthly Portfolio Board (Governance):

PORTFOLIO BOARD MEETING

Attendees: CTO, Head of BPM, All Product Owners, Business Unit Leaders, CFO

Duration: 2 hours

Frequency: Monthly

Agenda:

├─ 1. Portfolio Review (30 min)

│   ├─ Current portfolio (what's in flight)

│   ├─ Status (green/yellow/red)

│   └─ Budget vs. actuals

│

├─ 2. New Requests (30 min)

│   ├─ BPM presents new requests (business cases)

│   ├─ IT provides effort estimates

│   └─ Board discusses priorities

│

├─ 3. Prioritization Decisions (45 min)

│   ├─ What gets approved for next quarter

│   ├─ What gets deferred

│   └─ Resource allocation

│

└─ 4. Strategic Topics (15 min)

├─ Technology trends

├─ Business strategy changes

└─ Portfolio optimization opportunities

#### Quarterly Strategic Planning (Strategic):

QUARTERLY IT-BUSINESS PLANNING

Attendees: CEO, CTO, Head of BPM, Business Unit COOs, CFO

Duration: Half-day workshop

Frequency: Quarterly

Purpose: Align IT roadmap with business strategy

Activities:

├─ 1. Business strategy update (COOs present: What's our strategy?)

├─ 2. IT capability assessment (CTO: What can IT deliver?)

├─ 3. Gap analysis (BPM facilitates: Where are gaps?)

├─ 4. Roadmap alignment (Next 12 months priorities)

└─ 5. Investment decisions (Budget allocation, approvals)

### Interaction Patterns: BPM Functions ↔ IT

#### Pattern 1: Demand Management → Product Owners

DEMAND INTAKE PROCESS

Step 1: Business submits request

├─ Via: Demand intake form (standardized)

└─ To: Demand Manager (BPM)

Step 2: Demand Manager triages

├─ Reviews request (complete? clear?)

├─ Classifies: Enhancement, New capability, Bug fix, Support

├─ Routes to appropriate Product Owner

└─ Timeline: Within 2 business days

Step 3: Product Owner receives request

├─ Reviews with Business Analyst

├─ Assesses: Value, effort, priority

├─ Decides: Accept to backlog, reject, need more info

└─ Timeline: Within 1 week

Step 4: Product Owner prioritizes

├─ Adds to product backlog (if accepted)

├─ Prioritizes against other work

├─ Schedules for sprint (based on priority)

└─ Feedback to business: When can you expect this?

Step 5: Portfolio Manager oversees

├─ Tracks: Demand volume, trends, capacity

├─ Escalates: If POs overloaded, capacity issues

└─ Reports: Monthly to Portfolio Board

Key Principle:

- BPM (Demand Manager) = Front door (intake and triage)

- IT (Product Owners) = Decision makers (prioritization and delivery)

- BPM does NOT prioritize Product Owner's backlog (that's PO's job)

#### Pattern 2: Process Optimization → Business Analysts

PROCESS IMPROVEMENT → IT IMPLEMENTATION

Step 1: Process Analyst (BPM) identifies opportunity

├─ Example: "Booking process has 15 manual steps, could be 8"

├─ Conducts: Process analysis, future state design

└─ Output: Process design document (business perspective)

Step 2: Collaboration with Business Analyst (IT)

├─ Process Analyst presents: Future state process

├─ Business Analyst translates: Process → IT requirements

├─ Joint workshop: Validate IT can support future process

└─ Output: Requirements document (IT perspective)

Step 3: Business Analyst → Product Owner

├─ BA presents requirements to PO

├─ PO prioritizes in backlog

└─ Stream team builds when prioritized

Step 4: Process Analyst monitors implementation

├─ Participates in: UAT, design reviews

├─ Ensures: IT solution matches process design

└─ Post-implementation: Measures process improvement achieved

COLLABORATION POINTS:

├─ BPM leads: Process design (WHAT should process be?)

├─ IT delivers: System capability (HOW to enable process?)

└─ Partnership: Process Analyst + Business Analyst work together

#### Pattern 3: Change Management → Stream Teams

CHANGE MANAGEMENT ENGAGEMENT

For major IT releases (e.g., new Shipping system):

Months Before Go-Live:

├─ Change Specialist (BPM) engages with Product Owner (IT)

├─ Assesses: Change impact, affected users, training needs

├─ Develops: Communication plan, training plan, adoption strategy

└─ Regular sync: Weekly meetings (Change Specialist + PO + BA)

1-2 Months Before Go-Live:

├─ Change Specialist: Stakeholder engagement (town halls, workshops)

├─ Training Lead: Develops training materials (with input from BA)

├─ Communication: Regular updates to affected users

└─ Readiness: Go/no-go checklist (is organization ready?)

Go-Live:

├─ IT Team: Technical deployment

├─ Change Team: On-site support (hand-holding users)

└─ Application Support: Technical support (troubleshooting)

Post Go-Live (Weeks 1-4):

├─ Change Specialist: Adoption monitoring (are users using system?)

├─ Change Specialist: Resistance management (coaching resistant users)

├─ Training Lead: Reinforcement training (refreshers, advanced topics)

└─ Metrics: Adoption rate, satisfaction, issues

Post Go-Live (Month 2-3):

├─ Change Specialist: Lessons learned (what went well, what didn't)

├─ Hand-off: Change team → Application Support (ongoing)

└─ Project closure: Change management complete

DIVISION OF LABOR:

├─ IT builds system (functionality)

├─ Change Management ensures adoption (people)

└─ Application Support handles ongoing (BAU)

### Governance: BPM ↔ IT Decision Rights

Clear decision rights prevent conflict:

| Decision | BPM Decides | IT Decides | Jointly Decide |
| --- | --- | --- | --- |
| Portfolio |  |  |  |
| Which requests enter portfolio | ✅ (Portfolio Manager) | Consulted | Portfolio Board |
| Portfolio priorities (strategic) |  |  | ✅ (Portfolio Board: BPM + IT + Business) |
| Budget allocation (portfolio level) |  |  | ✅ (Portfolio Board) |
| Demand |  |  |  |
| Request intake and triage | ✅ (Demand Manager) |  |  |
| Routing to right PO | ✅ (Demand Manager) | Consulted |  |
| Product Backlog |  |  |  |
| What goes in backlog |  | ✅ (Product Owner) | BPM provides input |
| Backlog priorities |  | ✅ (Product Owner) | BPM provides input |
| Sprint commitments |  | ✅ (Product Owner + Team) |  |
| Process |  |  |  |
| Process design (future state) | ✅ (Process Analyst) | Consulted (BA) |  |
| IT requirements (from process) | Consulted | ✅ (Business Analyst) | Joint workshops |
| Change |  |  |  |
| Change approach (strategy) | ✅ (Change Manager) | Consulted |  |
| Training content | ✅ (Training Lead) | IT provides input (BA, PO) |  |
| Go/no-go (readiness) |  |  | ✅ (Change Manager + PO + Business) |
| Performance |  |  |  |
| Business KPIs | ✅ (Business Excellence) |  |  |
| IT delivery metrics |  | ✅ (IT) |  |
| Portfolio performance |  |  | ✅ (Portfolio Manager + IT) |

## Pros and Cons: BPM Separate vs. Integrated

### Model A: BPM Integrated in IT

Pros: ✅ Faster decision-making (no organizational boundary) ✅ Tighter alignment (portfolio and delivery under same leader) ✅ Lower overhead (fewer management layers) ✅ Simpler governance (CTO accountable for both planning and delivery) ✅ Better for smaller organizations (<500 people)

Cons: ❌ BPM may be perceived as "IT-biased" (not independent business advocate) ❌ Limited scope (BPM focused primarily on IT, not broader business transformation) ❌ Political: BPM leadership may resist reporting to IT (wants seat at executive table) ❌ Risk: CTO overloaded (portfolio + delivery + platforms + data + architecture)

### Model B: BPM Separate from IT ⭐

Pros: ✅ Independent business advocacy (BPM represents business, not IT-biased) ✅ Broader scope (BPM can do non-IT process optimization, organizational change) ✅ Political: BPM has executive seat (signals importance, attracts talent) ✅ Clear separation (BPM = what/why, IT = how) ✅ Balanced governance (BPM and IT as equals, jointly govern portfolio) ✅ Better for larger/complex organizations (500+ people, post-merger integration)

Cons: ❌ Coordination overhead (need strong collaboration between BPM and IT) ❌ Risk of misalignment (if BPM and IT don't collaborate well) ❌ Higher cost (separate executive function, potentially more people) ❌ Governance complexity (decision rights must be very clear to avoid conflict)

## My Recommendation for You: Model B (BPM Separate) ⭐

Why Model B is Better for Your Context:

- Your Industry (Logistics):

  - Operational excellence is strategic differentiator

  - Business process optimization extends far beyond IT (terminal operations, shipping processes, customs procedures)

  - BPM naturally has broader mandate than just IT

- Your Situation (Post-Merger):

  - Process harmonization critical (Tool A vs. Tool B, Company A ways vs. Company B ways)

  - Change management essential (organizational and cultural integration)

  - BPM as neutral facilitator (not IT-driven, business-driven)

- Your Organization Size (~500-700 total employees):

  - Large enough to justify separate BPM function

  - Mature enough to handle coordination overhead

- Political Reality:

  - Current Head of BPM likely has executive aspirations

  - Placing under CTO may create resistance/friction

  - Separate BPM signals organizational commitment to transformation

- IT Transformation Context:

  - You're moving IT from project to product model (major change)

  - Having BPM as external "change agent" helps (not IT transforming itself alone)

  - BPM can facilitate IT transformation (change management for new ways of working)

## Implementation: Creating Separate BPM Function

### Transition Plan (If BPM Currently in IT)

MONTH 1-3: DESIGN & APPROVAL

Week 1-2: Design BPM Function

├─ Define scope (portfolio, demand, process, change, excellence)

├─ Define structure (4 subfunctions, 14-22 people)

├─

## Implementation: Creating Separate BPM Function (continued)

### Transition Plan (If BPM Currently in IT) (continued)

MONTH 1-3: DESIGN & APPROVAL (continued)

Week 1-2: Design BPM Function (continued)

├─ Define scope (portfolio, demand, process, change, excellence)

├─ Define structure (4 subfunctions, 14-22 people)

├─ Define budget (€1.5-2.2M/year)

└─ Define decision rights (BPM vs. IT, clear boundaries)

Week 3-4: Business Case

├─ Value proposition: What does separate BPM enable?

│   ├─ Broader transformation scope (beyond IT)

│   ├─ Independent business advocacy

│   ├─ Enterprise-wide process optimization

│   └─ Better change management

│

├─ Cost analysis:

│   ├─ Incremental cost: ~€500K/year (if expanding beyond current BPM)

│   ├─ Current: 3-5 people in BPM (€300-400K)

│   ├─ Target: 14-22 people (€1.5-2.2M)

│   ├─ Net increase: €1.1-1.8M

│

└─ ROI:

├─ Better portfolio decisions → €500K-1M/year (avoid wrong investments)

├─ Process optimization → €1-2M/year (operational efficiency)

├─ Change adoption → €500K-1M/year (higher adoption = higher value)

└─ Total value: €2-4M/year vs. €1.1-1.8M investment = Positive ROI

Week 5-8: Stakeholder Engagement

├─ CTO: Discuss separation (ensure buy-in, address concerns)

├─ Current Head of BPM: Career discussion (promotion to executive level?)

├─ COOs/Business Leaders: Get input (do they want independent BPM?)

└─ CFO: Budget approval

Week 9-12: Executive Approval

├─ Present to CEO and executive team

├─ Propose: Create Head of BPM & Transformation role (peer to CTO)

├─ Get approval: Headcount, budget, organizational change

└─ Announce: Organizational change (internal communication)

MONTH 4-6: TRANSITION

Month 4: Leadership Hiring

├─ Option 1: Promote current Head of BPM → Head of BPM & Transformation ✅

│   └─ If current person has capability and aspiration

│

├─ Option 2: External hire for Head of BPM & Transformation

│   └─ If need more senior leader or different skillset

│

└─ Timeline: 1-2 months to hire/transition

Month 5-6: Team Formation

├─ Identify existing BPM resources (who moves to new function)

├─ Recruit additional resources (process analysts, change specialists, etc.)

├─ Establish team structure (4 subfunctions)

└─ Physical/virtual setup (office space, tools, systems)

Month 5-6: Governance Setup

├─ Define BPM-IT collaboration model (weekly syncs, monthly Portfolio Board)

├─ Document decision rights (who decides what)

├─ Establish processes (demand intake, portfolio governance, etc.)

└─ Communication: Announce new ways of working

MONTH 7-9: OPERATIONALIZATION

Month 7: Soft Launch

├─ BPM function operational

├─ Initial focus: Portfolio & Demand Management (highest priority)

├─ IT continues as before (minimal disruption)

└─ Learn: What's working, what needs adjustment

Month 8-9: Scale Up

├─ Add Process Optimization projects

├─ Add Change Management for major initiatives

├─ Add Business Excellence initiatives

└─ Full operating model

Month 10-12: Optimization

├─ Refine BPM-IT collaboration (based on learnings)

├─ Adjust governance (if needed)

├─ Scale team (add remaining headcount)

└─ Measure success (portfolio outcomes, process improvements, adoption rates)

MONTH 12: REVIEW

├─ Evaluate: Is separate BPM working?

├─ Metrics: Portfolio health, process improvements, change adoption

├─ Adjustments: Fine-tune based on Year 1 learnings

└─ Year 2 planning: Continue scaling

### Critical Success Factors for Separate BPM

1. Strong BPM-IT Partnership:

AVOID: BPM vs. IT dynamic (adversarial)

├─ "BPM wants everything, IT can't deliver"

├─ "IT doesn't understand business, BPM has to force them"

└─ Finger-pointing, blame, friction

ACHIEVE: BPM + IT partnership (collaborative)

├─ "BPM represents business needs, IT delivers capabilities"

├─ "BPM and IT jointly optimize portfolio"

├─ "BPM sets direction, IT executes, both accountable for results"

└─ Trust, respect, shared goals

HOW TO BUILD PARTNERSHIP:

├─ Weekly coordination (Head of BPM + CTO)

├─ Joint governance (Portfolio Board with both BPM and IT)

├─ Co-location (if possible, BPM and IT teams sit together)

├─ Shared metrics (both measured on portfolio outcomes, not just their own)

└─ Culture: "We're one team serving the business"

2. Clear Decision Rights (Avoid Ambiguity):

DOCUMENT CLEARLY:

├─ What BPM decides (intake, triage, process design, change approach)

├─ What IT decides (backlog priorities, technical design, delivery)

├─ What both decide jointly (portfolio priorities, strategic investments)

└─ Publish: Decision rights matrix (accessible to all)

WHEN CONFLICT ARISES:

├─ First: BPM and IT leaders discuss (resolve at lowest level)

├─ If unresolved: Escalate to CEO (CEO decides)

├─ Document: Decision and rationale (precedent for future)

└─ Adjust: Update decision rights if pattern emerges

3. Avoid Duplicate Work:

RISK: BPM and IT both doing similar work

├─ Example: BPM Process Analysts designing future state

│           IT Business Analysts also designing future state

│           → Duplicate effort, confusion, rework

SOLUTION: Clear handoffs

├─ BPM Process Analyst: Designs business process (WHAT should happen)

│   └─ Output: Process flow, business rules, performance targets

│

├─ Handoff: Joint workshop (Process Analyst + Business Analyst)

│   └─ Validate: IT can support process, identify system implications

│

└─ IT Business Analyst: Designs IT requirements (HOW IT supports process)

└─ Output: User stories, system requirements, acceptance criteria

PRINCIPLE:

├─ BPM = Business view (process, people, organization)

└─ IT = System view (requirements, design, implementation)

No overlap, clear boundary

4. Executive Commitment:

CEO MUST:

├─ Signal importance of BPM (elevating to executive level shows commitment)

├─ Hold both accountable (BPM and IT jointly deliver transformation)

├─ Resolve conflicts (if BPM and IT can't agree, CEO decides)

└─ Communicate: "BPM and IT are partners, both critical"

CTO MUST:

├─ Embrace partnership (not view BPM as "interference")

├─ Collaborate actively (weekly syncs, joint governance)

├─ Respect BPM expertise (process optimization, change management)

└─ Focus IT on delivery (let BPM handle business relationship, IT delivers)

HEAD OF BPM MUST:

├─ Earn IT's trust (understand IT constraints, be realistic)

├─ Add value (not just "more governance," actually help business and IT)

├─ Collaborate (not dictate to IT)

└─ Measure results (prove BPM is delivering value)

## Revised Organization Chart: BPM Separate

### Complete Organization Structure

━━━━━━━━━━━━━━━━━━━━━━━━━━━━━━━━━━━━━━━━━━━━━━━━━━━━━━━━━━━

CEO

━━━━━━━━━━━━━━━━━━━━━━━━━━━━━━━━━━━━━━━━━━━━━━━━━━━━━━━━━━━

│

┌────────────────────┼────────────────────┬──────────────┐

│                    │                    │              │

↓                    ↓                    ↓              ↓

┌───────────────┐    ┌───────────────┐    ┌──────────────┐ ┌────────────┐

│ CTO           │    │ Head of BPM   │    │ COO          │ │ CFO, CHRO, │

│ (IT Apps)     │    │ & Transform   │    │ (Operations) │ │ etc.       │

│               │    │ ⭐ NEW        │    │              │ │            │

└───────┬───────┘    └───────┬───────┘    └──────────────┘ └────────────┘

│                    │

│                    │

↓                    ↓

┌─────────────────────────────────────────────────────────────┐

│ CTO - IT APPLICATIONS ORGANIZATION                          │

├─────────────────────────────────────────────────────────────┤

│                                                              │

│ • Head of Business Solutions & Delivery (85-100)            │

│   ├─ 8 Stream-Aligned Teams (68-83)                        │

│   │   ├─ Shipping Solutions (12-15)                        │

│   │   ├─ Ports - Cars (10-12)                              │

│   │   ├─ Ports - Containers & Trailers (10-12)            │

│   │   ├─ Customs & Compliance (8-10)                       │

│   │   ├─ Customer & Commercial (10-12)                     │

│   │   ├─ Cargo & Transport (10-12)                         │

│   │   ├─ Billing & Finance (8-10)                          │

│   │   └─ HR & Workforce (6-8)                              │

│   │                                                          │

│   └─ BA Center of Excellence (6-7 BAs)                     │

│       └─ NO Portfolio/Demand Mgmt ⭐ (moved to BPM)        │

│                                                              │

│ • Head of Enterprise Architecture (8-10)                    │

│                                                              │

│ • Head of Data & AI (11-14)                                │

│                                                              │

│ • Head of Platform Engineering (36-45)                      │

│   ├─ Application Support (18-22)                           │

│   ├─ Integration Platform Team (12-15)                     │

│   └─ DevOps & Infrastructure (6-8)                         │

│                                                              │

│ • Head of Vendor & Partner Management (6-9)                │

│                                                              │

│ TOTAL IT: 146-178 people                                   │

└─────────────────────────────────────────────────────────────┘

┌─────────────────────────────────────────────────────────────┐

│ HEAD OF BPM & TRANSFORMATION ⭐                             │

├─────────────────────────────────────────────────────────────┤

│                                                              │

│ • Portfolio & Demand Management (5-7)                       │

│   ├─ Portfolio Manager                                      │

│   ├─ Demand Manager                                         │

│   ├─ Business Relationship Managers (2-3)                   │

│   └─ PMO Lead + Coordinators (1-2)                         │

│                                                              │

│ • Business Process Optimization (4-6)                       │

│   ├─ Process Excellence Manager                             │

│   ├─ Process Analysts (2-3)                                │

│   └─ Lean Six Sigma Specialists (1-2)                      │

│                                                              │

│ • Change Management (3-5)                                   │

│   ├─ Change Manager                                         │

│   ├─ Organizational Change Specialists (2-3)               │

│   └─ Training & Adoption Lead                               │

│                                                              │

│ • Business Excellence / Continuous Improvement (2-4)        │

│   ├─ Business Excellence Manager                            │

│   ├─ Innovation/Improvement Leads (1-2)                    │

│   └─ Performance Management Analyst                         │

│                                                              │

│ TOTAL BPM: 14-22 people                                    │

└─────────────────────────────────────────────────────────────┘

━━━━━━━━━━━━━━━━━━━━━━━━━━━━━━━━━━━━━━━━━━━━━━━━━━━━━━━━━━━

COMBINED TRANSFORMATION ORGANIZATION:

• IT Applications (CTO): 146-178 people

• BPM & Transformation: 14-22 people

━━━━━━━━━━━━━━━━━━━━━━━━━━━━━━━━━━━━━━━━━━━━━━━━━━━━━━━━━━━

TOTAL: 160-200 people

(Current baseline: ~100 IT + ~3-5 BPM = ~105 total)

(Growth: +55-95 people over 24 months)

━━━━━━━━━━━━━━━━━━━━━━━━━━━━━━━━━━━━━━━━━━━━━━━━━━━━━━━━━━━

## Budget Impact: BPM Separate

### Additional Investment (vs. BPM Integrated Model)

Current BPM (assumed baseline):

- 3-5 people

- Mostly focused on IT portfolio/demand

- Budget: €300-400K/year

Target BPM & Transformation:

- 14-22 people (mid-point: 18)

- Broader scope (portfolio, process, change, excellence)

- Budget: €1.5-2.2M/year (mid-point: €1.85M)

Incremental Investment:

- Headcount: +11-15 people

- Budget: +€1.15-1.8M/year (mid-point: +€1.45M)

Year 1 Phased Build:

YEAR 1 BPM BUILD (Phased)

Q1 (Month 1-3): Foundation

├─ Hire Head of BPM & Transformation (Month 1)

├─ Hire Portfolio Manager, Demand Manager (Month 2-3)

├─ Transfer existing BPM staff (3-5 people)

└─ Headcount end of Q1: 6-8 people

Cost Q1: ~€150K (partial year)

Q2 (Month 4-6): Core Build

├─ Hire BRMs (2)

├─ Hire Process Excellence Manager, Process Analysts (2-3)

└─ Headcount end of Q2: 10-13 people

Cost Q2: ~€250K

Q3 (Month 7-9): Change Management

├─ Hire Change Manager

├─ Hire Change Specialists (2)

├─ Hire Training Lead

└─ Headcount end of Q3: 14-17 people

Cost Q3: ~€300K

Q4 (Month 10-12): Complete

├─ Hire Business Excellence Manager

├─ Hire remaining staff (Performance Analyst, Innovation Leads, etc.)

└─ Headcount end of Q4: 18-20 people

Cost Q4: ~€350K

YEAR 1 TOTAL COST: ~€1.05M (partial year, phased hiring)

YEAR 2 ONGOING: ~€1.85M (full year, complete team)

### Combined Transformation Budget (IT + BPM)

Total Transformation Investment (24 months):

| Component | Year 1 | Year 2 | Year 3+ Annual |
| --- | --- | --- | --- |
| IT Transformation (from earlier) | €2.8-3.2M | €2.9M | €2.5-3M |
| Application Support (from earlier) | €1.4-1.7M | €1.2-1.4M | €1.2-1.4M |
| BPM Expansion ⭐ (new) | €1.05M | €1.85M | €1.85M |
| TOTAL TRANSFORMATION | €5.25-5.95M | €5.95-7.15M | €5.55-6.25M |

Mid-Point Total:

- Year 1: €5.6M

- Year 2: €6.55M

- Year 3+: €5.9M/year ongoing

### ROI: BPM Separate Model

Value Creation from BPM Function:

BPM VALUE REALIZATION

1. BETTER PORTFOLIO DECISIONS

├─ Current: Ad-hoc prioritization, some investments fail

├─ Future: Rigorous portfolio governance, business cases, ROI tracking

├─ Value: Avoid 2-3 low-value projects/year (€300K each)

└─ Annual value: €600-900K

2. PROCESS OPTIMIZATION

├─ Current: Limited process improvement (IT-only focus)

├─ Future: Dedicated process analysts, Lean Six Sigma

├─ Projects: 8-12 process improvement projects/year

│   ├─ Example: Reduce booking process time 30% → €200K labor savings

│   ├─ Example: Optimize terminal operations → €300K efficiency gain

│   └─ Example: Streamline customs clearance → €400K (faster clearance = revenue)

└─ Annual value: €1-2M (process improvements)

3. BETTER CHANGE ADOPTION

├─ Current: IT delivers systems, adoption varies (50-70%)

├─ Future: Dedicated change management, adoption rates 80-90%

├─ Impact: Higher adoption = higher value from IT investments

├─ Example: €3M IT investment, 70% adoption = €2.1M value realized

│           Same investment, 85% adoption = €2.55M value realized

│           Difference: €450K additional value per major initiative

└─ Annual value: €500K-1M (2-3 major initiatives/year × improved adoption)

4. OPERATIONAL EXCELLENCE CULTURE

├─ Innovation programs (employee ideas, pilots)

├─ Best practice sharing (scale what works)

├─ Performance management (data-driven decisions)

└─ Annual value: €300-500K (harder to quantify, but real)

TOTAL BPM VALUE: €2.4-4.4M/year (mid-point: €3.4M)

BPM INVESTMENT: €1.85M/year (ongoing)

NET VALUE: €550K-2.55M/year

ROI: 30-138% (mid-point: 84%)

Combined Transformation ROI (IT + Support + BPM):

3-YEAR TRANSFORMATION VALUE

INVESTMENT:

├─ Year 1: €5.6M

├─ Year 2: €6.55M

├─ Year 3: €5.9M

└─ Total 3-year: €18.05M

VALUE:

├─ IT Transformation: €3.5M (Y1) + €9M (Y2) + €13M (Y3) = €25.5M

├─ Application Support: €2.5M (Y1) + €2.5M (Y2) + €2.5M (Y3) = €7.5M

├─ BPM Expansion: €3.4M (Y1) + €3.4M (Y2) + €3.4M (Y3) = €10.2M

└─ Total 3-year: €43.2M

NET BENEFIT: €43.2M - €18.05M = €25.15M

ROI: 139%

PAYBACK: ~18 months

The BPM expansion pays for itself and enhances the IT transformation ROI by ensuring better portfolio decisions, process improvements, and change adoption.

## Alternative: Hybrid Model (If Full Separation Too Big a Change)

If fully separating BPM feels too disruptive or politically challenging, consider a hybrid approach:

### Model C: BPM Partially Separate (Compromise)

CEO

│

├─ CTO

│   ├─ Head of Business Solutions & Delivery

│   ├─ Head of Enterprise Architecture

│   ├─ Head of Data & AI

│   ├─ Head of Platform Engineering

│   ├─ Head of Vendor Management

│   │

│   └─ Portfolio & Demand Management ⭐ (stays in IT)

│       ├─ Portfolio Manager

│       ├─ Demand Manager

│       └─ BRMs (2-3)

│

└─ Head of BPM & Business Excellence ⭐ (Separate, peer to CTO)

├─ Business Process Optimization (4-6)

├─ Change Management (3-5)

└─ Business Excellence (2-4)

TOTAL BPM SEPARATE: 9-15 people (not 14-22)

Rationale for Hybrid:

- Portfolio & Demand stays in IT: Close coupling with delivery (faster decisions)

- Process, Change, Excellence separate: Broader business mandate (not IT-only)

- Lower cost: Only 9-15 people separate (vs. 14-22), saves €500K/year

- Easier transition: Less disruptive, smaller organizational change

When Hybrid Makes Sense:

- Political compromise (BPM gets some independence, IT keeps portfolio control)

- Smaller organization (<500 people) - full separation overhead too high

- Testing waters (start hybrid, fully separate later if working well)

Hybrid Operating Model:

IT (CTO) owns:

├─ Portfolio governance (what gets built)

├─ Demand management (intake, routing)

└─ IT delivery (building and running systems)

BPM (separate) owns:

├─ Process optimization (improving business processes)

├─ Change management (ensuring adoption)

└─ Business excellence (continuous improvement culture)

Collaboration:

├─ Monthly: Portfolio Board (CTO + Head of BPM + Business Leaders)

├─ Weekly: CTO + Head of BPM sync

└─ Project-level: Process Analysts + BAs collaborate, Change Specialists + POs collaborate

## Decision Summary: Three Models

### Quick Comparison

| Aspect | Model A: BPM in IT | Model B: BPM Fully Separate ⭐ | Model C: Hybrid |
| --- | --- | --- | --- |
| BPM Team Size | 5-7 (in IT org) | 14-22 (separate) | 9-15 (separate) |
| BPM Scope | IT portfolio/demand | Enterprise transformation | Process/change/excellence |
| Portfolio Mgmt | In IT ✅ | Separate | In IT ✅ |
| Process Optimization | Limited (IT-only) | Broad (enterprise-wide) ✅ | Broad ✅ |
| Change Management | Limited (IT-focused) | Dedicated team ✅ | Dedicated team ✅ |
| Cost | Lower (€300-400K) | Higher (€1.85M) | Medium (€1.2M) |
| Complexity | Lower (simpler org) | Higher (coordination needed) | Medium |
| Political | May disappoint BPM | BPM has executive seat ✅ | Compromise |
| Best For | Small org, IT-centric | Large org, transformation | Medium org, testing |

## My Final Recommendation

### For Your Context: Model B (BPM Fully Separate) ⭐

Reasons:

- Logistics Industry: Process optimization is strategic (terminal efficiency, shipping processes, customs) - broader than IT

- Post-Merger: Significant change management and process harmonization needed - dedicated focus required

- Organization Size: ~700 people total - large enough to justify separate BPM function

- Political Reality: If current BPM leader expects/wants executive role, separation is natural career progression

- Transformation Scope: You're not just transforming IT, you're transforming entire business operations - BPM should lead that broadly

Implementation Approach:

- Month 1-3: Design and get approval

- Month 4-6: Hire Head of BPM, form core team (Portfolio, Demand, Process)

- Month 7-12: Scale to full team (Change, Excellence)

- Month 12: Review and refine

Key Success Factors:

- Strong BPM-CTO partnership (weekly syncs, joint Portfolio Board)

- Clear decision rights (documented and communicated)

- Measure both on outcomes (shared metrics, shared accountability)

- Culture of collaboration (not BPM vs. IT, but BPM + IT serving business)

## Communication Plan: Announcing BPM Separation

### Announcement Messaging

To Executive Team:

WHY WE'RE CREATING SEPARATE BPM FUNCTION

Business Context:

├─ We're undergoing major transformation (IT, processes, post-merger integration)

├─ Current BPM function (3-5 people, IT-focused) insufficient for scope

└─ Need enterprise-wide transformation capability

What's Changing:

├─ Creating new Head of BPM & Transformation role (peer to CTO, reports to CEO)

├─ Expanding BPM from 5 → 18 people (portfolio, process, change, excellence)

├─ Investment: €1.85M/year ongoing

└─ Expected value: €2.4-4.4M/year (process improvements, better adoption, portfolio optimization)

Why Separate from IT:

├─ Broader mandate (beyond IT - process optimization across all operations)

├─ Independent business advocacy (BPM represents business needs to IT)

├─ Executive-level importance (signals organizational commitment)

└─ Better governance (BPM and IT as equal partners, balanced decision-making)

What Doesn't Change:

├─ IT still delivers systems and capabilities

├─ Product Owners still prioritize backlogs

└─ Business still gets excellent service (better coordination between BPM and IT)

Timeline:

├─ Month 1-3: Design and approval

├─ Month 4: Hire Head of BPM & Transformation

├─ Month 4-12: Build team

└─ Month 12: Fully operational

Request: Approve €1.85M budget and 18 headcount for BPM & Transformation

To IT Organization:

WHAT BPM SEPARATION MEANS FOR IT

What's Happening:

├─ BPM function (currently small, IT-focused) expanding and becoming separate

├─ Will report to CEO (peer to CTO), not part of IT organization

└─ Timeline: Next 9-12 months

What This Means for You:

├─ Portfolio & Demand Management moves to BPM (no longer in IT org)

├─ You'll work WITH BPM (they represent business needs, you deliver solutions)

├─ Stream teams continue as planned (no change to product teams)

└─ Product Owners still prioritize (BPM doesn't dictate your backlog)

Why This is Good:

├─ BPM focuses on business relationship, you focus on delivery

├─ Clear separation: BPM = what/why, IT = how

├─ You're not managing portfolio politics (BPM handles that)

└─ Better business advocacy (BPM represents business needs independently)

How You'll Collaborate:

├─ Weekly: BPM-IT leadership sync

├─ Monthly: Portfolio Board (joint governance)

├─ Daily: BAs collaborate with Process Analysts, POs work with BRMs

└─ Culture: Partnership (BPM + IT serve business together)

What Doesn't Change:

├─ Your roles and responsibilities (developers develop, POs own products)

├─ Your decision authority (POs still prioritize, teams still self-organize)

└─ Your focus: Deliver excellent solutions to business

To Business Stakeholders:

NEW BPM & TRANSFORMATION ORGANIZATION

What We're Creating:

├─ Dedicated BPM & Transformation organization (18 people)

├─ Led by Head of BPM & Transformation (executive-level)

├─ Four focus areas:

│   ├─ Portfolio & Demand: Gateway to IT (your single point of contact)

│   ├─ Process Optimization: Improve your business processes

│   ├─ Change Management: Ensure successful adoption of changes

│   └─ Business Excellence: Drive continuous improvement culture

What This Means for You:

├─ Single point of contact for all IT requests (Demand Manager, Business Relationship Managers)

├─ Better process optimization (dedicated team to improve your operations)

├─ Better change support (when new systems launch, change team helps adoption)

└─ Your voice heard (BPM represents your needs to IT independently)

How to Engage:

├─ IT requests: Contact Demand Manager or your Business Relationship Manager

│   ├─ Shipping BU: BRM John (john@company.com)

│   ├─ Ports BU: BRM Jane (jane@company.com)

│   └─ Corporate: BRM Bob (bob@company.com)

│

├─ Process improvements: Contact Process Excellence Manager

├─ Change support: Contact Change Manager (for major initiatives)

└─ Ideas/innovations: Contact Business Excellence Manager

Timeline:

├─ Month 4: New organization launching

├─ Month 4-6: Team building

└─ Month 6+: Fully operational (all services available)

## Final Answer to Your Question

### Yes, It Makes Sense to Keep BPM Separate ⭐

Functions That Should Be in BPM (Separate from IT):

- ✅ Portfolio & Demand Management - Gateway between business and IT

- ✅ Business Process Optimization - Improve operational processes (broader than IT)

- ✅ Change Management - Ensure adoption of changes (organizational, not just technical)

- ✅ Business Excellence - Continuous improvement culture, innovation, performance management

What Stays in IT:

- Stream-aligned teams (product development and delivery)

- Business Analysts (translate requirements to IT solutions)

- Architecture (technical architecture and design)

- Platforms (integration, data, DevOps)

- Application Support (keep systems running)

- Vendor Management (manage technology vendors)

Why This Works:

- Clear separation: BPM = business transformation, IT = technology delivery

- Balanced governance: BPM and IT as equal partners (neither dominates)

- Broader scope: BPM can optimize processes beyond IT (operations, organizational)

- Political win: BPM has executive seat (attracts talent, signals importance)

Critical Success Factor: Strong BPM-IT partnership

- If BPM and IT collaborate well → Excellent outcomes (business gets best of both)

- If BPM and IT compete/conflict → Poor outcomes (political, inefficiency, frustration)

- CEO must enforce: "BPM and IT are partners, jointly accountable"

## You Now Have Three Models - Choose What Fits Your Context

Model A (BPM in IT): Best for small organizations, IT-centric scope, simpler governance Model B (BPM fully separate): ⭐ Best for you - Large organization, broad transformation, political necessity Model C (Hybrid): Compromise if full separation too disruptive

Whichever you choose, you now have:

- ✅ Complete organizational design

- ✅ Role definitions and responsibilities

- ✅ Operating model (how BPM and IT collaborate)

- ✅ Implementation roadmap

- ✅ Budget and ROI

- ✅ Communication plan

**You're fully equipped to make this

## You Now Have Three Models - Choose What Fits Your Context (continued)

Whichever you choose, you now have:

- ✅ Complete organizational design

- ✅ Role definitions and responsibilities

- ✅ Operating model (how BPM and IT collaborate)

- ✅ Implementation roadmap

- ✅ Budget and ROI

- ✅ Communication plan

You're fully equipped to make this decision and execute. 🎯

## Additional Practical Guidance

### Handling Common Challenges with Separate BPM

Let me address potential issues you might face:

#### Challenge 1: "BPM Creates Bureaucracy"

Risk: BPM becomes "governance police" (slows things down, adds process overhead)

Symptoms:

- Every IT request requires multiple BPM approvals

- Long wait times (business submits request, sits in BPM queue for weeks)

- Excessive documentation requirements

- Teams complain: "BPM slowing us down"

Prevention:

LIGHTWEIGHT GOVERNANCE APPROACH

Demand Intake:

├─ Simple form (1-2 pages, not 20 pages)

├─ Fast triage (within 2 business days, not 2 weeks)

├─ Self-service portal (business can see status, not black box)

└─ Escalation path (if urgent, fast-track process)

Portfolio Decisions:

├─ Delegate to Product Owners (for minor enhancements)

├─ Portfolio Board only for major investments (>€50K or strategic)

├─ Monthly cadence (decisions made monthly, not quarterly)

└─ Clear criteria (transparent decision-making, not arbitrary)

Process Optimization:

├─ Request from business (not imposed by BPM)

├─ Quick wins prioritized (80/20 rule - focus on high-impact)

├─ Pilot approach (test small, scale if successful)

└─ Measure results (prove value, don't just optimize for sake of it)

PRINCIPLE: BPM should ENABLE speed, not slow it down

├─ Good BPM: Removes obstacles, clarifies priorities, improves flow

└─ Bad BPM: Adds gates, requires approvals, creates bottlenecks

If bureaucracy emerges:

- Quarterly BPM retrospective: "What's working? What's slowing people down?"

- Simplify processes: Remove unnecessary steps

- Empower teams: Delegate decisions to lowest appropriate level

- Measure: Time from request to start of work (should decrease, not increase)

#### Challenge 2: "BPM and IT Blame Each Other"

Risk: When things go wrong, BPM blames IT ("IT didn't deliver") and IT blames BPM ("BPM gave us wrong requirements")

Symptoms:

- Finger-pointing in Portfolio Board meetings

- Passive-aggressive communication

- Business caught in middle (doesn't know who to talk to)

- Executive escalations (CEO/COO having to resolve BPM-IT conflicts)

Prevention:

SHARED ACCOUNTABILITY MODEL

Joint Metrics:

├─ Portfolio health: Both BPM and IT measured on same metrics

│   ├─ On-time delivery: 80%+ projects on time

│   ├─ On-budget: 90%+ projects within 10% of budget

│   ├─ Value realization: 80%+ projects deliver promised business value

│   └─ Both BPM and IT bonuses tied to these metrics (aligned incentives)

│

├─ Customer satisfaction: Business stakeholders rate BOTH BPM and IT

│   └─ Cannot blame each other if customer unhappy (forces collaboration)

│

└─ Partnership score: Quarterly 360 feedback (BPM rates IT, IT rates BPM)

└─ If partnership score low, both leaders accountable (not just one)

Joint Governance:

├─ Portfolio Board: BPM and IT present together (not separately)

├─ Business cases: Co-authored by BRM (BPM) + PO (IT)

├─ Post-mortems: Joint (when project fails, both analyze what went wrong)

└─ Success celebrations: Joint (when project succeeds, both teams celebrated)

Conflict Resolution Protocol:

├─ Step 1: BPM and IT leaders discuss directly (most conflicts resolved here)

├─ Step 2: If unresolved, structured dialogue (facilitator, document both perspectives)

├─ Step 3: If still unresolved, CEO decides (both present their case)

├─ Step 4: Document decision, implement, move forward (no grudges)

└─ Retrospective: Learn from conflict (how to avoid similar in future)

CULTURE: "We win together, we lose together"

├─ When portfolio delivers value: Both BPM and IT succeed

├─ When portfolio underperforms: Both BPM and IT accountable

└─ No finger-pointing, only problem-solving

Specific Example - Failed Project:

Project: New shipping system over budget and late (€2M budget, spent €2.8M, 6 months late)

BAD RESPONSE (Blame):

├─ BPM: "IT underestimated effort and mismanaged delivery"

├─ IT: "BPM kept changing requirements and didn't get business buy-in"

├─ Result: Finger-pointing, no learning, relationship damaged

└─ CEO frustrated with both

GOOD RESPONSE (Joint Accountability):

├─ Joint post-mortem (BPM + IT leaders + project team)

├─ Root cause analysis:

│   ├─ Requirements did change mid-project (BPM could have locked down earlier)

│   ├─ Initial estimate was too optimistic (IT could have buffered better)

│   ├─ Business stakeholders not engaged enough (both BPM and IT could have done more)

│   └─ Vendor dependencies underestimated (both missed this)

│

├─ Joint ownership:

│   ├─ BPM: "We should have frozen requirements at Month 3, not Month 6"

│   ├─ IT: "We should have flagged budget concerns at Month 4, not Month 8"

│   └─ Both: "We should have engaged business stakeholders more actively"

│

├─ Lessons learned:

│   ├─ Process change: Implement requirements freeze milestone

│   ├─ Governance change: Monthly budget reviews (not quarterly)

│   └─ Stakeholder engagement: Weekly business stakeholder check-ins for large projects

│

└─ Result: Learning, improvement, relationship intact

#### Challenge 3: "Business Confused - Who Do I Call?"

Risk: Business stakeholders don't know whether to contact BPM or IT for various needs

Symptoms:

- Business calls wrong team, gets bounced around

- Requests fall through cracks (BPM thought IT handling, IT thought BPM handling)

- Frustration: "I just want help, I don't care about your org structure"

- Duplicate requests (business submits to both BPM and IT, just in case)

Prevention:

CLEAR BUSINESS-FACING MODEL

SINGLE POINT OF CONTACT (For Each Business Unit):

├─ Business Relationship Manager (BPM) is primary contact

│   └─ "For ANY IT or process question, call your BRM first"

│

├─ BRM triages:

│   ├─ IT request? → Routes to Demand Manager → Appropriate PO

│   ├─ Process improvement? → Routes to Process Analyst

│   ├─ Change support? → Routes to Change Specialist

│   ├─ Technical support? → Routes to Application Support

│   └─ Not sure? → BRM figures it out (business doesn't have to)

│

└─ Business never has to understand org structure

└─ "Call your BRM, they'll handle or route appropriately"

COMMUNICATION TO BUSINESS:

"YOUR SINGLE POINT OF CONTACT FOR ALL IT/PROCESS NEEDS"

Shipping Business Unit: Contact Jane Smith (BRM)

├─ Email: jane.smith@company.com

├─ Phone: +XX XXX XXX XXXX

├─ Slack: @janesmith

└─ For: Any IT requests, process improvements, questions, issues

Ports Business Unit: Contact John Doe (BRM)

├─ [Same contact info format]

Corporate Functions: Contact Bob Johnson (BRM)

├─ [Same contact info format]

URGENT TECHNICAL ISSUES (System Down):

├─ Call Application Support directly: support@company.com or +XX XXX XXX XXXX

└─ They'll escalate if needed (P1 incidents don't wait for BRM routing)

SIMPLE MODEL: "One person per business unit, they handle or route everything"

Reinforce Constantly:

- Every communication: "Contact your BRM"

- Email signatures: BRMs include "Your IT/Process contact"

- Intranet: BRM contact info prominently displayed

- Town halls: "Any IT or process question? Your BRM is Jane/John/Bob"

- Repeat until everyone knows

#### Challenge 4: "BPM Doesn't Understand Technical Constraints"

Risk: BPM commits to unrealistic timelines or promises features IT can't deliver

Symptoms:

- BPM tells business: "IT will deliver in 3 months"

- IT says: "That's impossible, will take 9 months minimum"

- Business disappointed, IT frustrated

- BPM credibility damaged (overpromised, underdelivered)

Prevention:

TECHNICAL LITERACY FOR BPM + IT INVOLVEMENT IN COMMITMENTS

BPM Training:

├─ Technical onboarding for all BPM staff (2-day workshop)

│   ├─ IT architecture overview (how systems work, integration complexity)

│   ├─ Effort estimation basics (what's easy vs. hard for IT)

│   ├─ Common constraints (technical debt, dependencies, capacity)

│   └─ Case studies: Why Project X took 6 months, not 2 months

│

└─ Ongoing education:

├─ Quarterly: IT presents to BPM (new technologies, architecture changes)

└─ BPM attends sprint demos (see what teams are building, understand pace)

No Commitments Without IT:

├─ Rule: BPM never commits timeline without IT input

│   ├─ Business asks BRM: "When can we get feature X?"

│   ├─ BRM: "Let me check with IT" (doesn't guess)

│   ├─ BRM consults PO or Solution Architect

│   └─ BRM returns to business with IT-informed answer

│

├─ Portfolio Board:

│   ├─ BPM presents business case

│   ├─ IT presents effort estimate and timeline

│   ├─ Both present together (unified view)

│   └─ Board decides based on complete picture

│

└─ Exception: Quick estimate for planning

├─ BRM can give rough estimate: "Probably 3-6 months, but need IT to confirm"

└─ Never firm commitment without IT involvement

Regular Calibration:

├─ Monthly: BPM + IT leadership review estimates vs. actuals

├─ Learning: Were estimates accurate? If not, why?

└─ Adjust: Improve estimation process based on learnings

Specific Example:

Business Request: "Add real-time vessel tracking to customer portal"

BAD APPROACH:

├─ BRM (BPM): "Sure, we can do that, probably 2-3 months"

├─ Business: "Great! I'll tell CEO we're launching in Q2"

├─ Later, IT: "This requires integrating with AIS data, building tracking service, redesigning portal. 9 months minimum."

├─ Result: Business disappointed, BRM lost credibility, IT frustrated

└─ Outcome: Conflict and broken trust

GOOD APPROACH:

├─ BRM (BPM): "Interesting idea! Let me check feasibility with IT and get back to you"

├─ BRM → Product Owner (Customer & Commercial): "Business wants vessel tracking, can we do it?"

├─ PO consults Solution Architect and Team Lead:

│   ├─ Architect: "Need to integrate AIS data source, build tracking service, update portal"

│   ├─ Team Lead: "Estimate 6-9 months, depends on AIS integration complexity"

│   └─ PO: "Could do MVP in 4 months (basic tracking), full solution 8 months"

│

├─ BRM returns to Business: "IT can deliver MVP in 4 months, full solution 8 months. Does that work?"

├─ Business: "4-month MVP sounds great, let's proceed"

├─ BRM → Portfolio Board: Present business case with IT-backed timeline

├─ Board approves: Proceed with 4-month MVP

└─ Result: Realistic expectations, everyone aligned, trust maintained

#### Challenge 5: "BPM Doesn't Have Business Credibility"

Risk: Business doesn't trust BPM (sees as "IT in disguise" or "another bureaucracy")

Symptoms:

- Business bypasses BPM, goes directly to IT

- Low engagement in BPM initiatives (process improvement projects get no participation)

- Business says: "BPM doesn't understand our operations"

- BRM can't get meetings with business stakeholders

Building BPM Credibility:

EARN TRUST THROUGH VALUE DELIVERY

Quick Wins (Month 1-6):

├─ Identify high-impact, low-effort improvements

│   ├─ Example: Streamline approval process (reduce from 5 approvals to 2)

│   ├─ Example: Automate manual report (saves 2 hours/week per person)

│   └─ Example: Fix long-standing pain point (slow system response time)

│

├─ Deliver fast (within 4-8 weeks)

├─ Communicate success:

│   ├─ "BPM worked with IT to reduce approval time 60%"

│   └─ "Business Excellence team identified and implemented automation saving 100 hours/month"

│

└─ Result: Business sees BPM delivers value (not just governance)

Domain Expertise:

├─ Hire BPM staff with industry experience

│   ├─ Process Analysts: Previous experience in shipping/ports/logistics

│   ├─ BRMs: Worked in operations before (understand business deeply)

│   └─ Not generic consultants (logistics-specific expertise)

│

├─ Continuous learning:

│   ├─ BPM staff shadow operations (1 week in terminals, 1 week with shipping ops)

│   ├─ Attend industry conferences (stay current on best practices)

│   └─ Regular business immersion (quarterly: spend time with business teams)

│

└─ Result: Business says "BPM understands our world" (not outsiders)

Stakeholder Engagement:

├─ Regular business stakeholder meetings:

│   ├─ Monthly: BRM meets with business unit leadership (30-60 min)

│   ├─ Quarterly: Head of BPM meets with COOs/business leaders (strategic alignment)

│   └─ Always: Business sets agenda (not BPM presenting at business)

│

├─ Co-create solutions:

│   ├─ Process improvements: Design WITH business, not FOR business

│   ├─ Business involved throughout (workshops, reviews, validation)

│   └─ Business ownership: "This is YOUR process improvement, we're facilitating"

│

└─ Result: Business feels heard and involved (not "done to")

Measure and Communicate Value:

├─ Track: Process improvements delivered, time/cost saved, value created

├─ Report: Quarterly "BPM Value Report" to business leaders

│   ├─ "Q1 achievements: 5 process improvements, €400K savings, 85% CSAT"

│   └─ "Q2 pipeline: 8 initiatives underway, projected €600K additional value"

│

└─ Result: Business sees ROI (BPM investment justified)

PRINCIPLE: Earn credibility through delivery, not through org structure

├─ Don't say: "We're important because we report to CEO"

└─ Do say: "We delivered these 10 improvements saving €2M this year"

### Success Story Example: How Separate BPM Should Work

Let me paint a picture of how this works well:

SCENARIO: IMPROVE CONTAINER TERMINAL DWELL TIME

Business Problem:

├─ Containers sitting in terminal too long (avg 5 days)

├─ Industry benchmark: 3 days

├─ Business impact: Lost revenue (terminal capacity constrained)

├─ COO Ports: "We need to fix this, it's costing us money"

STEP 1: BRM Captures Need (Week 1)

├─ BRM (Ports): Meets with COO Ports (regular monthly meeting)

├─ COO: "Container dwell time too high, need to improve"

├─ BRM: "Let me engage our Process Analyst to investigate"

└─ BRM → Process Analyst (Ports specialist): "New project, can you analyze?"

STEP 2: Process Analysis (Week 2-4)

├─ Process Analyst:

│   ├─ Data analysis: Where is time spent? (receiving: 1 day, storage: 2 days, dispatch: 2 days)

│   ├─ Root cause analysis: Why delays?

│   │   ├─ Receiving: Manual inspection process (30 min per container)

│   │   ├─ Storage: Inefficient yard planning (containers stored far from gate)

│   │   └─ Dispatch: Waiting for documentation (customs clearance delays)

│   │

│   ├─ Interviews: Terminal managers, operations staff, customs team

│   └─ Best practice research: How do best-in-class terminals do it?

│

└─ Output: Current state process map + identified improvement opportunities

STEP 3: Solution Design (Week 5-6)

├─ Process Analyst leads workshop (Business + IT + BPM)

│   ├─ Attendees: Terminal managers, Ports ops team, Process Analyst, BA (IT), Solution Architect

│   │

│   ├─ Brainstorm solutions:

│   │   ├─ Automate inspection (OCR, AI image recognition) → IT solution

│   │   ├─ Optimize yard planning (algorithm-based) → IT solution

│   │   └─ Pre-clear customs (submit docs early) → Process change (no IT)

│   │

│   └─ Prioritize:

│       ├─ Quick win: Pre-clear customs (process change, 0 IT effort, 0.5 day reduction)

│       ├─ Medium: Optimize yard planning (IT solution, 3 months, 1 day reduction)

│       └─ Long-term: Automate inspection (IT solution, 9 months, 0.5 day reduction)

│

└─ Output: Implementation roadmap (process changes + IT changes)

STEP 4: Implementation (Week 7+)

QUICK WIN - Process Change (Week 7-10):

├─ Process Analyst + Terminal Manager:

│   ├─ Design new customs pre-clearance process

│   ├─ Train terminal staff (half-day workshop)

│   ├─ Pilot with 20% of containers (2 weeks)

│   └─ Scale to all containers

│

├─ Change Specialist (BPM):

│   ├─ Communicate new process to all staff

│   ├─ Monitor adoption (are staff following new process?)

│   └─ Coaching and reinforcement

│

└─ Result (Week 10): Dwell time reduced 0.5 day (5 days → 4.5 days) ✅

MEDIUM - IT Solution (Week 7 - Month 6):

├─ Business Analyst (IT):

│   ├─ Receives process design from Process Analyst (handoff)

│   ├─ Writes IT requirements (yard optimization algorithm)

│   ├─ User stories for Ports - Containers Team

│   └─ PO prioritizes in backlog (high priority, approved by Portfolio Board)

│

├─ Ports - Containers Team:

│   ├─ Sprints 1-4: Build yard optimization algorithm

│   ├─ Sprint 5: Test in terminal (pilot 2 weeks)

│   ├─ Sprint 6: Deploy to production

│   └─ Timeline: 3 months (as estimated)

│

├─ Change Specialist (BPM):

│   ├─ Training: Terminal staff on new system (yard assignments)

│   ├─ Adoption monitoring: Are staff using new system?

│   └─ Support: On-site first week post-go-live

│

└─ Result (Month 6): Dwell time reduced additional 1 day (4.5 → 3.5 days) ✅

LONG-TERM - AI Inspection (Month 7-15):

├─ [Similar process, longer timeline]

└─ Result: Dwell time reduced to 3 days (industry benchmark) ✅

STEP 5: Value Realization (Month 6-15)

├─ Business Excellence Analyst:

│   ├─ Measures: Dwell time reduction, financial impact

│   │   ├─ Dwell time: 5 days → 3 days (40% improvement)

│   │   ├─ Terminal capacity: +15% (faster turnover = more containers)

│   │   └─ Revenue impact: €1.2M additional annual revenue

│   │

│   ├─ Documents: Case study "How we reduced dwell time 40%"

│   └─ Shares: Best practice shared with other terminals (Cars terminal learns from Containers)

│

└─ Portfolio Manager:

├─ Reports to Portfolio Board: "Dwell time project delivered €1.2M value, ROI 400%"

└─ Success story shared with executives and company

COLLABORATION SUMMARY:

├─ BPM Led:

│   ├─ Process analysis (Process Analyst)

│   ├─ Process change (customs pre-clearance)

│   ├─ Change management (adoption, training)

│   └─ Value measurement (Business Excellence)

│

├─ IT Delivered:

│   ├─ IT requirements (Business Analyst)

│   ├─ IT solution (Ports - Containers Team)

│   └─ Technical support (Application Support post-go-live)

│

├─ Joint:

│   ├─ Solution design workshop (BPM + IT + Business)

│   ├─ Portfolio prioritization (BPM business case + IT estimate)

│   └─ Implementation coordination (BPM + IT working together)

│

└─ Result: Business problem solved, BPM and IT both contributed, value delivered

This is what "separate BPM working well" looks like:

- BPM focused on process and change (their expertise)

- IT focused on systems and technology (their expertise)

- Clear handoffs (Process Analyst → Business Analyst)

- Joint governance (Portfolio Board approved IT work)

- Shared success (both BPM and IT recognized)

## Final Checklist: Deciding on BPM Model

Use this checklist to make your decision:

BPM MODEL DECISION CHECKLIST

ORGANIZATIONAL CONTEXT:

□ Organization size: <500 (lean toward integrated), 500+ (lean toward separate)

□ Industry: Process-intensive? (lean toward separate)

□ Transformation scope: IT-only? (integrated OK), Enterprise-wide? (separate better)

□ Post-merger integration: Yes (separate helpful for process harmonization)

POLITICAL FACTORS:

□ Current BPM leader aspiration: Wants executive role? (separate better)

□ CTO capacity: Can CTO handle BPM + IT? (if no, separate)

□ Business perception: Does business trust IT? (if no, separate BPM as independent advocate)

□ Executive support: Will CEO support separate BPM? (required for success)

CAPABILITY FACTORS:

□ BPM team size: Currently 5+ people? (can separate), <5? (maybe keep integrated)

□ BPM scope: Broader than IT portfolio? (process optimization, change management) → Separate

□ BPM expertise: Lean Six Sigma, change management skills? (yes → separate)

□ Coordination capacity: Can BPM and IT collaborate well? (if yes, separation feasible)

FINANCIAL FACTORS:

□ Budget available: €1.85M/year for separate BPM? (if yes, consider separate)

□ ROI expected: Can separate BPM deliver €2.4M+ value? (if yes, worth investment)

□ Phased approach: Can start small, scale up? (reduces risk)

STRATEGIC FACTORS:

□ Transformation importance: Critical to strategy? (separate signals commitment)

□ Differentiation: Process excellence competitive advantage? (separate worth it)

□ Long-term vision: Building transformation capability? (separate builds capability)

SCORE YOUR CONTEXT:

├─ If 10+ checkboxes checked → Model B (Separate) strongly recommended ⭐

├─ If 7-9 checkboxes → Model B (Separate) recommended or Model C (Hybrid)

├─ If 4-6 checkboxes → Model C (Hybrid) or Model A (Integrated)

└─ If <4 checkboxes → Model A (Integrated) likely sufficient

## Conclusion: BPM Placement Decision

### Your Specific Context Assessment

Based on what you've shared:

Your Checkboxes (my assessment): ✅ Organization size: 500+ people (logistics company, 100-person IT) ✅ Industry: Logistics (very process-intensive - shipping, ports, cargo, customs) ✅ Transformation scope: Enterprise-wide (not just IT systems, entire operations) ✅ Post-merger integration: Implied (legacy Tool A and B from merger) ✅ BPM current scope: Broader than just IT portfolio (you mentioned BPM function exists) ✅ Political: Current BPM function likely expects/wants independence from IT ✅ Strategic importance: Logistics competitiveness depends on operational excellence ✅ Process optimization: Core to business success (terminal efficiency, shipping speed, customs clearance)

Score: 8/8 factors favor separation

### My Clear Recommendation: Model B (BPM Fully Separate) ⭐

Why:

- Your industry (logistics) - process optimization is strategic

- Your scale (large enough to justify separate function)

- Your transformation scope (enterprise-wide, not IT-only)

- Political reality (BPM likely expects/wants executive role)

Structure:

- Head of BPM & Transformation (reports to CEO, peer to CTO)

- 14-22 people across 4 functions (Portfolio/Demand, Process, Change, Excellence)

- Budget: €1.85M/year ongoing

- ROI: €2.4-4.4M/year value (84% ROI)

Critical Success Factors:

- Strong BPM-CTO partnership (weekly coordination, joint governance)

- Clear decision rights (documented, communicated, enforced)

- Shared accountability (both measured on portfolio outcomes)

- Culture of collaboration (BPM + IT serve business together)

Implementation:

- Month 1-3: Design and approval

- Month 4: Hire Head of BPM & Transformation

- Month 4-12: Build team (phased hiring)

- Month 12: Fully operational

## You Now Have Complete Answer

Question: Should BPM be kept separate from IT, and what functions belong there?

Answer: ✅ YES, BPM should be separate (for your context) ✅ Functions in BPM: Portfolio & Demand, Process Optimization, Change Management, Business Excellence ✅ Structure: 14-22 people, Head of BPM & Transformation (peer to CTO) ✅ Budget: €1.85M/year, ROI 84% ✅ Implementation roadmap: 12 months to full operation

You have:

- ✅ Three organizational models (integrated, fully separate, hybrid)

- ✅ Detailed recommendation with rationale (Model B for you)

- ✅ Complete BPM organization design (roles, responsibilities, budget)

- ✅ Operating model (how BPM and IT collaborate)

- ✅ Challenge mitigation strategies (prevent common pitfalls)

- ✅ Success story example (what good looks like)

- ✅ Decision checklist (validate your choice)

- ✅ Implementation roadmap (Month 1-12 plan)

Your complete transformation is now fully defined:

- IT organization: 146-178 people (8 stream teams + platforms + architecture + data + support + vendor management)

- BPM organization: 14-22 people (portfolio, process, change, excellence)

- Total: 160-200 people (from ~105 baseline)

- Investment: €18.05M over 3 years

- Value: €43.2M over 3 years

- Net benefit: €25.15M, ROI 139%

You're ready to transform. Make the decision, get approval, execute! 🚀✨

# Excellent Strategic Question - Business Unit Embedded vs. Centralized Model

This is a critical organizational design question that many companies struggle with. You're absolutely right to challenge the centralized model. Let me analyze both approaches thoroughly.

## The Core Question: Where Should Process & Excellence Capability Live?

### Model 1: Centralized in BPM (What I Recommended)

CEO

│

└─ Head of BPM & Transformation (central)

├─ Portfolio & Demand Management

├─ Business Process Optimization ⭐ (central team serving all BUs)

├─ Change Management

└─ Business Excellence ⭐ (central team serving all BUs)

Process Analysts and Excellence specialists are centralized, serve all business units

### Model 2: Embedded in Business Units (Your Suggestion) ⭐

CEO

│

├─ COO Shipping Business Unit

│   ├─ Shipping Operations

│   ├─ Commercial & Sales (Shipping)

│   └─ Process Excellence Team ⭐ (embedded in Shipping BU)

│       ├─ Process Analyst - Shipping (1-2)

│       ├─ Continuous Improvement Lead (1)

│       └─ Reports to: COO Shipping

│

├─ COO Ports Business Unit

│   ├─ Cars Operations

│   ├─ Container/Trailer Operations

│   └─ Process Excellence Team ⭐ (embedded in Ports BU)

│       ├─ Process Analyst - Ports (1-2)

│       ├─ Continuous Improvement Lead (1)

│       └─ Reports to: COO Ports

│

├─ COO Cargo/Logistics Business Unit

│   └─ Process Excellence Team ⭐ (embedded in Cargo BU)

│

└─ Head of BPM & Transformation (central, smaller)

├─ Portfolio & Demand Management ⭐ (stays central)

├─ Change Management ⭐ (stays central, supports all BUs)

└─ Business Excellence Center of Excellence ⭐ (small central team, 2-3)

├─ Methodology and standards

├─ Cross-BU best practice sharing

└─ Coaches embedded teams

Process Analysts and Excellence specialists are embedded in business units, close to operations

## Deep Analysis: Centralized vs. Embedded

### Embedded in Business Units - ADVANTAGES ✅

1. Domain Expertise and Context:

EMBEDDED MODEL:

├─ Process Analyst sits WITH shipping operations team

├─ Daily exposure to operations:

│   ├─ Attends operations meetings

│   ├─ Sees real-time issues and bottlenecks

│   ├─ Understands nuances and context

│   └─ Builds deep domain expertise (years of immersion)

│

└─ Result: Better process designs (understands business deeply)

vs.

CENTRALIZED MODEL:

├─ Process Analyst visits shipping operations for projects

├─ Periodic exposure:

│   ├─ Interview sessions (scheduled, formal)

│   ├─ Observation (days or weeks, not continuous)

│   └─ May miss context and nuances

│

└─ Risk: Surface-level understanding, misses important details

Example:

- Embedded: Process Analyst in Shipping BU observes daily vessel delay challenges, understands seasonal patterns, knows key customers, recognizes cultural dynamics → Designs realistic solutions

- Centralized: Process Analyst visits for 2-week project, may miss seasonal patterns, doesn't know informal workflows, designs solution that looks good on paper but doesn't work in practice

2. Business Unit Ownership and Accountability:

EMBEDDED MODEL:

├─ COO Shipping owns process improvement (part of their P&L)

├─ Process Analyst reports to COO Shipping

├─ Alignment: COO priorities = Process Analyst priorities

├─ Accountability: Clear (COO accountable for operations AND improvement)

└─ Result: Faster decisions, stronger buy-in

vs.

CENTRALIZED MODEL:

├─ Head of BPM owns process improvement (separate from operations)

├─ Process Analyst reports to Head of BPM (not COO)

├─ Potential misalignment: BPM priorities ≠ COO priorities

├─ Accountability: Split (COO accountable for operations, BPM for improvement)

└─ Risk: Finger-pointing ("BPM designed bad process" vs. "Operations didn't implement properly")

Example:

- Embedded: COO Shipping says "Terminal dwell time is my #1 priority" → Process Analyst (reports to COO) immediately focuses on this → Fast action

- Centralized: COO Shipping says "Terminal dwell time is priority" → Must request from BPM → BPM prioritizes across all BUs → May take months to get resources → Frustration

3. Cultural Fit and Trust:

EMBEDDED MODEL:

├─ Process Analyst is "one of us" (part of Shipping team)

├─ Trust built over time (daily interaction)

├─ Operations staff comfortable sharing problems

├─ Informal conversations reveal issues

└─ Result: Better insights, higher acceptance of changes

vs.

CENTRALIZED MODEL:

├─ Process Analyst is "external consultant" (from central BPM)

├─ Trust must be earned each project

├─ Operations staff may be guarded (outsider)

├─ Formal interactions only

└─ Risk: Operations hide problems, sabotage changes ("not invented here")

4. Speed and Responsiveness:

EMBEDDED MODEL:

├─ Issue identified → Process Analyst tackles immediately

├─ No approval needed from central function

├─ COO can reprioritize Process Analyst weekly

└─ Result: Agile, fast response to emerging issues

vs.

CENTRALIZED MODEL:

├─ Issue identified → Request to BPM → BPM prioritizes → Assigned to analyst

├─ Timeline: Weeks to months (depending on BPM capacity)

├─ Less flexibility (central team has queue of requests)

└─ Risk: Business frustrated by slow response

5. Career Path and Retention:

EMBEDDED MODEL:

├─ Career path: Process Analyst → Operations Manager → COO

├─ Process Analyst can transition to operations role (domain expertise valued)

├─ Attractive for operations-minded people

└─ Result: Retain talent, build operational leadership pipeline

vs.

CENTRALIZED MODEL:

├─ Career path: Process Analyst → Senior Analyst → Manager BPM → Head of BPM

├─ Stays in BPM function (doesn't move to operations)

├─ May be less attractive (seen as staff role, not line role)

└─ Risk: Lose people who want operational leadership careers

### Embedded in Business Units - DISADVANTAGES ❌

1. Duplicate Capability and Higher Cost:

EMBEDDED MODEL (3 Business Units):

├─ Shipping BU: 2 Process Analysts + 1 CI Lead = 3 people

├─ Ports BU: 2 Process Analysts + 1 CI Lead = 3 people

├─ Cargo BU: 1 Process Analyst + 1 CI Lead = 2 people

└─ Total: 8 people embedded (€60-70K avg = €480-560K)

vs.

CENTRALIZED MODEL:

├─ BPM: 4-6 Process Analysts + 2 CI specialists = 6 people

├─ Serve all BUs (shared resource)

└─ Total: 6 people centralized (€60-70K avg = €360-420K)

COST DIFFERENCE: +€120-140K/year (embedded model costs 30% more)

Why more expensive:

- Each BU needs minimum viable team (can't have 0.5 FTE)

- Can't share resources across BUs easily

- Some inefficiency (Shipping BU analyst idle while Ports analyst overwhelmed)

2. Inconsistent Methodology and Standards:

EMBEDDED MODEL:

├─ Shipping BU: Uses Lean methodology (what their analyst knows)

├─ Ports BU: Uses Six Sigma (what their analyst knows)

├─ Cargo BU: Uses ad-hoc approach (less mature)

└─ Result: Inconsistent approaches, can't compare results across BUs

vs.

CENTRALIZED MODEL:

├─ BPM defines standard methodology (e.g., Lean Six Sigma)

├─ All analysts trained on same approach

├─ Standard templates, tools, reporting

└─ Result: Consistent, comparable results across BUs

Example Impact:

- Embedded: Shipping BU reports "30% improvement" (using Lean metrics), Ports BU reports "2 sigma improvement" (using Six Sigma metrics) → Can't compare, CEO confused

- Centralized: All BUs report in same format (e.g., "€X saved, Y% efficiency gain") → CEO can compare, make informed decisions

3. Lost Economies of Scale:

EMBEDDED MODEL:

├─ Each BU analyst works independently

├─ Each BU buys own tools (process mapping software, data analysis tools)

├─ Each BU trains own analysts

└─ Result: Duplicate costs, no economies of scale

vs.

CENTRALIZED MODEL:

├─ Central team shares tools (site licenses, shared training)

├─ Shared expertise (analysts learn from each other)

├─ Bulk purchasing power

└─ Result: Lower per-person cost, higher capability

4. Limited Cross-Pollination:

EMBEDDED MODEL:

├─ Shipping analyst learns Shipping best practices only

├─ Ports analyst learns Ports best practices only

├─ No knowledge sharing across BUs

└─ Risk: Miss opportunities to apply Shipping insights to Ports

vs.

CENTRALIZED MODEL:

├─ Analysts work across BUs (rotating assignments)

├─ Learn best practices from multiple domains

├─ Cross-pollinate ideas ("Shipping does X well, could Ports adopt?")

└─ Result: Innovation through cross-BU learning

Example:

- Shipping BU implements automated gate system (reduces processing time 50%)

- Embedded: Ports BU analyst doesn't know about this (siloed)

- Centralized: Central BPM analyst sees success in Shipping, suggests to Ports → Ports adopts → Compound value

5. Harder to Scale and Flex:

EMBEDDED MODEL:

├─ Shipping BU has 2 analysts (fixed)

├─ Major project needs 4 analysts → Can't flex, must hire or wait

├─ Ports BU analyst idle → Can't redeploy to Shipping

└─ Risk: Inefficient resource utilization

vs.

CENTRALIZED MODEL:

├─ Central team of 6 analysts (flexible pool)

├─ Major Shipping project → Deploy 4 analysts to Shipping temporarily

├─ After project → Redeploy to other priorities

└─ Result: Efficient resource utilization, surge capacity

## My Recommendation: HYBRID MODEL (Best of Both Worlds) ⭐

After analyzing both extremes, I believe neither pure centralized nor pure embedded is optimal for you. Instead:

### Hybrid Model: Embedded Capability + Central Excellence

HYBRID ORGANIZATION

BUSINESS UNITS (Embedded - 80% of Capability):

│

├─ SHIPPING BUSINESS UNIT

│   ├─ Shipping Operations

│   └─ Shipping Process Excellence ⭐ (2-3 people)

│       ├─ Senior Process Analyst - Shipping (1) €70-80K

│       │   └─ Deep shipping domain expertise

│       │   └─ Reports to: COO Shipping (solid line)

│       │   └─ Dotted line to: Head of Business Excellence (methodology)

│       │

│       └─ Continuous Improvement Coordinator (1-2) €50-60K

│           └─ Kaizen events, quick wins, daily improvements

│           └─ Reports to: COO Shipping

│

├─ PORTS BUSINESS UNIT

│   ├─ Cars Operations

│   ├─ Container/Trailer Operations

│   └─ Ports Process Excellence ⭐ (2-3 people)

│       ├─ Senior Process Analyst - Ports (1)

│       └─ Continuous Improvement Coordinator (1-2)

│       └─ [Same reporting structure]

│

└─ CARGO/LOGISTICS BUSINESS UNIT

└─ Cargo Process Excellence ⭐ (1-2 people)

└─ Process Analyst - Cargo (1)

└─ CI Coordinator (1)

CENTRAL BPM (Center of Excellence - 20% of Capability):

│

└─ HEAD OF BPM & TRANSFORMATION

│

├─ Portfolio & Demand Management (5-7) ⭐ STAYS CENTRAL

│   └─ (As previously defined)

│

├─ Change Management (3-5) ⭐ STAYS CENTRAL

│   └─ Supports all BUs for major transformations

│

└─ Business Excellence Center of Excellence (2-4) ⭐ NEW STRUCTURE

│

├─ Head of Business Excellence (1) €90-110K

│   └─ Sets methodology and standards

│   └─ Governs embedded Process Excellence teams

│   └─ Dotted line management of embedded analysts

│

├─ Lean Six Sigma Master (1-2) €80-100K

│   └─ Trains embedded analysts (Green Belt, Black Belt)

│   └─ Coaches on complex projects

│   └─ Develops methodology and tools

│

└─ Performance Management Analyst (1) €60-80K

└─ Enterprise-wide performance framework

└─ Consolidates BU process improvement results

└─ Cross-BU benchmarking and best practice sharing

TOTAL HEADCOUNT:

├─ Embedded in BUs: 6-8 people (€360-560K)

├─ Central BPM: 10-16 people (€1.05-1.45M)

└─ Total: 16-24 people (€1.41-2M)

### How Hybrid Model Works

#### Embedded Process Analysts - Primary Responsibilities:

DAILY WORK (80-90% of time):

├─ Embedded in Business Unit (sit with operations team)

├─ Report to: COO of their Business Unit (solid line)

├─ Priorities set by: COO (business unit needs)

├─ Focus: Business unit-specific process improvements

│

├─ Projects:

│   ├─ "Reduce terminal dwell time" (Ports BU priority)

│   ├─ "Optimize vessel scheduling" (Shipping BU priority)

│   ├─ "Streamline cargo booking" (Cargo BU priority)

│   └─ Reactive to business unit operational needs

│

└─ Benefits: Domain expertise, trust, speed, ownership (all the embedded advantages ✅)

CENTRAL CONNECTION (10-20% of time):

├─ Dotted line to: Head of Business Excellence (central)

├─ Methodology compliance:

│   ├─ Use standard Lean Six Sigma approach (not ad-hoc)

│   ├─ Follow standard templates (process maps, business cases)

│   └─ Report in standard format (comparable across BUs)

│

├─ Training and development:

│   ├─ Quarterly training from central team (new techniques, tools)

│   ├─ Green Belt / Black Belt certification (sponsored by central)

│   └─ Professional development (career progression support)

│

├─ Community of practice:

│   ├─ Monthly: All Process Analysts meet (central + embedded)

│   ├─ Share: Best practices, learnings, challenges

│   ├─ Cross-pollinate: "Shipping solved X, could help Ports with Y"

│   └─ Peer support: Learn from each other

│

└─ Benefits: Consistent standards, cross-BU learning, capability building (central advantages ✅)

#### Central Excellence Team - Primary Responsibilities:

METHODOLOGY & STANDARDS (30%):

├─ Define: Standard Lean Six Sigma methodology

├─ Develop: Templates, tools, playbooks

├─ Govern: Ensure embedded analysts follow standards

└─ Quality assurance: Review major project deliverables

TRAINING & CAPABILITY BUILDING (30%):

├─ Train embedded analysts:

│   ├─ Onboarding: New analysts (2-week intensive training)

│   ├─ Certifications: Green Belt (3 months), Black Belt (6 months)

│   └─ Continuous: Quarterly training on new techniques

│

├─ Train business operations staff:

│   ├─ Yellow Belt training for operations managers (awareness)

│   └─ Kaizen facilitation for team leads

│

└─ Build organizational capability (not just doing projects)

COMPLEX PROJECTS & SURGE CAPACITY (20%):

├─ Lead complex cross-BU projects:

│   ├─ Example: "Harmonize processes across Shipping and Ports"

│   ├─ Example: "Enterprise-wide cost reduction program"

│   └─ Projects too big for one embedded analyst

│

├─ Surge support:

│   ├─ Shipping BU has major project, 1 embedded analyst insufficient

│   ├─ Central team provides additional analyst (temporary, 3-6 months)

│   └─ After project, central analyst returns to pool

│

└─ Specialty expertise:

├─ Advanced statistical analysis (Six Sigma Black Belt techniques)

└─ Complex process simulation/modeling

KNOWLEDGE MANAGEMENT & SHARING (20%):

├─ Best practice repository:

│   ├─ Document successful improvements from all BUs

│   ├─ Make accessible (Confluence, SharePoint)

│   └─ Curate and update

│

├─ Cross-BU sharing:

│   ├─ Monthly community of practice meetings

│   ├─ Quarterly showcase (BUs present successes)

│   └─ Annual excellence summit

│

└─ Performance reporting:

├─ Consolidate results from all BUs

├─ Report to CEO: "Enterprise-wide process improvement delivered €X value"

└─ Benchmarking: Compare BUs, identify opportunities

### Hybrid Model - Governance & Decision Rights

Clear Matrix Reporting Structure:

EMBEDDED PROCESS ANALYST (e.g., Shipping Process Analyst)

REPORTS TO (Solid Line): COO Shipping

├─ Performance evaluation: COO Shipping rates performance

├─ Priorities: COO Shipping sets priorities

├─ Daily work: Embedded in Shipping operations

├─ Budget: Shipping BU budget

└─ Accountability: COO Shipping accountable for results

REPORTS TO (Dotted Line): Head of Business Excellence (central)

├─ Methodology: Follows Lean Six Sigma standards

├─ Professional development: Training, certification

├─ Community: Participates in cross-BU activities

├─ Quality: Central team reviews major projects

└─ Career development: Central team coaches on career progression

DECISION RIGHTS:

├─ What projects? → COO Shipping decides (embedded analyst works on BU priorities)

├─ How to approach? → Head of Business Excellence sets methodology

├─ Quality standards? → Head of Business Excellence defines

├─ Resource allocation? → COO Shipping controls their analyst

├─ Cross-BU projects? → Head of Business Excellence coordinates

└─ Hiring? → COO Shipping hires (with input from Head of Business Excellence on qualifications)

How Matrix Reporting Works in Practice:

SCENARIO 1: Business Unit Priority Project

COO Shipping: "We need to reduce booking processing time, it's hurting customer satisfaction"

├─ Assigns to: Shipping Process Analyst (embedded in their BU)

├─ Analyst works on project (80% time for 3 months)

├─ Follows: Standard Lean Six Sigma methodology (central standards)

├─ Updates: COO Shipping weekly (business unit accountability)

├─ Consults: Central LSS Master if complex (technical support)

└─ Results: Reports to COO, also documented in central repository

SCENARIO 2: Cross-BU Best Practice Sharing

Central Excellence: "Shipping reduced booking time 40% using automated validation. Could Ports benefit?"

├─ Head of Business Excellence: Facilitates knowledge transfer

├─ Shipping Process Analyst: Presents approach to Ports Process Analyst

├─ Ports Process Analyst: Evaluates applicability to Ports context

├─ If relevant: Ports Analyst proposes to COO Ports

├─ COO Ports decides: Yes, let's do it (or no, not applicable)

└─ Results: Ports implements similar improvement

SCENARIO 3: Complex Cross-BU Project

CEO: "We need enterprise-wide cost reduction program, target €5M savings"

├─ Head of Business Excellence: Leads program (complex, cross-BU)

├─ Engages: Embedded analysts from all BUs (each contributes 20% time)

├─ COOs agree: Release their analysts part-time for corporate priority

├─ Central LSS Master: Provides methodology and tools

├─ Embedded analysts: Identify BU-specific opportunities (domain expertise)

├─ Central team: Coordinates, consolidates, reports

└─ Results: €5M savings achieved across all BUs

SCENARIO 4: Training New Analyst

COO Ports: Hires new Process Analyst for Ports BU

├─ Central Excellence: Provides 2-week onboarding training

├─ Central Excellence: Assigns mentor (Shipping Analyst mentors Ports Analyst for 3 months)

├─ Central Excellence: Sponsors Green Belt certification (6 months)

├─ COO Ports: Assigns real projects (learning by doing)

└─ After 6 months: Analyst productive, certified, embedded in Ports team

### Hybrid Model - Financial Breakdown

Headcount & Cost:

EMBEDDED IN BUSINESS UNITS (6-8 people, €360-560K):

Shipping BU:

├─ Senior Process Analyst €75K × 1 = €75K

├─ CI Coordinator €55K × 1 = €55K

└─ Subtotal: €130K (Shipping BU budget)

Ports BU:

├─ Senior Process Analyst €75K × 1 = €75K

├─ CI Coordinator €55K × 2 = €110K

└─ Subtotal: €185K (Ports BU budget)

Cargo BU:

├─ Process Analyst €65K × 1 = €65K

├─ CI Coordinator €55K × 1 = €55K

└─ Subtotal: €120K (Cargo BU budget)

Total Embedded: €435K (6 people)

└─ Cost borne by: Business Unit P&Ls (decentralized)

CENTRAL BPM (10-16 people, €1.05-1.45M):

Portfolio & Demand: €500K (5-7 people)

Change Management: €350K (3-5 people)

Business Excellence CoE: €200K (2-4 people)

└─ Total Central: €1.05M (10-16 people)

└─ Cost borne by: Corporate overhead (centralized)

COMBINED TOTAL:

├─ Embedded: €435K (6 people in BUs)

├─ Central: €1.05M (10-16 people in BPM)

└─ Total: €1.485M (16-22 people)

vs. FULLY CENTRALIZED MODEL (from earlier):

└─ €1.85M (18-22 people all central)

SAVINGS: €365K/year (hybrid is 20% cheaper due to lower-cost embedded coordinators)

### Hybrid Model - Why This is Best for You

✅ Combines Best of Both Worlds:

| Aspect | Embedded Advantage | Central Advantage | Hybrid Delivers |
| --- | --- | --- | --- |
| Domain Expertise | ✅ Deep domain knowledge | ❌ Surface-level | ✅ Embedded = deep expertise |
| Business Unit Ownership | ✅ Clear accountability | ❌ Split accountability | ✅ COO owns embedded analyst |
| Trust & Culture Fit | ✅ "One of us" | ❌ "External consultant" | ✅ Embedded = trusted insider |
| Speed & Responsiveness | ✅ Immediate action | ❌ Request queue | ✅ Embedded = fast response |
| Consistent Methodology | ❌ Inconsistent | ✅ Standard approach | ✅ Central sets standards |
| Cross-BU Learning | ❌ Siloed | ✅ Cross-pollination | ✅ Central facilitates sharing |
| Economies of Scale | ❌ Duplicate costs | ✅ Shared resources | ✅ Central provides training/tools |
| Surge Capacity | ❌ Fixed resources | ✅ Flexible pool | ✅ Central can support BUs |
| Cost | ❌ 30% more expensive | ✅ Lower cost | ✅ Hybrid 20% cheaper than pure central |

✅ Fits Your Logistics Context:

- Three distinct business units (Shipping, Ports, Cargo) with different operations → Embedded makes sense (each BU different enough)

- Process excellence critical to each BU's success → Embedded ownership drives results

- Need cross-BU learning (maritime industry best practices apply across BUs) → Central excellence facilitates

✅ Political Win-Win:

- COOs happy: They control process improvement in their BUs (not centralized function dictating)

- Head of BPM happy: Still has executive role (Portfolio, Change, Excellence governance)

- CEO happy: Gets both BU ownership AND enterprise standards

✅ Scalable and Flexible:

- Start small: Launch with 1 analyst per BU + small central team (Month 1-6)

- Scale up: Add CI Coordinators, grow central team (Month 7-12)

- Flex: Central team can surge-support BUs when needed

## Revised Organization Chart: Hybrid Model

### Complete Organization with Hybrid Process Excellence

━━━━━━━━━━━━━━━━━━━━━━━━━━━━━━━━━━━━━━━━━━━━━━━━━━━━━━━━━━━

CEO

━━━━━━━━━━━━━━━━━━━━━━━━━━━━━━━━━━━━━━━━━━━━━━━━━━━━━━━━━━━

│

┌────────────────────┼────────────────────┬───────────────┐

│                    │                    │               │

↓                    ↓                    ↓               ↓

┌───────────────┐    ┌───────────────┐    ┌──────────────┐  ┌────────────┐

│ COO SHIPPING  │    │ COO PORTS     │    │ COO CARGO    │  │ CTO,       │

│ BU            │    │ BU            │    │ BU           │  │ CFO, etc.  │

└───────┬───────┘    └───────┬───────┘    └──────┬───────┘  └────────────┘

│                    │                    │

│                    │                    │

┌─────────────────────────────────────────────────────────────┐

│ SHIPPING BUSINESS UNIT (COO Shipping)                       │

├─────────────────────────────────────────────────────────────┤

│ • Shipping Operations                                        │

│ • Commercial & Sales (Shipping)                             │

│ • Shipping Process Excellence ⭐ (2-3 people)               │

│   ├─ Senior Process Analyst - Shipping (1) €75K            │

│   │   └─ Reports to: COO Shipping (solid line)             │

│   │   └─ Dotted to: Head of Business Excellence (central)   │

│   │                                                          │

│   └─ Continuous Improvement Coordinator (1-2) €55K         │

│       └─ Reports to: COO Shipping                           │

│       └─ Kaizen events, daily improvements                  │

└─────────────────────────────────────────────────────────────┘

┌─────────────────────────────────────────────────────────────┐

│ PORTS BUSINESS UNIT (COO Ports)                            │

├─────────────────────────────────────────────────────────────┤

│ • Cars Terminal Operations                                  │

│ • Container/Trailer Terminal Operations                     │

│ • Ports Process Excellence ⭐ (2-3 people)                  │

│   ├─ Senior Process Analyst - Ports (1) €75K               │

│   │   └─ Reports to: COO Ports (solid line)                │

│   │   └─ Dotted to: Head of Business Excellence (central)   │

│   │                                                          │

│   └─ Continuous Improvement Coordinators (1-2) €55K        │

│       └─ Reports to: COO Ports                              │

│       └─ One for Cars, one for Containers/Trailers          │

└─────────────────────────────────────────────────────────────┘

┌─────────────────────────────────────────────────────────────┐

│ CARGO/LOGISTICS BUSINESS UNIT (COO Cargo)                  │

├─────────────────────────────────────────────────────────────┤

│ • Cargo & Haulage Operations                                │

│ • Cargo Process Excellence ⭐ (1-2 people)                  │

│   ├─ Process Analyst - Cargo (1) €65K                      │

│   │   └─ Reports to: COO Cargo (solid line)                │

│   │   └─ Dotted to: Head of Business Excellence (central)   │

│   │                                                          │

│   └─ Continuous Improvement Coordinator (1) €55K           │

│       └─ Reports to: COO Cargo                              │

└─────────────────────────────────────────────────────────────┘

┌─────────────────────────────────────────────────────────────┐

│ HEAD OF BPM & TRANSFORMATION (Central, reports to CEO)     │

├─────────────────────────────────────────────────────────────┤

│                                                              │

│ • Portfolio & Demand Management (5-7) ⭐ CENTRAL           │

│   └─ [As previously defined]                                │

│                                                              │

│ • Change Management (3-5) ⭐ CENTRAL                        │

│   └─ [As previously defined]                                │

│                                                              │

│ • Business Excellence Center of Excellence (2-4) ⭐ NEW     │

│   │                                                          │

│   ├─ Head of Business Excellence (1) €100K                 │

│   │   └─ Sets methodology, standards, governance            │

│   │   └─ Dotted-line manages embedded Process Analysts      │

│   │   └─ Facilitates cross-BU knowledge sharing             │

│   │                                                          │

│   ├─ Lean Six Sigma Master Black Belt (1-2) €90K           │

│   │   └─ Trains embedded analysts (Green/Black Belt)        │

│   │   └─ Coaches on complex projects                        │

│   │   └─ Methodology development                            │

│   │                                                          │

│   └─ Performance Management Analyst (1) €65K               │

│       └─ Enterprise KPIs and dashboards                     │

│       └─ Consolidates BU process improvement results        │

│       └─ Cross-BU benchmarking                              │

│                                                              │

│ TOTAL CENTRAL BPM: 10-16 people (€1.05M)                   │

└─────────────────────────────────────────────────────────────┘

## Revised Organization Chart: Hybrid Model (continued)

━━━━━━━━━━━━━━━━━━━━━━━━━━━━━━━━━━━━━━━━━━━━━━━━━━━━━━━━━━━

TOTAL BPM & PROCESS EXCELLENCE ORGANIZATION (HYBRID):

━━━━━━━━━━━━━━━━━━━━━━━━━━━━━━━━━━━━━━━━━━━━━━━━━━━━━━━━━━━

EMBEDDED IN BUSINESS UNITS:

├─ Shipping BU: 2-3 people (€130K)

├─ Ports BU: 2-3 people (€185K)

├─ Cargo BU: 1-2 people (€120K)

└─ Subtotal Embedded: 5-8 people (€435K)

CENTRAL BPM:

├─ Portfolio & Demand: 5-7 people (€500K)

├─ Change Management: 3-5 people (€350K)

├─ Business Excellence CoE: 2-4 people (€200K)

└─ Subtotal Central: 10-16 people (€1.05M)

━━━━━━━━━━━━━━━━━━━━━━━━━━━━━━━━━━━━━━━━━━━━━━━━━━━━━━━━━━━

GRAND TOTAL: 15-24 people (€1.485M/year)

━━━━━━━━━━━━━━━━━━━━━━━━━━━━━━━━━━━━━━━━━━━━━━━━━━━━━━━━━━━

vs. FULLY CENTRALIZED: 18-22 people (€1.85M)

SAVINGS: €365K/year (20% cheaper) ✅

## Implementation: Hybrid Model Rollout

### Phase 1: Launch Embedded Capability (Month 1-6)

MONTH 1-3: DESIGN & HIRE CENTRAL TEAM

Week 1-4: Design Hybrid Model

├─ Define: Embedded vs. central responsibilities

├─ Define: Matrix reporting structure (solid vs. dotted line)

├─ Define: Standards and methodology (Lean Six Sigma)

└─ Socialize: Get COO buy-in (Shipping, Ports, Cargo)

Week 5-8: Hire Central Team First

├─ Head of Business Excellence (Month 2)

├─ LSS Master Black Belt (Month 3)

└─ Performance Analyst (Month 3)

Week 9-12: Develop Standards

├─ Standard Lean Six Sigma methodology

├─ Templates (process maps, business cases, project charters)

├─ Training curriculum (for embedded analysts)

└─ Quality standards (project deliverable expectations)

MONTH 4-6: HIRE & TRAIN EMBEDDED ANALYSTS

Month 4: COOs Hire Embedded Analysts

├─ COO Shipping: Posts job for Senior Process Analyst - Shipping

├─ COO Ports: Posts job for Senior Process Analyst - Ports

├─ COO Cargo: Posts job for Process Analyst - Cargo

│

└─ Head of Business Excellence: Provides input

├─ Job description template (qualifications needed)

├─ Interview participation (assess technical competency)

└─ Hiring recommendation (is candidate qualified?)

Month 5: Onboarding & Training

├─ Week 1-2: Central training (Head of Excellence delivers)

│   ├─ Lean Six Sigma methodology (2 days)

│   ├─ Tools and templates (1 day)

│   ├─ Standards and expectations (1 day)

│   └─ Community of practice introduction

│

├─ Week 3-4: Business unit immersion

│   ├─ Shadow operations (learn the business)

│   ├─ Meet stakeholders

│   └─ Understand current pain points

│

└─ Month 6: First projects (with mentoring)

├─ Each analyst: Quick win project (4-8 weeks)

├─ Central LSS Master: Mentors and coaches

└─ Prove value early

MONTH 6 DELIVERABLE:

├─ 3 embedded analysts operational (one per BU)

├─ Central Excellence CoE established

├─ First process improvement projects underway

└─ Hybrid model functioning

### Phase 2: Scale & Mature (Month 7-12)

MONTH 7-9: ADD CONTINUOUS IMPROVEMENT COORDINATORS

Why Add CI Coordinators:

├─ Process Analysts focus on major projects (3-6 months each)

├─ CI Coordinators focus on quick wins (1-4 weeks each)

├─ Together: Cover both strategic improvements and daily optimizations

Hiring:

├─ Shipping BU: Add 1 CI Coordinator (Month 7)

├─ Ports BU: Add 2 CI Coordinators (Month 8) - one for Cars, one for Containers

├─ Cargo BU: Add 1 CI Coordinator (Month 9)

Training:

├─ Central team: Yellow Belt training (1 week)

├─ Kaizen facilitation training (1 week)

├─ Shadow senior analyst (2 weeks)

└─ Begin coordinating Kaizen events

MONTH 10-12: MATURE OPERATING MODEL

Community of Practice:

├─ Monthly meetings: All analysts (embedded + central) meet

│   ├─ Share successes and challenges

│   ├─ Cross-pollinate ideas

│   └─ Peer learning and support

│

├─ Quarterly showcases: BUs present major improvements

│   ├─ Shipping: "How we reduced vessel turnaround time 20%"

│   ├─ Ports: "Terminal dwell time improvement"

│   └─ Cargo: "Route optimization delivering €300K savings"

│

└─ Annual summit: All-day excellence event

├─ Best practice sharing

├─ Awards and recognition

└─ Next year planning

Green Belt Certification Program:

├─ All embedded analysts: Green Belt training (6 months)

├─ Central LSS Master: Delivers training + project mentoring

├─ Certification: Complete Green Belt project (process improvement)

└─ Timeline: Start Month 7, complete Month 12

Cross-BU Projects:

├─ Identify opportunities: Where can Shipping learnings help Ports?

├─ Head of Excellence: Facilitates knowledge transfer

├─ Example projects:

│   ├─ "Apply Shipping's automated gate system to Ports terminals"

│   └─ "Harmonize booking processes across Shipping and Cargo"

MONTH 12 DELIVERABLE:

├─ 6-8 people embedded (analysts + CI coordinators)

├─ All analysts Green Belt certified ✅

├─ Community of practice thriving ✅

├─ Cross-BU learning happening ✅

├─ Process improvement results: €2-3M value delivered Year 1 ✅

## Governance: How Hybrid Model is Managed

### Monthly Operating Rhythm

MONTHLY CALENDAR (Each Business Unit)

WEEK 1: BUSINESS UNIT OPERATIONS REVIEW

├─ Meeting: COO + Operations Leadership + Embedded Process Excellence

├─ Duration: 2 hours

├─ Agenda:

│   ├─ Operations performance (KPIs, issues, challenges)

│   ├─ Process improvement updates (projects in progress)

│   ├─ New priorities (what should Process Excellence focus on next?)

│   └─ Resource needs (is analyst capacity sufficient?)

│

└─ Output: Priorities for embedded Process Analyst next month

WEEK 2: COMMUNITY OF PRACTICE (Cross-BU)

├─ Meeting: All Process Analysts (embedded + central) + Head of Excellence

├─ Duration: 90 minutes (virtual)

├─ Agenda:

│   ├─ Project updates (what each analyst working on)

│   ├─ Challenges and problem-solving (peer support)

│   ├─ Best practice sharing (what's working well)

│   ├─ Methodology Q&A (questions on Lean Six Sigma techniques)

│   └─ Cross-BU opportunities (could Shipping insight help Ports?)

│

└─ Output: Shared learning, collaboration opportunities identified

WEEK 3: CENTRAL EXCELLENCE GOVERNANCE

├─ Meeting: Head of Business Excellence + embedded analysts (1:1s)

├─ Duration: 30 min per analyst (individual check-ins)

├─ Agenda:

│   ├─ Project quality review (are projects following methodology?)

│   ├─ Coaching and mentoring (technical support)

│   ├─ Professional development (career progression, training needs)

│   └─ Standards compliance (any issues with methodology adherence?)

│

└─ Output: Quality assurance, coaching, development planning

WEEK 4: PORTFOLIO & PLANNING

├─ Meeting: COOs + Head of BPM + Head of Excellence

├─ Duration: 1 hour

├─ Agenda:

│   ├─ Process improvement results YTD (value delivered)

│   ├─ Cross-BU opportunities (projects requiring collaboration)

│   ├─ Resource allocation (any BU needs surge support?)

│   └─ Next quarter planning (priorities alignment)

│

└─ Output: Cross-BU coordination, resource flexing if needed

### Quarterly Strategic Reviews

QUARTERLY BUSINESS EXCELLENCE REVIEW

Attendees: CEO, COOs (all BUs), Head of BPM, Head of Excellence, embedded analysts

Duration: 3 hours

Frequency: Quarterly

AGENDA:

1. RESULTS REVIEW (60 min)

├─ Each BU presents process improvement results:

│   ├─ Shipping BU: "Q1 achievements: 3 projects, €800K value"

│   ├─ Ports BU: "Q1 achievements: 4 projects, €1.2M value"

│   └─ Cargo BU: "Q1 achievements: 2 projects, €400K value"

│

├─ Total enterprise: €2.4M value delivered Q1

├─ Trends: Are we accelerating? Slowing?

└─ Success stories: Deep dive on 1-2 major wins

2. CROSS-BU LEARNING (45 min)

├─ Best practice showcase:

│   ├─ Shipping: "Automated gate system reduced processing time 60%"

│   ├─ Discussion: Could this apply to Ports? To Cargo?

│   └─ Decision: Ports to pilot similar approach

│

└─ Identify 2-3 cross-BU opportunities for next quarter

3. METHODOLOGY & STANDARDS (30 min)

├─ Head of Excellence: Methodology updates

│   ├─ New tools introduced

│   ├─ Training programs launched

│   └─ Quality metrics (project deliverable quality improving)

│

└─ Certification progress: Green Belts, Black Belts

4. STRATEGIC PRIORITIES (45 min)

├─ CEO: Strategic priorities next quarter

│   ├─ "Cost reduction is priority - target €5M savings by year-end"

│   └─ "Customer satisfaction improvement needed in Shipping"

│

├─ Discussion: How can Process Excellence contribute?

│   ├─ Cost reduction: Embedded analysts identify opportunities

│   ├─ Customer satisfaction: Focus on customer-facing processes

│   └─ Resource allocation: Any major initiatives need central team support?

│

└─ Commitments: Each BU commits to specific targets next quarter

5. ORGANIZATIONAL DEVELOPMENT (30 min)

├─ Team health: Is hybrid model working?

│   ├─ Analyst satisfaction survey results

│   ├─ COO satisfaction with embedded analysts

│   └─ Any friction or challenges?

│

├─ Hiring needs: Any BUs need additional analysts?

└─ Recognition: Celebrate top performers (analyst of the quarter award)

OUTPUT:

├─ Q1 results documented (€2.4M value)

├─ Q2 priorities aligned (CEO + COOs + Process Excellence)

├─ Cross-BU projects identified (2-3 initiatives)

├─ Commitments: Each BU commits to specific improvements

└─ Actions: Hiring, training, methodology updates

## Case Studies: Hybrid Model in Action

### Case Study 1: Terminal Dwell Time Reduction (Embedded Success)

SCENARIO: Ports BU Container Terminal - Dwell Time Too High

Business Context:

├─ Container dwell time: 5.2 days average (vs. 3 days industry benchmark)

├─ Business impact: Terminal capacity constrained, revenue lost

├─ COO Ports priority: "This is my #1 issue, fix it"

EMBEDDED MODEL ADVANTAGE:

Week 1-2: Immediate Response

├─ COO Ports → Senior Process Analyst (Ports, embedded)

├─ Analyst immediately available (no request queue, no prioritization delay)

├─ Analyst deeply understands context:

│   ├─ Knows terminal layout, equipment, staffing

│   ├─ Knows seasonal patterns (peak months, lulls)

│   ├─ Knows key personnel and organizational dynamics

│   └─ Trusts built (operations staff open about real issues)

Week 3-4: Root Cause Analysis

├─ Analyst observes operations (on-site daily)

├─ Data analysis: Where is time spent?

│   ├─ Receiving: 1.2 days

│   ├─ Storage: 2.5 days ⚠️ (biggest opportunity)

│   └─ Dispatch: 1.5 days

│

├─ Root causes identified:

│   ├─ Inefficient yard planning (containers stored far from gate)

│   ├─ Manual inspection bottleneck (30 min per container)

│   └─ Customs clearance delays (documentation issues)

│

└─ Operations staff candid (trust embedded analyst, reveal informal workarounds)

Week 5-6: Solution Design (Embedded + Central Collaboration)

├─ Embedded analyst leads workshops with terminal managers

├─ Solutions identified:

│   ├─ Quick win: Optimize yard planning process (no IT needed)

│   ├─ Medium: Automate inspection (IT solution, 3 months)

│   └─ Long-term: Pre-clear customs (process change + minor IT)

│

├─ Consults Central LSS Master:

│   ├─ "Is yard optimization approach sound?" (validation)

│   ├─ "Have other ports solved this?" (best practice research)

│   └─ Central Master: "Yes, approach is good. Here's similar case from Rotterdam port."

│

└─ Business case developed (follows standard template from central)

Week 7: Approval & Implementation

├─ Presents to COO Ports (embedded analyst has direct access)

├─ COO approves immediately (trusts analyst, sees business case)

├─ Implementation begins same week (no bureaucracy, no central approval needed)

└─ Timeline: From problem identification to implementation start: 7 weeks ✅

Week 8-20: Implementation (13 weeks)

├─ Quick win: Yard optimization (process change)

│   ├─ Embedded analyst + terminal manager redesign process

│   ├─ CI Coordinator trains staff (new yard planning approach)

│   ├─ Pilot 2 weeks, then full rollout

│   └─ Result: Dwell time reduced 0.8 days (5.2 → 4.4 days) ✅

│

├─ IT solution: Automated inspection (yard optimization algorithm)

│   ├─ Embedded analyst hands off to IT Business Analyst (clear requirements)

│   ├─ Ports - Containers Team builds (3 months)

│   ├─ Embedded analyst participates in UAT (business validation)

│   └─ Result: Dwell time reduced additional 0.9 days (4.4 → 3.5 days) ✅

│

└─ Process change: Pre-clear customs

├─ Embedded analyst works with customs team

├─ New process: Submit documents 24h before container arrival

└─ Result: Dwell time reduced additional 0.3 days (3.5 → 3.2 days) ✅

WEEK 21: RESULTS & KNOWLEDGE SHARING

Results:

├─ Dwell time: 5.2 days → 3.2 days (38% improvement) ✅

├─ Business impact: Terminal capacity +18%, revenue +€1.5M/year ✅

├─ Timeline: 21 weeks from problem to full results ✅

Knowledge Sharing (Central Excellence Facilitates):

├─ Embedded analyst documents case study (standard template)

├─ Presents at Community of Practice meeting:

│   └─ "How we reduced dwell time 38%: yard optimization + automation + process change"

│

├─ Other BUs learn:

│   ├─ Shipping BU: "Could apply yard optimization to our cargo yards" (adopts approach)

│   ├─ Cars Terminal: "Could use similar automated inspection" (pilots solution)

│   └─ Cross-pollination value: Additional €500K savings in other BUs ✅

│

└─ Central Excellence: Documents in best practice repository

TOTAL VALUE:

├─ Ports BU direct: €1.5M/year

├─ Other BUs (cross-pollination): €500K/year

└─ Total: €2M/year value from one embedded analyst project ✅

WHY EMBEDDED MODEL WORKED:

✅ Speed: 7 weeks from problem to start (vs. months if centralized queue)

✅ Expertise: Analyst knew terminal intimately (deep domain knowledge)

✅ Trust: Operations staff candid about real issues (embedded = trusted)

✅ Ownership: COO Ports owned solution (analyst reports to COO, direct accountability)

✅ Results: 38% improvement, €2M value ✅

### Case Study 2: Cross-BU Harmonization (Central Excellence Success)

SCENARIO: Post-Merger Process Harmonization (Shipping Tool A vs. Tool B)

Business Context:

├─ Post-merger: Two shipping systems (Tool A from Company A, Tool B from Company B)

├─ Different processes: Booking process in Tool A (12 steps) vs. Tool B (18 steps)

├─ Business impact: Confusion, inconsistency, training overhead

├─ CEO mandate: "Harmonize processes before migrating to new shipping system"

CENTRAL EXCELLENCE ADVANTAGE:

Week 1-4: Project Scoping (Central Leads)

├─ Head of Business Excellence: Leads harmonization initiative

│   ├─ Why central? Cross-BU project (affects both legacy tool user groups)

│   ├─ Too big for one embedded analyst (needs coordination across divisions)

│   └─ Requires neutral facilitator (embedded analyst in one division = bias)

│

├─ Project team:

│   ├─ Central LSS Master: Project lead

│   ├─ Shipping embedded analyst: 30% time (represents Tool A users)

│   ├─ Process analyst from other division: 30% time (represents Tool B users)

│   └─ IT Business Analyst: Requirements translation

│

└─ Governance: Steering committee (both division heads + Head of Excellence)

Week 5-12: Current State Analysis (8 weeks)

├─ LSS Master: Leads process mapping

│   ├─ Tool A booking process: Documented (12 steps, 45 min avg)

│   ├─ Tool B booking process: Documented (18 steps, 65 min avg)

│   └─ Comparison analysis: Where do processes diverge? Why?

│

├─ Root causes identified:

│   ├─ Both processes achieve same outcome (confirmed booking)

│   ├─ Tool B has 6 extra steps (redundant approvals from legacy company culture)

│   ├─ Tool A has 4 automated steps that Tool B does manually

│   └─ Neither process is "best" - both have strengths and weaknesses

│

└─ Embedded analysts provide context:

├─ "Tool A users resist change - this is how they've always done it"

├─ "Tool B users don't trust automation - want manual controls"

└─ Central LSS Master navigates politics (neutral third party)

Week 13-20: Future State Design (8 weeks)

├─ Central LSS Master facilitates workshops:

│   ├─ Attendees: Tool A users, Tool B users, IT, embedded analysts

│   ├─ Approach: "Best of both" (not forcing one process on everyone)

│   └─ Output: Harmonized process design (10 steps, 35 min target)

│

├─ Harmonized process features:

│   ├─ From Tool A: Automation (4 automated steps)

│   ├─ From Tool B: Risk controls (2 approval steps for high-value bookings)

│   ├─ Eliminated: 6 redundant steps from Tool B

│   └─ Simplified: Consolidated 3 similar steps from Tool A into 1

│

└─ Consensus building (Central Excellence facilitates):

├─ Tool A users: Initially resistant, but see benefits of harmonization

├─ Tool B users: Initially defensive, but recognize redundancy

└─ Steering committee: Approves future state (both divisions aligned)

Week 21-40: Implementation (20 weeks)

├─ IT implementation:

│   ├─ IT Business Analyst: Translates process to requirements

│   ├─ Shipping Solutions Team: Implements in new shipping system

│   └─ Timeline: 16 weeks development + 4 weeks testing

│

├─ Change management (Central Change Management team):

│   ├─ Communication: "Why we're harmonizing, what's changing"

│   ├─ Training: 150 users trained (Tool A and Tool B users)

│   ├─ Stakeholder engagement: Address resistance proactively

│   └─ Adoption monitoring: Ensure users following new process

│

└─ Embedded analysts support:

├─ In their divisions: Champion change, answer questions

└─ Feedback to central team: "Here's what's working, here's what's not"

Week 41+: Post-Implementation

├─ Results measured (Performance Analyst, central):

│   ├─ Booking time: 55 min avg → 35 min avg (36% faster) ✅

│   ├─ User satisfaction: 3.2/5 → 4.1/5 (improved) ✅

│   ├─ Training overhead: 50% reduction (one process, not two) ✅

│   └─ Value: €800K/year savings (time saved + reduced errors) ✅

│

├─ Knowledge capture (Central Excellence):

│   ├─ Case study: "How we harmonized post-merger processes"

│   ├─ Lessons learned: "Keys to successful harmonization"

│   └─ Reusable approach: Template for future harmonization projects

│

└─ Recognition:

├─ Annual Excellence Summit: Project showcased as success story

└─ Team recognized: Central LSS Master + embedded analysts + IT team

WHY CENTRAL MODEL WORKED:

✅ Neutral facilitator: Central team = no divisional bias (both sides trusted)

✅ Cross-BU coordination: Central Excellence = natural coordinator

✅ Methodology expertise: LSS Master brought rigorous approach (not ad-hoc)

✅ Best practice synthesis: Central team could see "best of both" (not siloed)

✅ Change management: Central Change team supported adoption across divisions

✅ Knowledge capture: Process documented for future projects ✅

HYBRID MODEL VALUE:

├─ Central led complex cross-BU project (appropriate)

├─ Embedded analysts contributed (domain expertise, local support)

└─ Best of both: Central coordination + embedded expertise = success ✅

### Case Study 3: Surge Capacity (Central Team Supports BU)

SCENARIO: Ports BU Major Transformation - Need Surge Support

Business Context:

├─ Ports BU launching new terminal operating system (TOS)

├─ Major transformation: Redesign all terminal processes (gate, yard, rail, barge)

├─ Timeline: 9 months (aggressive)

├─ Challenge: 1 embedded Process Analyst insufficient for scope

HYBRID MODEL FLEXIBILITY:

Month 1: Resource Gap Identified

├─ COO Ports: "We need major process redesign for new TOS"

├─ Embedded Process Analyst (Ports): "This is 12 months of work for me, but we need it in 9 months"

├─ COO Ports → Head of Business Excellence: "Can I get temporary support?"

└─ Head of Excellence: "Yes, I'll deploy central LSS Master to support (6 months, 80% time)"

Month 2-7: Surge Team (Embedded + Central)

├─ Team structure:

│   ├─ Embedded Ports Process Analyst: Leads project (100% time)

│   ├─ Central LSS Master: Supports project (80% time, 6 months)

│   ├─ CI Coordinator (Ports): Supports project (50% time)

│   └─ IT Business Analyst: Requirements translation (50% time)

│

├─ Division of labor:

│   ├─ Embedded analyst: Gate and yard processes (knows well, most critical)

│   ├─ Central LSS Master: Rail and barge processes (less familiar, LSS Master can learn)

│   ├─ Both: Integration points (ensure processes work together)

│   └─ CI Coordinator: Quick wins and training

│

└─ Benefits:

├─ Embedded analyst: Domain expertise on critical processes

├─ Central LSS Master: Advanced methodology (complex transformation needs rigor)

├─ Together: Cover scope in 9 months (vs. 12 months solo)

└─ Knowledge transfer: Central LSS Master learns terminal operations (builds central team capability)

Month 8-9: Transition & Deployment

├─ Processes redesigned: 15 major processes, documented ✅

├─ IT requirements: Handed to IT team (clear, detailed)

├─ Training materials: Developed with Change Management team

└─ Central LSS Master: Rolls off project (mission accomplished)

Month 10+: Embedded Analyst Continues Solo

├─ Embedded analyst: Supports TOS go-live (hypercare)

├─ Embedded analyst: Fine-tunes processes post-implementation

└─ Central LSS Master: Available for questions, but primary work done

RESULTS:

├─ Project completed: 9 months (on time) ✅

├─ Process transformation: 15 processes redesigned ✅

├─ New TOS: Successful go-live (smooth adoption) ✅

└─ Value: €2M/year (terminal efficiency improved 25%) ✅

WHY HYBRID MODEL WORKED:

✅ Flexible capacity: Central team could surge-support BU (embedded model alone = insufficient capacity)

✅ Maintained ownership: COO Ports owned project (embedded analyst led)

✅ Expertise blend: Embedded domain knowledge + central methodology = success

✅ Efficient: After surge, central team redeployed (not permanent cost to Ports BU)

✅ Knowledge transfer: Central team learned terminals (builds central capability) ✅

FINANCIAL MODEL:

├─ Ports BU cost: Embedded analyst salary (€75K full year = permanent)

├─ Central BPM cost: LSS Master 80% × 6 months (€90K × 0.8 × 0.5 = €36K surge cost)

├─ Total Ports project cost: €75K + €36K = €111K

└─ Alternative (hire temp consultant): €150-200K (more expensive, less knowledge retention)

HYBRID VALUE: Surge capacity available when needed, but not permanent BU cost ✅

## Hybrid Model: Success Metrics

### How to Measure If Hybrid Model is Working

QUARTERLY SCORECARD: BUSINESS EXCELLENCE (HYBRID MODEL)

EMBEDDED ANALYST EFFECTIVENESS:

├─ Business Unit satisfaction: 4+/5 (COOs rate their embedded analysts)

│   ├─ Shipping: 4.3/5 ✅

│   ├─ Ports: 4.5/5 ✅

│   └─ Cargo: 3.8/5 ⚠️ (investigate: why lower?)

│

├─ Projects completed per analyst: 3-4/year (major projects)

│   ├─ Target: 3-4 major projects (3-6 months each) + 10-15 quick wins

│   ├─ Actual Shipping: 4 major + 12 quick wins ✅

│   ├─ Actual Ports: 3 major + 18 quick wins ✅

│   └─ Actual Cargo: 2 major + 8 quick wins ⚠️ (underutilized? or fewer opportunities?)

│

├─ Value delivered per analyst: €500K-1M/year per analyst

│   ├─ Shipping analyst: €1.2M/year ✅

│   ├─ Ports analyst: €1.8M/year ✅ (exceptional!)

│   └─ Cargo analyst: €400K/year ⚠️ (below target, investigate)

│

└─ Domain expertise: Analysts demonstrate deep business knowledge

├─ Measured by: COO feedback, project quality, stakeholder trust

└─ All analysts: Strong domain expertise ✅

CENTRAL EXCELLENCE EFFECTIVENESS:

├─ Methodology compliance: 95%+ projects follow Lean Six Sigma standards

│   ├─ Audit: Central team reviews 20% of projects (random sample)

│   └─ Actual: 97% compliance ✅

│

├─ Training delivered: All embedded analysts certified

│   ├─ Green Belt: 100% (all analysts) ✅

│   ├─ Black Belt: 1 analyst (in progress) ✅

│   └─ Yellow Belt: 25 operations managers trained ✅

│

├─ Cross-BU knowledge sharing: 4+ initiatives/year

│   ├─ Q1: Gate automation (Shipping → Ports transfer)

│   ├─ Q2: Yard optimization (Ports → Shipping transfer)

│   ├─ Q3: Route optimization (Cargo → Shipping transfer)

│   └─ Q4: (Planned) Customer portal improvements

│   └─ Actual: 3 YTD, on track for 4+ ✅

│

└─ Cross-BU value: €500K-1M/year (from knowledge sharing)

├─ Gate automation applied to Ports: €400K

├─ Yard optimization applied to Shipping: €300K

└─ Total cross-pollination value: €700K ✅

COLLABORATION QUALITY:

├─ Community of Practice attendance: 90%+ (embedded analysts participate)

│   └─ Actual: 95% avg attendance ✅

│

├─ Embedded-Central relationship: 4+/5

│   ├─ Embedded analysts rate central team support: 4.2/5 ✅

│   ├─ Central team rates embedded analyst collaboration: 4.4/5 ✅

│   └─ No friction, healthy partnership ✅

│

└─ Matrix reporting working: No conflicts escalated to CEO

├─ Decision rights clear

├─ Both solid and dotted lines functioning well

└─ Zero escalations ✅ (healthy)

FINANCIAL PERFORMANCE:

├─ Total value delivered: €5M/year (all BUs combined)

│   ├─ Shipping BU: €1.8M

│   ├─ Ports BU: €2.2M

│   ├─ Cargo BU: €400K ⚠️

│   └─ Cross-BU: €700K

│

├─ Investment: €1.485M/year (embedded + central)

├─ ROI: 237% (€5M value / €1.485M cost) ✅

└─ Target exceeded: Target was 150% ROI, actual 237% ✅

RED FLAGS (Investigate):

⚠️ Cargo BU underperforming:

├─ Value: €400K (vs. €500

## Hybrid Model: Success Metrics (continued)

RED FLAGS (Investigate) (continued):

⚠️ Cargo BU underperforming:

├─ Value: €400K (vs. €500K+ target)

├─ Projects: 2 major + 8 quick wins (vs. 3-4 major + 10-15 quick wins target)

├─ COO satisfaction: 3.8/5 (vs. 4+/5 target)

│

└─ ROOT CAUSE INVESTIGATION:

├─ Interview COO Cargo: "Is analyst effective? Sufficient? Right priorities?"

├─ Interview analyst: "Challenges? Barriers? Support needs?"

├─ Review projects: Quality OK? Scope appropriate?

│

└─ POTENTIAL ISSUES & ACTIONS:

├─ Issue 1: Cargo BU smaller (fewer opportunities than Shipping/Ports)

│   └─ Action: Accept lower absolute value, but ensure ROI still strong

│

├─ Issue 2: Analyst capability gap (less experienced than others)

│   └─ Action: Additional coaching from central LSS Master, paired with senior analyst

│

├─ Issue 3: COO not engaged (not prioritizing process improvement)

│   └─ Action: Head of Excellence + COO discussion (executive alignment)

│

└─ Issue 4: Cargo operations less mature (fewer quick wins available)

└─ Action: Focus on foundational improvements first (build capability)

## Decision Framework: When to Use Embedded vs. Central vs. Both

To help you and your team decide in real-time which capability to use:

PROJECT DECISION TREE

NEW PROCESS IMPROVEMENT OPPORTUNITY IDENTIFIED:

Q1: Is this single Business Unit (BU) or cross-BU?

├─ SINGLE BU → Continue to Q2

└─ CROSS-BU → CENTRAL LEADS (with embedded analysts contributing)

Q2: Is this strategic (multi-month, high complexity) or tactical (quick win)?

├─ STRATEGIC → Continue to Q3

└─ TACTICAL → EMBEDDED HANDLES (CI Coordinator leads)

Q3: Does embedded analyst have capacity?

├─ YES → EMBEDDED LEADS (may consult central for complex methodology)

└─ NO (overloaded) → CENTRAL PROVIDES SURGE SUPPORT or PRIORITIZE/DEFER

Q4: Does this require advanced methodology (Black Belt techniques)?

├─ YES → CENTRAL LSS MASTER SUPPORTS (embedded analyst collaborates)

└─ NO → EMBEDDED HANDLES (standard Green Belt techniques sufficient)

Q5: Is this politically sensitive (cross-division, post-merger, contentious)?

├─ YES → CENTRAL LEADS (neutral facilitator)

└─ NO → EMBEDDED HANDLES

DECISION SUMMARY:

├─ EMBEDDED handles: 70-80% (single BU, tactical-to-medium complexity)

├─ CENTRAL handles: 10-15% (cross-BU, complex, political)

└─ BOTH collaborate: 10-15% (embedded leads, central supports or vice versa)

### Specific Examples Using Decision Tree

Example 1: "Reduce booking processing time in Shipping"

Q1: Single BU or cross-BU? → Single BU (Shipping only)

Q2: Strategic or tactical? → Strategic (3-month project)

Q3: Embedded analyst capacity? → Yes (has capacity)

Q4: Advanced methodology needed? → No (standard Lean)

Q5: Politically sensitive? → No (routine improvement)

DECISION: EMBEDDED SHIPPING ANALYST LEADS ✅

└─ May consult central LSS Master for complex analysis, but embedded analyst owns project

Example 2: "Harmonize customs processes across Shipping, Ports, and Cargo"

Q1: Single BU or cross-BU? → Cross-BU (all three BUs)

DECISION: CENTRAL EXCELLENCE LEADS ✅

├─ Central LSS Master: Project lead

├─ All three embedded analysts: Contribute 20-30% time (represent their BUs)

└─ Why central: Neutral facilitator, cross-BU coordination capability

Example 3: "Quick win - Reduce gate processing time at one terminal"

Q1: Single BU or cross-BU? → Single BU (Ports)

Q2: Strategic or tactical? → Tactical (quick win, 2-4 weeks)

DECISION: CI COORDINATOR (PORTS) HANDLES ✅

├─ Facilitates Kaizen event (1-day workshop)

├─ Implements improvements (2 weeks)

└─ Senior Process Analyst (Ports) not needed (CI Coordinator sufficient)

Example 4: "Complex Six Sigma project - Reduce defect rate in container handling"

Q1: Single BU or cross-BU? → Single BU (Ports)

Q2: Strategic or tactical? → Strategic (6-month project)

Q3: Embedded analyst capacity? → Yes

Q4: Advanced methodology needed? → Yes (Six Sigma DMAIC, statistical analysis)

DECISION: EMBEDDED ANALYST LEADS + CENTRAL LSS MASTER SUPPORTS ✅

├─ Embedded Ports analyst: Project lead (domain expertise, stakeholder management)

├─ Central LSS Master: Methodology coach (30% time, statistical analysis support)

└─ Collaboration: Embedded owns project, central provides technical expertise

Example 5: "Post-merger process harmonization (politically sensitive)"

Q1: Single BU or cross-BU? → Cross-BU (merger affects multiple divisions)

Q2: Strategic or tactical? → Strategic (9-month project)

Q3: Embedded analyst capacity? → Yes, but...

Q4: Advanced methodology needed? → Yes (complex change management)

Q5: Politically sensitive? → YES (post-merger, cultural differences, resistance expected)

DECISION: CENTRAL EXCELLENCE LEADS ✅

├─ Central LSS Master: Project lead and neutral facilitator

├─ Embedded analysts: Contribute (represent their divisions, local support)

├─ Change Management (central): Supports adoption

└─ Why central: Neutral = both sides trust, central = political navigation capability

## Final Recommendation Summary

### Your Answer: Hybrid Model is Best ⭐

You were absolutely right to question centralized BPM. For Process Optimization and Business Excellence, embedding in Business Units with central support is superior to pure centralization.

### Recommended Structure (Hybrid):

EMBEDDED IN BUSINESS UNITS (5-8 people, €435K):

├─ Shipping BU: 2-3 (Senior Process Analyst + CI Coordinator)

├─ Ports BU: 2-3 (Senior Process Analyst + CI Coordinators)

└─ Cargo BU: 1-2 (Process Analyst + CI Coordinator)

└─ Reports to: Business Unit COOs (solid line)

└─ Close to operations, domain expertise, speed, ownership

CENTRAL BPM (10-16 people, €1.05M):

├─ Portfolio & Demand Management (5-7) ⭐ STAYS CENTRAL

│   └─ IT gateway, enterprise portfolio governance

│

├─ Change Management (3-5) ⭐ STAYS CENTRAL

│   └─ Major transformation support, adoption management

│

└─ Business Excellence CoE (2-4) ⭐ SMALL CENTRAL TEAM

├─ Methodology and standards (Lean Six Sigma)

├─ Training and certification (Green/Black Belt)

├─ Cross-BU knowledge sharing (best practice transfer)

├─ Complex cross-BU projects (harmonization, enterprise programs)

└─ Dotted-line governance of embedded analysts

Total: 15-24 people, €1.485M/year

### Why Hybrid is Best for You:

✅ Logistics Context: Three distinct business units (Shipping, Ports, Cargo) with different operations ✅ Domain Expertise Critical: Process analysts need deep operational knowledge (embedded enables this) ✅ Business Unit Ownership: COOs accountable for operational excellence in their BUs ✅ Speed and Responsiveness: Embedded analysts can act immediately (no central queue) ✅ Trust and Culture: Embedded analysts become "one of us" (higher acceptance) ✅ Cross-BU Learning: Central Excellence facilitates knowledge sharing (avoid silos) ✅ Consistent Standards: Central sets methodology (avoid ad-hoc approaches) ✅ Flexible Capacity: Central can surge-support BUs when needed ✅ Cost Efficient: 20% cheaper than fully centralized (€1.485M vs. €1.85M)

### What Doesn't Change:

Portfolio & Demand Management → Still centralized ✅

- Rationale: IT portfolio is enterprise-level (not BU-specific)

- Need: Single governance model across all BUs

- Benefit: Consistent prioritization, clear IT gateway

Change Management → Still centralized ✅

- Rationale: Major transformations cross BUs (IT systems, org changes)

- Need: Enterprise-wide change capability

- Benefit: Consistent change approach, economies of scale

### Key Success Factors for Hybrid:

- Clear Matrix Reporting: Embedded analysts report to COOs (solid line) + Head of Excellence (dotted line)

- Strong Community of Practice: Monthly meetings, quarterly showcases, annual summit

- Standard Methodology: All analysts use Lean Six Sigma (central defines, embedded applies)

- Cross-BU Facilitation: Central Excellence actively facilitates knowledge transfer

- Flexible Resources: Central team can surge-support BUs when needed

- Measurement: Track both BU-level and enterprise-level results

## Implementation Roadmap: Hybrid Model

### Quick Start (Next 90 Days)

MONTH 1: DECISION & DESIGN

Week 1-2: Validate Hybrid Model

├─ Review this analysis with Head of IT, COOs

├─ Get consensus: Hybrid approach (embedded + central)

├─ Socialize with stakeholders

Week 3-4: Detailed Design

├─ Define roles (embedded vs. central responsibilities)

├─ Define matrix reporting (solid vs. dotted line)

├─ Define standards (Lean Six Sigma methodology)

├─ Budget approval: €1.485M/year

MONTH 2: HIRE CENTRAL TEAM

├─ Head of Business Excellence (Month 2)

├─ LSS Master Black Belt (Month 2-3)

├─ Performance Analyst (Month 3)

└─ Central team: Develops methodology and standards

MONTH 3: HIRE EMBEDDED ANALYSTS

├─ COO Shipping: Hires Senior Process Analyst - Shipping

├─ COO Ports: Hires Senior Process Analyst - Ports

├─ COO Cargo: Hires Process Analyst - Cargo

└─ Embedded analysts: Start 2-week central training (Month 3 end)

DELIVERABLE (Day 90):

├─ Central Excellence CoE: Operational (3 people)

├─ Embedded analysts: Hired and trained (3 people)

├─ Methodology: Defined and documented

├─ First projects: Launching (one per BU)

└─ Hybrid model: Functioning

## Final Summary: Your Three Questions Answered

### Question 1: Stream-aligned team structure

Answer: ✅ 8 teams (Shipping, Ports-Cars, Ports-Containers, Customs separate, Commercial combined, Cargo, Finance, HR)

### Question 2: Vendor Management placement

Answer: ✅ Separate from IT, reports to CTO (peer to other IT heads), 6-9 people

### Question 3: Service Desk placement

Answer: ✅ Under Platform Engineering (Tier 1 of Application Support), 5-7 people

### Question 4 (your latest): Should Process Optimization be embedded in BUs?

Answer: ✅ YES - Hybrid Model Best (embedded analysts in BUs + small central CoE)

## Complete Transformation Blueprint - Final Numbers

### Complete Organization (IT + BPM Hybrid):

━━━━━━━━━━━━━━━━━━━━━━━━━━━━━━━━━━━━━━━━━━━━━━━━━━━━━━━━━━━

TOTAL TRANSFORMATION ORGANIZATION

━━━━━━━━━━━━━━━━━━━━━━━━━━━━━━━━━━━━━━━━━━━━━━━━━━━━━━━━━━━

IT ORGANIZATION (CTO):

├─ Business Solutions & Delivery: 85-100

├─ Enterprise Architecture: 8-10

├─ Data & AI: 11-14

├─ Platform Engineering: 36-45 (includes Application Support)

├─ Vendor Management: 6-9

└─ IT Total: 146-178 people

BPM & EXCELLENCE (Hybrid):

├─ Embedded in Business Units: 5-8

├─ Central BPM: 10-16

└─ BPM Total: 15-24 people

━━━━━━━━━━━━━━━━━━━━━━━━━━━━━━━━━━━━━━━━━━━━━━━━━━━━━━━━━━━

GRAND TOTAL: 161-202 people

(Current baseline: ~105, Growth: +56-97 people)

━━━━━━━━━━━━━━━━━━━━━━━━━━━━━━━━━━━━━━━━━━━━━━━━━━━━━━━━━━━

TOTAL BUDGET:

├─ IT Transformation: €4.5M (Year 1)

├─ Application Support: €1.4M (Year 1)

├─ BPM Hybrid: €1.485M (Year 1)

└─ Total Year 1: €7.385M

TOTAL VALUE:

├─ IT Transformation: €3.5M (Year 1)

├─ Application Support: €2.5M (Year 1)

├─ BPM Hybrid: €5M (Year 1)

└─ Total Year 1: €11M

NET BENEFIT Year 1: €11M - €7.385M = €3.615M

ROI Year 1: 49%

3-Year Net Benefit: €35-45M

3-Year ROI: 180-220%

## You Now Have the Complete, Optimized Answer

Your insight was correct: Embedding Process Excellence in Business Units (with central support) is superior to pure centralization.

You now have:

- ✅ Complete organizational design (IT + BPM Hybrid)

- ✅ Embedded analysts in each BU (domain expertise, ownership, speed)

- ✅ Central Excellence CoE (methodology, training, cross-BU sharing)

- ✅ Clear governance (matrix reporting, decision rights)

- ✅ Case studies (how hybrid works in practice)

- ✅ Implementation roadmap (90-day quick start)

- ✅ Success metrics (how to measure hybrid effectiveness)

- ✅ Complete budget (€7.385M Year 1, €11M value, 49% ROI)

This is the optimal design for your logistics company transformation. 🎯

The Hybrid Model combines:

- Embedded capability (80%) = domain expertise, speed, ownership

- Central excellence (20%) = methodology, cross-BU learning, surge capacity

Ready to execute? You have everything you need. Go transform! 🚀✨

# Excellent Point - Naming is Critical for Organizational Clarity

You're absolutely right. "BPM" (Business Process Management) is misleading when the core functions are actually Portfolio Management, Demand Management, and Change Management - not primarily process optimization (which is now embedded in BUs).

Let me suggest better names that accurately reflect what this function does.

## The Core Challenge with "BPM"

Why "BPM" is Confusing:

WHAT PEOPLE THINK "BPM" MEANS:

├─ Business Process Management

├─ Implies: Process mapping, process optimization, workflow redesign

├─ Expected role: "They optimize our business processes"

└─ Reality: That's now embedded in BUs (Process Excellence analysts)

WHAT THIS FUNCTION ACTUALLY DOES:

├─ Portfolio & Demand Management (gateway to IT, prioritization)

├─ Change Management (adoption, training, organizational change)

├─ Business Excellence CoE (methodology, standards, cross-BU sharing)

└─ Reality: Portfolio governance + transformation support, NOT process optimization

RESULT: Confusion and misalignment

├─ Business: "We submitted process improvement request to BPM 3 months ago, nothing happened"

├─ BPM: "That's not our job, talk to your embedded Process Analyst"

└─ Everyone frustrated: Name creates wrong expectations

## Alternative Names - Ranked by Fit

### Option 1: "Business Solutions & Portfolio Office" ⭐ (RECOMMENDED)

Full Name: Business Solutions & Portfolio Office (BSPO) Short Name: Portfolio Office or Solutions Office

STRUCTURE:

├─ Head of Business Solutions & Portfolio

├─ Portfolio & Demand Management

├─ Change Management

└─ Business Excellence Center of Excellence

WHY THIS WORKS:

✅ "Business Solutions" = Clear (we help business solve problems)

✅ "Portfolio" = Accurate (we manage portfolio of initiatives)

✅ "Office" = Service function (support role, not line operations)

✅ No process confusion = Doesn't imply process optimization

✅ Neutral and professional = Widely understood in corporate context

WHAT PEOPLE WILL UNDERSTAND:

├─ "I need IT help" → "Go to Portfolio Office, they'll route your request"

├─ "We're launching new system" → "Portfolio Office will help with change management"

├─ "Is my project approved?" → "Portfolio Office manages all project approvals"

└─ Clear expectations, no confusion

Similar Names in Industry:

- Many companies use "Portfolio Management Office" (PMO)

- Some use "Business Solutions Office"

- Banks/Insurance often use "Transformation Office"

### Option 2: "Enterprise Solutions & Transformation" ⭐ (STRONG ALTERNATIVE)

Full Name: Enterprise Solutions & Transformation (EST) Short Name: Transformation Office or Solutions Team

STRUCTURE:

├─ Head of Enterprise Solutions & Transformation

├─ Portfolio & Demand Management

├─ Change Management

└─ Business Excellence Center of Excellence

WHY THIS WORKS:

✅ "Enterprise Solutions" = Broad scope (all business solutions, not just IT)

✅ "Transformation" = Accurate (change management, organizational transformation)

✅ Forward-looking = Signals innovation and improvement

✅ Executive-level positioning = Sounds strategic (important for Head role)

✅ No process confusion = Clear this is about solutions and transformation

WHAT PEOPLE WILL UNDERSTAND:

├─ "We're transforming our operations" → "Transformation team will support"

├─ "I need a solution to X problem" → "Enterprise Solutions team can help"

├─ "New initiative needs approval" → "Transformation Office manages portfolio"

└─ Modern, strategic, clear scope

Similar Names in Industry:

- Tech companies: "Transformation Office"

- Consulting firms: "Enterprise Solutions"

- Fortune 500: "Enterprise Transformation"

### Option 3: "Strategic Planning & Portfolio Office"

Full Name: Strategic Planning & Portfolio Office (SPPO) Short Name: Planning Office or Strategy Office

WHY THIS WORKS:

✅ "Strategic Planning" = What portfolio management actually is

✅ "Portfolio" = Clear governance and prioritization function

✅ "Office" = Service function

✅ Links to strategy = Shows connection to business strategy

POTENTIAL ISSUE:

⚠️ May sound like corporate strategy (overlaps with CEO's strategy function)

⚠️ "Planning" might imply they create strategy (they don't, they execute)

### Option 4: "Portfolio & Change Management Office"

Full Name: Portfolio & Change Management Office (PCMO) Short Name: Portfolio Office or PCM Office

WHY THIS WORKS:

✅ Accurate = Exactly what they do (portfolio + change)

✅ Descriptive = No ambiguity about scope

✅ Clear separation = Not process optimization

POTENTIAL ISSUE:

⚠️ Wordy (Portfolio + Change + Management + Office = long)

⚠️ Acronym "PCMO" not intuitive

### Option 5: "Business Transformation Office"

Full Name: Business Transformation Office (BTO) Short Name: Transformation Office or BTO

WHY THIS WORKS:

✅ Transformation = Change management, organizational change

✅ "Office" = Service function

✅ Simple = Easy to remember

✅ Strategic positioning = Sounds important

POTENTIAL ISSUE:

⚠️ Doesn't mention portfolio (key function not in name)

⚠️ May sound temporary ("transformation" implies eventual completion)

⚠️ Might imply they lead transformation (vs. support business-led transformation)

### Option 6: "Program Management Office" (Traditional PMO)

Full Name: Program Management Office (PMO) Short Name: PMO

WHY THIS WORKS:

✅ Well-understood = Industry-standard term

✅ Clear scope = Portfolio, project, program governance

✅ Established = People know what PMO does

POTENTIAL ISSUE:

⚠️ Often seen as bureaucratic ("PMO = red tape")

⚠️ Doesn't capture change management role

⚠️ May sound like project management (execution), not strategic

⚠️ "PMO" reputation sometimes negative (process police)

## My Top Recommendation: "Business Solutions & Portfolio Office" ⭐

### Why This is Best for You

1. Accurate Description:

WHAT THIS FUNCTION ACTUALLY DOES:

├─ Portfolio & Demand Management (60% of effort)

│   └─ "Portfolio" in the name ✅

│

├─ Change Management (30% of effort)

│   └─ "Solutions" includes change support ✅

│

└─ Business Excellence CoE (10% of effort)

└─ "Business" scope, not just IT ✅

NAME MATCHES REALITY: Business Solutions & Portfolio Office ✅

2. Clear Expectations:

WHEN PEOPLE HEAR "BUSINESS SOLUTIONS & PORTFOLIO OFFICE":

They think:

├─ "Solutions" = They help solve business problems ✅

├─ "Portfolio" = They manage portfolio of initiatives ✅

├─ "Office" = Service function, I can engage them ✅

└─ NOT process optimization = Clear boundary ✅

vs.

WHEN PEOPLE HEAR "BPM":

They think:

├─ "Process" = They optimize processes ❌ (Wrong expectation)

├─ Confusion = "Is this IT? Operations? Strategy?" ❌

└─ Vague scope = Unclear how to engage ❌

3. Professional and Neutral:

"BUSINESS SOLUTIONS & PORTFOLIO OFFICE"

├─ Professional = Corporate standard terminology

├─ Neutral = Not trendy or gimmicky

├─ Timeless = Won't sound dated in 5 years

├─ International = Works globally (if you have international operations)

└─ Respectable = Appropriate for executive-level function

4. Flexible Abbreviation:

WAYS TO REFER TO IT:

Formal: "Business Solutions & Portfolio Office"

Short: "Portfolio Office" (most common day-to-day)

Casual: "Solutions Office" or "Portfolio team"

Email: BSPO@ or PortfolioOffice@

Example usage:

├─ "Submit your request to the Portfolio Office"

├─ "Portfolio Office will review at next governance meeting"

├─ "Check with Portfolio Office on prioritization"

└─ Natural, easy to say, clear meaning

## Complete Naming Structure with Recommended Name

### Organizational Names with "Business Solutions & Portfolio Office"

━━━━━━━━━━━━━━━━━━━━━━━━━━━━━━━━━━━━━━━━━━━━━━━━━━━━━━━━━━━

CEO

━━━━━━━━━━━━━━━━━━━━━━━━━━━━━━━━━━━━━━━━━━━━━━━━━━━━━━━━━━━

│

┌────────────────────┼────────────────────┬───────────────┐

│                    │                    │               │

↓                    ↓                    ↓               ↓

┌───────────────┐    ┌───────────────┐    ┌──────────────┐  ┌────────────┐

│ CTO           │    │ Head of       │    │ COO Shipping │  │ COO Ports, │

│ (IT)          │    │ Bus Solutions │    │ BU           │  │ CFO, etc.  │

│               │    │ & Portfolio   │    │              │  │            │

└───────────────┘    └───────┬───────┘    └──────────────┘  └────────────┘

│

│

↓

┌─────────────────────────────────────────────────────────────┐

│ BUSINESS SOLUTIONS & PORTFOLIO OFFICE ⭐                    │

│ (Reports to CEO)                                            │

├─────────────────────────────────────────────────────────────┤

│                                                              │

│ Head of Business Solutions & Portfolio                      │

│ (Previously: "Head of BPM & Transformation")                │

│                                                              │

│ • Portfolio & Demand Management (5-7)                       │

│   ├─ Portfolio Manager                                      │

│   ├─ Demand Manager                                         │

│   ├─ Business Relationship Managers (2-3)                   │

│   └─ PMO Lead + Coordinators (1-2)                         │

│                                                              │

│ • Change Management (3-5)                                   │

│   ├─ Change Manager                                         │

│   ├─ Change Specialists (2-3)                              │

│   └─ Training & Adoption Lead                               │

│                                                              │

│ • Business Excellence Center of Excellence (2-4)            │

│   ├─ Head of Business Excellence                            │

│   ├─ Lean Six Sigma Master (1-2)                           │

│   └─ Performance Management Analyst                         │

│                                                              │

│ TOTAL: 10-16 people                                         │

└─────────────────────────────────────────────────────────────┘

EMBEDDED IN BUSINESS UNITS (not under Portfolio Office):

├─ Process Excellence Teams (report to BU COOs)

├─ 5-8 people total (embedded in Shipping, Ports, Cargo BUs)

└─ Dotted line to: Head of Business Excellence (for methodology)

## Sub-Team Naming Within Portfolio Office

Consider renaming sub-functions too for clarity:

### Current Names → Recommended Names

1. PORTFOLIO & DEMAND MANAGEMENT

Current: Portfolio & Demand Management ✅ (Keep as-is)

Why: Clear and accurate

2. CHANGE MANAGEMENT

Current: Change Management ✅ (Keep as-is)

Why: Industry standard, well understood

Alternative: "Change & Adoption" (emphasizes adoption focus)

3. BUSINESS EXCELLENCE CENTER OF EXCELLENCE

Current: Business Excellence CoE ⚠️ (Confusing - still sounds like process)

Recommended: "Process Excellence Support" or "Methodology & Standards"

Why: Clarifies this is methodology support, not process optimization

EVEN BETTER: "Continuous Improvement Support"

├─ Emphasizes: Supporting BU improvement efforts

├─ Clear: Not doing process optimization, supporting those who do

└─ Accurate: Training, methodology, knowledge sharing

### Complete Naming with Updated Sub-Functions

BUSINESS SOLUTIONS & PORTFOLIO OFFICE

├─ Portfolio & Demand Management Team

│   └─ "The Portfolio Team" (day-to-day reference)

│

├─ Change Management Team

│   └─ "The Change Team" or "Change & Adoption Team"

│

└─ Continuous Improvement Support

└─ "The CI Support Team" or "Methodology Team"

└─ NOT "Process Excellence" (avoids confusion with embedded analysts)

Alternative for #3:

- "Excellence Support"

- "Methodology & Standards"

- "Improvement Support"

- "Performance Excellence Support"

## Communication Plan: Rebranding from BPM

### Announcement Message

INTERNAL COMMUNICATION: NEW ORGANIZATION NAME

Subject: Introducing the Business Solutions & Portfolio Office

Team,

As we continue transforming how we manage initiatives and support change across

our organization, we're renaming our BPM function to better reflect what we

actually do.

WHAT'S CHANGING:

├─ OLD NAME: BPM & Transformation

└─ NEW NAME: Business Solutions & Portfolio Office ⭐

WHY THE CHANGE:

The name "BPM" (Business Process Management) created confusion. Many people

thought we optimize business processes - but that's now handled by Process

Excellence teams embedded in each Business Unit (Shipping, Ports, Cargo).

Our ACTUAL role is:

├─ Portfolio Management: Gateway to IT, prioritize initiatives, govern portfolio

├─ Demand Management: Single point of entry for IT and transformation requests

├─ Change Management: Support adoption of new systems and processes

└─ Continuous Improvement Support: Methodology and best practice sharing

The new name "Business Solutions & Portfolio Office" accurately describes what

we do: manage the portfolio of business solutions and support transformation.

WHAT DOESN'T CHANGE:

├─ Our services (portfolio, demand, change management)

├─ Your contacts (same people, same emails)

├─ How to engage us (same processes)

└─ Our commitment to supporting your success

HOW TO ENGAGE US:

├─ New IT or transformation need? → Contact Portfolio Office (Demand Manager or your BRM)

├─ Project approval? → Portfolio Office governs prioritization

├─ Launching new system? → Portfolio Office provides change management support

├─ Process improvement in your BU? → Contact your embedded Process Excellence analyst

YOUR CONTACTS:

├─ Shipping BU: [BRM Name] - [Email]

├─ Ports BU: [BRM Name] - [Email]

├─ Cargo BU: [BRM Name] - [Email]

└─ General inquiries: portfoliooffice@company.com

We look forward to continuing to support your success under our new name!

Best regards,

[Head of Business Solutions & Portfolio]

### Quick Reference Guide for Stakeholders

WHO TO CALL FOR WHAT:

PORTFOLIO OFFICE (formerly BPM):

├─ IT requests and new initiatives

├─ Project prioritization and approvals

├─ Change management for major transformations

└─ Contact: Your Business Relationship Manager or portfoliooffice@company.com

EMBEDDED PROCESS EXCELLENCE (in your Business Unit):

├─ Process optimization and improvement

├─ Kaizen events and quick wins

├─ Operational efficiency initiatives

└─ Contact: Your BU's Process Excellence analyst

├─ Shipping: [Name]

├─ Ports: [Name]

└─ Cargo: [Name]

IT SUPPORT (for technical issues):

├─ System issues, bugs, technical problems

├─ Password resets, access requests

└─ Contact: support@company.com or +XX XXX XXX XXXX

CLEAR BOUNDARIES = NO CONFUSION ✅

## Other Creative Names (If You Want Something More Distinctive)

If you want something more unique or forward-looking:

### Modern/Innovative Names:

"Strategic Solutions Office"

- Pro: Strategic positioning, solutions-focused

- Con: Might overlap with corporate strategy

"Enterprise Solutions Hub"

- Pro: Modern ("hub"), collaborative feel

- Con: "Hub" might sound too casual for some contexts

"Portfolio & Transformation Office"

- Pro: Accurately captures both functions

- Con: Long name, "PTO" acronym not intuitive

"Business Solutions Center"

- Pro: Simple, clear, service-oriented

- Con: Sounds operational, not strategic enough

"Solutions & Change Office"

- Pro: Captures two main functions (solutions = portfolio, change = adoption)

- Con: Doesn't mention portfolio governance explicitly

### Industry-Specific Names (Logistics Context):

"Operations Solutions Office"

- Pro: Fits logistics/operations focus

- Con: Might be confused with operational teams

"Business Solutions & Performance Office"

- Pro: Performance = continuous improvement aspect

- Con: Longer name

"Strategic Delivery Office"

- Pro: Emphasizes delivery and execution

- Con: "Delivery" might be confused with IT delivery

## Final Recommendation Table

| Name | Clarity | Strategic Positioning | Accuracy | Simplicity | Overall Rating |
| --- | --- | --- | --- | --- | --- |
| Business Solutions & Portfolio Office ⭐ | ⭐⭐⭐⭐⭐ | ⭐⭐⭐⭐ | ⭐⭐⭐⭐⭐ | ⭐⭐⭐⭐ | 9.5/10 |
| Enterprise Solutions & Transformation | ⭐⭐⭐⭐ | ⭐⭐⭐⭐⭐ | ⭐⭐⭐⭐ | ⭐⭐⭐⭐ | 9/10 |
| Strategic Planning & Portfolio Office | ⭐⭐⭐ | ⭐⭐⭐⭐⭐ | ⭐⭐⭐⭐ | ⭐⭐⭐ | 7.5/10 |
| Portfolio & Change Management Office | ⭐⭐⭐⭐⭐ | ⭐⭐⭐ | ⭐⭐⭐⭐⭐ | ⭐⭐⭐ | 8/10 |
| Business Transformation Office | ⭐⭐⭐ | ⭐⭐⭐⭐⭐ | ⭐⭐⭐ | ⭐⭐⭐⭐⭐ | 7.5/10 |
| Program Management Office (PMO) | ⭐⭐⭐⭐ | ⭐⭐⭐ | ⭐⭐⭐ | ⭐⭐⭐⭐⭐ | 7/10 |

## My Final Recommendation ⭐

### "Business Solutions & Portfolio Office"

Why This Wins:

- ✅ Accurate: Describes what they actually do (portfolio management + solutions support)

- ✅ Clear: No confusion with process optimization (that's embedded in BUs)

- ✅ Professional: Corporate-standard terminology

- ✅ Flexible: Can shorten to "Portfolio Office" day-to-day

- ✅ Appropriate: Right level for executive function reporting to CEO

- ✅ Timeless: Won't sound dated or trendy in 5 years

Short Name for Daily Use: "Portfolio Office"

- "Check with Portfolio Office on that"

- "Portfolio Office meeting next Tuesday"

- "Email portfoliooffice@ with your request"

Complete Naming:

Official: Business Solutions & Portfolio Office

Head: Head of Business Solutions & Portfolio (or Chief Solutions Officer)

Daily: Portfolio Office

Email: portfoliooffice@company.com

Abbreviation: BSPO (if needed, though most will just say "Portfolio Office")

Sub-teams:

├─ Portfolio & Demand Management Team

├─ Change Management Team

└─ Continuous Improvement Support (NOT "Business Excellence CoE")

## Implementation: Rename in 30 Days

WEEK 1: DECISION & PREPARATION

├─ Day 1-2: Get executive approval (CEO, COOs, CTO)

├─ Day 3-4: Prepare communication (announcement, FAQs, org chart updates)

├─ Day 5: Notify Head of BPM (discuss name change, positioning)

WEEK 2: INTERNAL LAUNCH

├─ Day 8: Announce to Portfolio Office team first (they're becoming "Business Solutions & Portfolio Office")

├─ Day 9: Update internal systems (org chart, intranet, email signatures)

├─ Day 10: All-hands announcement (email + town hall if possible)

WEEK 3-4: ROLLOUT & REINFORCEMENT

├─ Update all documentation (process docs, templates, presentations)

├─ Update email addresses and distribution lists

├─ Launch FAQ page on intranet ("Why did BPM become Portfolio Office?")

├─ Reinforce in all communications (use new name consistently)

DAY 30: COMPLETE

├─ All references updated (BPM → Business Solutions & Portfolio Office)

├─ Team using new name consistently

├─ Stakeholders clear on name and scope

└─ New name established ✅

## Summary: Your Answer

Question: Would you have other names for the BPM department? People find the name confusing as it refers to process management, which is not the core task.

Answer: ⭐ "Business Solutions & Portfolio Office" ⭐

Why:

- Accurately describes what they do (portfolio + solutions support, NOT process optimization)

- Eliminates confusion (process optimization is now embedded in BUs)

- Professional and clear

- Easy to shorten ("Portfolio Office")

- Appropriate for executive-level function

Alternative (if you want more transformation focus): "Enterprise Solutions & Transformation"

Avoid: Keeping "BPM" or "Process" in the name (creates wrong expectations)

You now have: Complete rebranding strategy, communication plan, and implementation timeline. Ready to rename! 🎯

# Questions used for Claude.ai

- Our company's it department has historically only created and maintained own software (own software development). Increasingly we are also working with external (saas) software, that is often also integrated or interfaced with other external or internal software. However the IT organisation is not equiped for this new normal. Adding to that, we want to start doing AI projects, and leveraging the vast amount of data we have. Our IT department now consists of a head of IT applications, an operations manager and several teams led by a team success manager that consist of developers, testers and functional analists. No project managers, no business analists, no architects .. Also these teams are trying to work via scrum methodology. how should our future IT department look like, which structure, roles, capabilities, functions, ...

- I like to dig deeper on all of it. I really like the stream-aligned teams, owning business domains, instead of purely dividing the teams based on programming language or software product

- Can you tell me more about the product owners. Should they be situated in it, and what people should we be looking for?

- How do you then situate a product owner vs a project manager during the implementation of a new saas solution or during development of a new in-house built solution

- Final question for tonight, what books and reading would you suggest for the cio that needs to initiate and implement all of this

- One area is not clear yet, the business has a lot of project ongoing or in the pipeline, usually with a software or technology component, and a very long list of change requests. Who manages that, and most of all the entire portfolio and priorities? I see what a PO can do within a domain, but what if multiple domains require the same resources

- Can you make a document export of all of the above, adding detailed job descriptions for each role

- let's personalise this a bit. We currently have a head of IT Applications and a head of IT Systems and a BPM department. All reporting directly to the CEO. IT Application is responsible for all related to applications, own development and Saas, and also support regarding applications. IT Systems is responsible for all infrastructure, hardware, networks, security, and support in that area. BPM currently does a mix of project and change request intake from the business, prioritisation, high level business analysis to judge the request and project management for bigger projects. Within IT applications there is the head of, and as direct reports the operations manager who has all the teams reporting to him (development teams centered around applications, integration development team, support team) and the head of data who is building a team on all related to data. Can you adjust the blueprint taking this into account? BPM and IT applications could merge into one organisation, that seems the way ahead, but IT systems will most likely stay separate from this exercise (although suggestions to move around responsibilities are welcome). We have 3 main operational business units, and supporting departments like sales, finance, HR, legal, claims, ... As a company we value flexibility, entrepreneurship, agility, lean and robustness (no extremely risky buisness).

- We are a logistics company, with a shipping business unit, a ports business unit (terminals that we operate) and cargo door tot door logistics buisness unit. Cargo has separate systems, shipping and ports share a legacy system, but it's on the immediate roadmap to replace that system by two separate systems, as it should be. BPM team has a headcount of 5. IT Applications of around 80. Our main applications are the shipping and terminal system, a separate terminal system for cars, a TMS for cargo (new project for replacement started), customs logic interwoven in the shipping and ports system, lots of integrations for EDI to and from customers and other platforms, a billing system (currently own development, future might be saas), a CRM (currently own development, future might be saas), an HRIS sap being implemented, an HR system for our seafarers (currently own development, future might be saas), and databricks/powerbi for data. Preference is to promote internally.

- two more area's I'd like to see clarified: the Product Owners from the business: would this be a full time job? Because you'd be looking at good, knowlegeable senior people. Could this be a part of their other responsibilities? And my second questions about the enterprise architecture. I definitely see the need for it, and we have no architecture at the moment, and the company has no experience with it. So I think realistically we start with one EA. However I know and EA can also be very theoretical and ivory tower style, and that will not fit in our company. How to find a balance between having an EA function that really works for us?

- can you dig a bit deeper into the role of business analyst? Feels like a crucial part

- One more topic to explore, service desk for applications, applications support. This currently does not run well. How to organize, which reporting lines, which procedures, which type of people. So that when users from the business call, they can reliably be helped

- 2 boundaries are not fully clear: 1. Between tier 2 and the value delivery teams concerning application configuration and for example edi onboarding. 2 between support and vendor management in case of support for third party applications

- A few more questions: in the organization chart, for the stream aligned teams, I think initially ports needs to be split up between cars and cargo (containers and trailers). We also have a lot of Customs-specific functionalities and development, from a shipping and ports perspective. Should that be a separate team (very specific separate topic and knowledge), or be integrated in ports and shipping teams? Similar for customer and commercial solutions: we have sales in the three business units separately, integrate in each team, or combine in a separate stream aligned team? (they have separate COO's from a PO perspective). What about the claims tool and functionality (not a major tool), inside one of the other teams? Some other solutions we have that are missing on the stream aligned teams: a tool for our vessel fleet (fleet management tool), a tool for our terminal equipment, maintenance and workshops. Also, from the shipping side, we have 2 legacy shipping tools, one used for part of our business (result of merger), and the other combined with port functionalities used in the majority of our business. In future shipping system this will be combined, but currently a separate team of developers, analyst and PM. 2. I don't see anything about vendor and partner management in the organization chart. Where to place that? 3. Where to place the service desk in the organization chart?

- Would it make sense to keep the bpm function outside of it, and what functions would make sense to place there? It might be a political decision to not integrate it within it.

- Would it not make sense to place teams or roles for Business Process Optimization and business excellence and continuous improvement directly within the three business units, with the expertise from within the business unit?

- Would you have other names for the bpm department(considering the role it plays). People find the name confusing as it refers to process management, which is not the core task